WORKING IN partnership

TO dELIVER resultS

Vietnam Partnership Report 2005

An Informal Report Prepared
for the Consultative Group Meeting for Vietnam

Hanoi, December 6-7, 2005

ACKNOWLEDGEMENTS

This volume is the product of teamwork and partnerships in Vietnam, and brings together contributions from many of the joint Government-donor-NGO partnership groups, all working together to help Vietnam achieve its development targets, to improve the co-ordination and to make delivery of Official Development Assistance (ODA) more effective.  Its production was only possible through the co-operation, contributions and active support of a wide range of development partners, including Government staff, donors and NGOs. Key contacts (though not necessarily leaders) of the groups, most of which have reported in this volume, are currently as detailed below.  Non-inclusion in this volume does not imply non-activity on the part of a partnership group.

Poverty Working Group/Poverty Task Force	Cao Viet Sinh (MPI); Martin Rama/Doan Hong Quang (World Bank); Nguyen Tien Phong (UNDP)

Partnership to support National Target Programs	Nguyen Hai Huu/ Tran Phi Tuoc (MOLISA);

Do Thanh Lam (UNDP)

Partnership to Assist the Poorest Communes 	Vuong Xuan Chinh (MPI)

Gender Action Partnership  			Tran Mai Huong (NCFAW)

ISG Environment	Nguyen Thi Tho (MoNRE)

People’s Participation’s Working Group 	Nguyen Thi Le Hoa (Oxfam GB)

Partnership on SOE Reform & Equitization	Daniel Musson (WB); Nguyen Danh Hao (IMF)

Partnership Group for SME Promotion and  	Nguyen Van Trung (MPI); Kazuhiro Iryu (EOJ);

Private Sector Development 	Philippe Scholtes (UNIDO)

Financial Sector Working Group	Dang Anh Mai (SBV)

Trade Reforms Working Group	Martin Rama/Nguyen Minh Duc(World Bank)

Vietnam Business Forum		Sin Foong Wong (IFC)

Education Working Group	Tran Ba Viet Dzung (MoET); Chu Shiu-Kee (UNESCO); Steve Passingham (DFID)

Health Sector Working Group			Le Thi Thu Ha (MoH); Hans Troedsson (WHO)

HIV/AIDS Technical Working Group		Nancy Fee (UNAIDS)

Forest Sector Support Program and Partnership	Nguyen Tuong Van/Paula Williams (FSSP&P MARD)

Natural Disasters Mitigation Partnership		Nguyen Si Nuoi/Nguyen Thanh Phuong (MARD)

ISG-MARD					Le Van Minh  (MARD)

Transport Partnership Group	Truong Tan Vien (MoT); Masayuki Karasawa (JBIC)

HCMC ODAP			Trang Trung Son (HCMODAP)

Urban Forum					Pham Khanh Toan (Ministry of Construction)

Legal Reforms Partnership 			Luu Tien Dung (UNDP)

Public Administrative Reform Partnership 	Pham Van Diem (MoHA); Nguyen Tien Dung (UNDP)

Public Financial Management Partnership	Nguyen Ba Toan (Ministry of Finance)

Partnership group on Aid Effectiveness		Ho Quang Minh (MPI); Jordan Ryan (UNDP)

Bo Thi Hong Mai (World Bank) managed production of this volume and coordinated the Theme Notes from the Development Partnership Groups. Nguyen Thuy Ngan (World Bank) provided invaluable support. Photo by Trinh Quang Vinh.

Further copies of this report are available from the Vietnam Development

Information Center, Ground Floor, 63 Ly Thai To, Hanoi, and at www.worldbank.org.vn , www.un.org.vn and www.vdic.org.vn

TABLE OF CONTENTS

- INTRODUCTION AND OVERVIEW 	1

POVERTY WORKING GROUP/PTF…………………………………………

PARTNERSHIP TO SUPPORT THE NATIONAL TARGET PROGRAMMES……

- PARTNERSHIP TO ASSIST THE POOREST COMMUNES

- GENDER ACTION PARTNERSHIP

- ISG ENVIRONMENT

- PEOPLE'S PARTICIPATION WORKING GROUP

- PARTNERSHIP ON SOE REFORM & EQUITIZATION

- SME PARTNERSHIP GROUP ………………………………………………………………….

- FINANCIAL SECTOR WORKING GROUP………………………………………………….

TRADE REFORMS WORKING GROUP…………………………………………………….

HEALTH SECTOR WORKING GROUP………………………………………………………..

EDUCATION WORKING GROUP…………………………………………………………….

FOREST SECTOR SUPPORT PROGRAM AND PARTNERSHIP…………………………….

- NATURAL DISASTER MITIGATION  PARTNERSHIP

- AGRICULTURE AND RURAL DEVELOPMENT (ISG)

TRANSPORT PARTNERSHIP GROUP…………………………………………………………

URBAN FORUM……………………………………………………………………………….

LEGAL REFORMS PARTNERSHIP ……………………………………………………………

PUBLIC ADMINISTRATIVE REFORM PARTNERSHIP ……………………………………..

PUBLIC FINANCIAL MANAGEMENT PARTNERSHIP

- ACRONYMS AND AbbreviationS

ADB		Asian Development Bank

ASEAN		Association of South East Asian Nations

AFD		Agence Francaise de Developpement

CEPT 		Common Effective Preferential Tariff

CIDA		Canadian International Development Agency

CIE		Center for International Economics

CIEM		Central Institute for Economic Management

CPNET 		The government information network

CPRGS 		Comprehensive Poverty Reduction and Growth Strategy

CPLAR		Cooperation Program on Land Administration Reform

DANIDA		Danish International Development Agency

EU		European Union

FAO             	Food and Agricultural Organisation

GDP		Gross Domestic Product

ILO             	International Labour Organization

ISG		International Support Group

JICA		Japanese International Cooperation Agency

JBIC		The Japan Bank for International Cooperation

KfW		Kreditanstalt fur Wiederaufbau

LPTS		Legal Professional Training School

LMDG		Like-Minded Donor Group

MDG		Millennium Development Goal

MOJ		Ministry of Justice

MOT		Ministry of Trade

NGO		Non-governmental Organization

NORAD		Norway Agency for Development

NSCERD		National Steering Committee for Enterprise Reform and Development

ODA		Official Development Assistance

ONA		Office of National Assembly

OSS		One-Stop Shop

PPA       		Participatory Poverty Assessment

RPA		Regional Poverty Assessment

SDC		Swiss Development Cooperation

SIDA		Swedish International Development Agency

SPC		Supreme People’s Court

SPP		Supreme People’s Procuracy

UNDP 		United Nations Development Programme

UNODC		United Nations Office of Drug Control

UN             	United Nations

# UNFPA      	United Nations Population Fund

UNICEF     	United Nations Children's Fund

UNESCO    	United Nations Educational, Scientific and Cultural Organization

UNIDO        	United Nations Industrial Development Organization

UNV            	United Nations Volunteers

UNHCR               United Nations High Commissioner for Refugee

VDG		Vietnam Development Goal

VHLSS 		Vietnam Household Living Standards Survey

VNU		Viet Nam National University

SBV		State Bank of Vietnam

WB		World Bank

WHO          	World Health Organization

WTO		World Trade Organization

INTRODUCTION AND OVERVIEW

Introduction

- The past year has seen significant progress in achieving a more efficient way of delivering and managing official development assistance (ODA) in Vietnam based on an ever increasing degree of Government ownership of the partnership agenda. The international community is committed to following Vietnam’s long-term goals and strategy. Donors have extended great support to the preparation of Vienam’s Socio-Economic Development Plan 2006-2010 and commit to assist Vietnam implement the new SEDP and achieve its development goals.

The development partnerships highlighted in this volume have made significant contributions to Vietnam’s poverty reduction. The partnership groups are now working to ensure that the approaches and principles of the Comprehensive Poverty Reduction and Growth Strategy (CPRGS) would be integrated into to the new SEDP and reflected in the sectoral strategies in order to make it the new guiding framework for ODA.

Challenges in enhancing aid effectiveness, improve coordination, reducing transaction cost, while maintaining strong Government ownership, remain. But overall Vietnam is on track to achieve the ambitious targets it has set for itself.

2.	The main part of the report brings together a series of notes, prepared by 20 development partnership groups (see content page), setting out the progress they have made in meeting development outcomes since their last report to the Consultative Group Meeting  and in bringing about significant changes in their sector. Groups highlighted this changed behaviour by answering four ‘key questions’ (Box 1) that form the structure of the notes to be found later in this report; key highlights are presented in Box 2.  Most of the groups consist of Government and donor representatives, and many also include both international and local NGOs.

Box 1: The four ‘Key Questions’

1) What progress has your partnership group made over the past six (or twelve) months ?

2) What work has your partnership carried out in supporting the Government, central and provincial agencies to prepare the draft of new SEDP for 2006 - 2010 and sectoral strategies and programs ?

3) Over the next twelve months, what concrete actions will your group take, including to align donor support to sectoral strategies and Vietnam's socioeconomic development plan ?

- 4) What are your revised success criteria - or milestones- for 2006 to ensure your partnership group reaches its development outcomes? It may be useful to put this in a matrix format, with Date, Planned Activities, Outcomes, and Key Players as the column headings.

Box 2: Examples of Activities of Partnership Groups in the past six (or twelve) months Poverty Reduction - Supporting the development of Vietnam’s Socio-Economic Development Plan 2006-2010 and its consultation process with all stakeholders. - Strengthening planning processes in the provinces National Target Programme - Supporting the development and implementation of the National Target Programme on Poverty Reduction and Programme 135 Poorest Communes - A Final Report on the ASEM-EU Grant utilization was published in February 2005, which summarized the main outputs, progress and achievements of the Partnership to Assist the Poorest Communes (PAC). - Developing a new concept note for the next phase of the partnership Gender - Organizing a series of consultations throughout the country on SEDP to make sure the plan is gender responsive. - Framework mapping of key gender-related activities in Vietnam. Environment - Assisting the development of the next Five-year Plan for the natural resources and environment sector - Reviewing legal system for natural resources and environment People’s Participation - Providing support to drafting process of the Vietnam’s SEDP 2006-2010 - Supporting a wide-range of activities related to promotion of people’s participation and decentralization. State Owned Enterprise Reform - Disseminating and sharing information and mobilizing assistance for the formulation and implementation of SOEs reform programme SME promotion and Private Sector Development - Contributing to the formulation of the SEDP 2006-2010 and stronger aligning government agencies and donor objectives under a common framework for improved coordination and resource efficiency. - Seven thematic working groups have been very active in coordinating development assistance at different levels. Financial Sector - Discussing the progress of banking reform agenda and assistance needs of the State Bank of Vietnam as well as a coordinating donor’s assistance in financial sector. - Supporting the implementation of government’s financial sector reform program. Education - Providing a joint comment on both content and the format to strengthen the Five-Year Strategic Education Development Plan 2006-2010 - Preparing a working note on operationalizing UN Girls’ Education Initiatives – a global strategy. Box 2: Examples of Activities of Partnership Groups in the past six (twelve) months (cont.) Health - Identifying ways to improve the management and effectiveness of ODA in the health sector. - Preparing the health sector plans and strategies and introducing the Sector Programme Support (SWAP) Forestry - Supporting the preparation of supporting legal documents for the revised Law on Forest Protection and Development and other important legal decrees and regulations for the sector. - Supporting the formulation of the National Forestry Strategy 2006-2010 and SEDP - Establishing an updated database on ODA support to the forest sector, to complement the data already collected by the International Support Group of MARD. Natural Disaster Mitigation - Developing a more comprehensive Action Plan of the NDP Partnership aiming at strengthening coordination while contributing more actively to sectoral priorities and the implementation of the CPRGS - Facilitating discussions and providing inputs to ensure that a holistic approach for disaster reduction is clearly reflected in MARD Five-Year Plan and subsequently the SEDP Agriculture and Rural Development ## Supporting the development of the sector FYP (from Mar to Dec 2005), and support its implementation - Supporting MARD and donors in formulation of the RWSS Sector Support partnership. - Supporting MARD institutional development activities, strengthening capacity in formulation and development ODA M&E system; strengthen capacity in management of ODA, INGO and FDI for the ARD sector Transport - Consolidating information and experience on transport projects and programs to encourage the alignment of supports and the improvement of aid effectiveness. - Focusing group discussions on the Five-Year Plan and three specific issues: “Road Maintenance,” “Traffic safety” and “Hanoi Urban Transport”. Urban Forum - Reorganizing the Secretariat and the new coordinator for the forum was appointed. - Conducting studies, organizing conferences and workshops, supporting training courses Legal reform - The Strategy for the Development and Improvement of Vietnam’s Legal System to the Year 2010, the Direction for the Period of up to 2020 and the Judicial Reform Strategy to 2020 were approved. - The Legal Partnership Forum has been promoting discussion, coordination and strategizing between Vietnamese agencies as well as well as foreign partners, in order to further development and improvement of Vietnam’s legal and judicial systems. Public Finance Management - Increasing information exchange to improve the quality of the cooperation between different stakeholders. - Members of the partnership have jointly implemented the state budget and financial management reforms Public Administration Reform - Partnership activities have become more diverse, combining both formal and informal, bilateral and multilateral activities. - Providing opportunities for donors to contribute their comments and ideas, and to recommend on how to improve management and coordination in the course of implementing the PAR Master Programme of the Government, linking PAR efforts with HEPR ect.

The Drive to Partnership – Increasing efficiency

- Vietnam has been one of the major recipients of ODA in recent years. Donors have committed USD14.597 billion in aid during the period of 2001-2005. Although aid inflow is more modest when compared to the size of the Vietnamese economy, strong efforts from both government and donor community are required to ensure best possible use of the resource.

In order to minimise ODA transaction costs and improve effectiveness of this resource, Vietnam and the donors have been cooperating to harmonize the ODA process and procedures in compliance with the national system and improving the effectiveness of foreign aid. Indeed, Vietnam has been working along the three pillars of the Paris Declaration on Aid Effectiveness and was the first country to localize the three principles of ownership, alignment and harmonization and translate them into practice by releasing the Hanoi Core Statement  (Box 3).

The “Hanoi Core Statement” was adopted by donors at the at The Mid-term Consultative Group Meeting for Vietnam, held in Can Tho city on June 2-3, 2005, and approved in principle by the Prime Minister of Vietnam in September 2005.

Box 3: Hanoi Core Statement on Aid Effectiveness Ownership, Harmonisation, Alignment, Results Background Statement We, the Government of Vietnam and development partners, agree to take far-reaching and monitorable actions to make aid more effective as we look ahead to the achievement of Vietnam’s Development Goals (VDGs) by 2010, and the Millennium Development Goals (MDGs) by 2015. We recognise that while volumes of aid and other development resources are increasing to achieve the VDGs, aid effectiveness must also increase significantly to support Vietnam’s efforts to strengthen governance, to improve development performance, and to enhance development outcomes. We agree to localise the conclusions of the High Level Forum on Aid effectiveness held in Paris in March 2005 ("The Paris Declaration") to reflect circumstances in Vietnam. We resolve to increase the impact of aid in reducing poverty and inequality, increasing growth, building the capacity of human resources and institutions, and accelerating achievement of the VDGs. Partnership Commitments Developed in a spirit of mutual accountability, these Partnership Commitments reflect the ambitions and structure of the Paris Declaration and build on the on-going efforts and experiences of development in Vietnam. ## 1. Ownership ### Vietnam defines operational development policies - The Government of Vietnam exercises leadership in developing and implementing its 5 Year Socio Economic Development Plan (SEDP) through a broad consultative processes which integrates overseas development aid into mainstream planning (Indicator 1). - The Government of Vietnam further strengthens its leadership role in co-ordinating aid at all levels. ## 2. Alignment ### Donors align with Vietnam's strategies and commit to use strengthened country systems - Donors base their support on the Government of Vietnam’s SEDP and related national, regional and provincial, and sectoral plans (Indicator 2). - Donors base dialogue on the poverty reduction and growth agenda articulated in the SEDP. - The Government of Vietnam and donors establish mutually agreed frameworks that provide reliable assessments of country systems, procedures and their performance. - Donors use country systems and procedures to the maximum extent possible. Where use of country systems is not feasible, donors establish additional safeguards and measures in ways that strengthen country systems and procedures (Indicator 5, 6 and 8). - Donors avoid creating parallel structures (PMUs) for day-to-day management and implementation of aid-financed projects and programmes (Indicator 3). - Donors phase out paid incentives for government officials administering aid financed activities and do not establish incentives in future activities. ### Vietnam strengthens institutional capacity with support from donors; ### Donors increasingly use government systems - The Government of Vietnam integrates capacity building objectives in the SEDP and related national, regional and provincial, and sectoral plans and leads a comprehensive capacity building programme with co-ordinated donor support (Indicator 4). - The Government of Vietnam undertakes reforms, such as public administration reforms (PAR), that promote long-term capacity development. - The Government of Vietnam undertakes reforms to ensure that the legal framework, national systems, institutions and procedures for managing aid and other development resources are effective, accountable and transparent. - The Government of Vietnam and donors commit sufficient resources to support and sustain reform and capacity building in public procurement and public financial management. - Donors progressively rely on the Government of Vietnam's procurement system once mutually agreed standards have been attained (Indicator 5). - Donors progressively rely on the Government of Vietnam’s public financial management system once mutually agreed standards have been attained (Indicator 6). - The Government of Vietnam publishes timely, transparent and reliable reports on budget planning and execution (Indicator 6). - Donors enhance the predictability of future aid through transparent decision making processes, provide reliable indicative commitments of aid over a multi-year framework (including aid commitments covering multi-year expenditures of projects) and release aid in a timely and predictable fashion in relation to the Government of Vietnam's budget cycle (Indicator 7). - The Government of Vietnam, supported by donors, develop specialised technical and policy capacity for social and environmental analysis (SIA and EIA) and enforcement of legislation (Indicator 8). ## 3. Harmonisation and Simplification ### Donors implement common arrangements and simplify procedures - The Government of Vietnam and donors jointly conduct and use core diagnostic reviews such as Country Financial Accountability Assessment (CFAA), Public Expenditure Review (PER), Country Procurement Assessment Report (CPAR), etc, and the Government of Vietnam and donors work together to share other reviews and carry out more joint reviews (Indicator 9). - Donors rationalise their systems and procedures by implementing common arrangements for planning, design, implementation, M&E and reporting to Government of Vietnam on donor activities and aid flows (Indicator 10). - Government of Vietnam and donors increasingly use programme based approaches (Defined in Box 3.1, Chapter 3 “Sector Approaches” of Harmonising Donor Practices for Effective Aid Delivery, Volume 2 (OECD, 2005)) (Indicator 11). - Decentralisation and delegation of authority to the country level is maximised for each donor (Indicator 12). ### Complementarity: more effective division of labour - The Government of Vietnam provides clear views on donors’ comparative advantage, different aid modalities and on how to achieve donor complementarity at country or sector level. - Donors make full use of respective comparative advantage at sector level by aligning support and agreeing, where appropriate, lead donors for co-ordinating programmes, activities and tasks, including delegated co-operation. ### Incentives for collaborative behaviour - Government and donors devise practical means to encourage harmonisation, alignment, and results based management. ## 4. Managing for results ### Managing resources and improving decision-making for results - The Government of Vietnam and donors jointly use results-oriented performance assessment frameworks to maximise aid effectiveness and manage implementation of the SEDP and related national, regional, provincial and sectoral plans (Indicator 13). - Donors link country programmes and resources to achieve results that contribute to, and are assessed by, Government of Vietnam performance assessment frameworks, using agreed indicators. ## 5. Mutual Accountability ### Government of Vietnam and donors are accountable for development results - The Government of Vietnam and donors jointly assess, and carry out annual independent reviews, on progress in implementing agreed commitments on aid effectiveness and improved development outcomes through existing and increasingly objective country level mechanisms (Indicator 14). - Donors provide timely, transparent and comprehensive information on aid flows and programme intentions to enable Government of Vietnam to present comprehensive budget reports to legislatures and citizens, and co-ordinate aid more effectively.

- 4. 	Since its official launch in Vietnam in 1998, the Partnership Approach has continuously served as a useful and important instrument to improve coordination, promote open dialogues between government agencies and development partners. The ‘Partnerships Journey’ is still proving fundamental to successful country-led development in Vietnam. The partnership groups in general have moved to much deeper, broader involvement in the country’s development strategies and have made substantial progress in the past year. Some groups made significant steps along the six-stage partnership journey in the past year (Chart 1).

Chart 1: The Partnership Journey

- Source: Consultative Group for Vietnam (2001)

(vi) implementation, monitoring and evaluation of outcomes, and feedback.

(v) clarity of tasks and funding

(iv) joint development of a detailed shared action plan

(iii) agreement of principles in finding solutions

(ii) a common technical diagnosis

(i) shared information and understanding

5.	More partnership groups have been moving toward the formal structure (for example: the International Support Groups of MARD and MoNRE), which has proved as useful and effective in increasing understanding, transparency and coordination between Government agencies and international donors. The formal structure also helps increase the Government ownership of the process and promote better coordination within the government system, which in turn improve the effectiveness of development programs in general and donor assistance in particular.

On the other hand, the format of an information-sharing forum has been found to be an effective mechanism for some groups and their members. This format also provides the partnership more flexibility to raise new issues for discussions and adapt new focuses, although it might not always link to any specific policy-making context.

Each format has its own strength and weakness. It is clear that there is no “one size fits all”, so members of the groups should choose the model that is best for them to achieve their desired outcomes. The success of a working group also depends on the degree of flexibility in working structures and form as the environment changes. Many groups carry out regular reassessment of their activities, mandate, organization and direction to increase the effectiveness and be more adaptable to the changes of the new situation.

- The degree of Government ownership of partnerships continues to increase in the past year, with 15 groups are now chaired by Government (for example, the Financial Sector Working Group, Health Sector Working Group, Urban Forum), and some (for example, ISG at Ministry of Agriculture and Rural Development, Forest Sector Support Program and Partnership, ISG at Ministry of Natural Resources and Environment) entirely managed and supported from within existing Government structures. Strong Government ownership is desirable and necessary to ensure the success of partnership.

- Despite progress and success stories in the past year, many issues remain to be solved on the path of building better partnership for development.

Partnership groups are operating at different levels of effectiveness. Different groups face very different and sometimes wide ranging obstacles in improving partnership effectiveness. Some even have difficulties in convening regular group meetings. The issue of possible overlapping work between different groups has also been raised.

- Factors for success: Attitude, Flexibility and adaptability, Ownership, Commitment, Wide, multi-level support, Funding, Technical Knowledge.

- Looking ahead

8.	Looking forward, the principles and approach of CPRGS have been integrated into Vietnam’s next Socio-Economic Development Plan (SEDP) 2006-2010. The new SEDP could serve as the main coordinator of ODA activities over the period.

Partnership groups have been facilitating the support to SEDP formulation. As useful fora for information exchange, policy dialogues and technical discussion between development partners, the partnership groups will continue to be a good mechanism to improve coordination, making the best possible use of donor support and enhance government ownership in implementing the new Five-Year Plan.

9.	The experience in Vietnam has shown the benefits of donors and NGOs working in partnership with Government to support all stages of the development process. Ensuring a stronger partnership between all stakeholders is becoming even more crucial to help Vietnam achieve ambitious development goals it has set for itself.

The Theme Notes

- 10.	There was strong support for documenting the work of partnerships throughout 2004, and to lay out the path ahead.  Thus it was agreed that Partnership Groups should produce brief theme notes answering the ‘key questions’, detailed in Box 1.  These notes form the body of this report.

- Further information and bibliography

Further information on the Partnerships in Vietnam can be obtained from:

www.un.org.vn , www.undp.org.vn , www.vdic.org.vn , www.worldbank.org.vn

- The following documents provide more detailed information about the partnership approach and the CPRGS in Vietnam.

Consultative Group Meeting for Vietnam (December 2001). Putting Partnership to Work in Vietnam - Informal report for the Consultative Group Meeting, Hanoi.

Consultative Group Meeting for Vietnam (June 2002). Putting Partnerships to Work in Vietnam: Update.  An Informal Report for the Mid-Term Consultative Group Meeting, Ho Chi Minh City.

Socialist Republic of Vietnam (SRV) (2002).  Comprehensive Poverty Reduction and Growth Strategy, Hanoi.

World Bank with Asian Development Bank (2003).  Poverty -  Vietnam Development Report 2004.  Hanoi.

Consultative Group Meeting for Vietnam (Dec 2004). Partnership for Development.  An Informal Report for the Consultative Group Meeting, Hanoi.

World Bank and others. 2004. Vietnam Development Report 2005 – Government. Hanoi.

Partnership Group on Aid Effectiveness, 2004. Harmonisation and Alignment for Greater Aid Effectiveness in Vietnam - Report 2004. Hanoi

Consultative Group Meeting for Vietnam (December 2004). Moving Towards 2010 -  Informal report for the Consultative Group Meeting, Hanoi

Mid-term Consultative Group Meeting for Vietnam (June 2005). Moving Towards 2010, Informal report for the Consultative Group Meeting, Hanoi (Mid-year Update)

# POVERTY WORKING GROUP / POVERTY TASK FORCE

Introduction

The Poverty Task Force (PTF) is a Government-Donor-NGO forum for poverty analysis and strengthening the poverty focus of policy making and development planning in Vietnam. Since its inception in 1999, the PTF has supported the Government in a range of tasks including collaborative analytical work and activities associated with the development of a poverty reduction strategy (the Comprehensive Poverty Reduction and Growth Strategy - or CPRGS). Meetings are held several times a year and comprise representatives from government ministries, from the donor community and from local and international organisations. Where the agenda seems relevant, representatives from provincial governments are sometimes invited to attend. Each meeting is co-chaired by the Ministry of Planning and Investment (MPI) and a representative from the donor community (which rotates every meeting). In the past six months, however, a number of changes have taken place that perhaps call for a rethinking of the mandate of the PTF.

Supporting the development of the Socio-Economic Development Plan

In 2004, the government decided that the CPRGS approach and principles were to be integrated into the next socio-economic development plan (SEDP) 2006-2010. Many donors and NGOs were keen to ensure that this was happening, as this would make it possible for them to use the new SEDP as a framework for aligning their development assistance to Vietnam. As a consequence, many donors and NGOs were interested to engage with the development of this plan.

At the PTF meeting in April 2005, the preparations of sector five year plans and the national Socio-Economic development Plan (SEDP) were reviewed and donor-NGO support to their formulation were discussed. MPI proposed an action plan for arranging broad-based consultation in the preparation of the SEDP and invited donors to support these activities. Discussion included other support activities such as developing a results-based approach and integrating an appropriate M&E system into the plan and donor support to strengthening M&E of the SEDP.

In the past six months, the main focus of donor-NGO and government has continued to shift even more to the development of the SEDP and line ministry five year plans. Donors and NGOs interacted with the planning process through a number of mechanisms. For example, information on the SEDP planning process was shared through a large gathering of donors and NGOs called “the friends of the five year plan”, chaired by the Country Director of the World Bank. And support to the sector five year plans was often provided through technical task forces operating under the various sector partnership groups.

Donors have supported a wide–ranging consultative process on the SEDP. Meetings have taken place with local officials in three regional workshops. Donors and international NGOs have supported consultations with communities in nine sites around the country. Processes have also been supported to gather feedback from the domestic private sector and local associations and NGOs. The government has also conducted its own consultations with academics and stakeholders within government.

CPRGS rollout: strengthening planning processes in the provinces

Over the past 6 months, the rolling-out of CPRGS at sub-national levels of government has continued to move forward. Donors and NGO, in close partnership with MPI, have further introduced the concept of results-based planning in about ten provinces. These approaches have subsequently been adopted in the five year plans of these provinces such as (1) a much more open and consultative process in plan preparation; and (2) adopted the use of modern planning tools such as log frames and policy matrices.

During the past period, MPI also produced a first draft of a planning manual, utilizing the valuable lessons and training material from the on-going CPRGS roll-out. The planning manual will serve as a practical guideline for planning staff at all levels of government. A workshop to discuss the first draft was held in November.

# Possible issues related to poverty analysis and pro-poor planning that need to be tackled in 2007

As the partnership ‘landscape’ continues to evolve, a rethinking of the mandate of the PTF might be needed. But a defined Government-Donor-NGO partnership group will continue to be needed for handling technical aspects in the areas of (a) poverty analysis, and (b) strengthening the poverty focus of policy making and development planning in Vietnam. Three broad important areas of attention can be identified:

1. There are likely to be energetic government efforts to revise the SEDP after it is discussed at the National Assembly and the CG meeting. Donors and NGOs will be keen to support the government in this revision process and on helping maintain a focus of the plan on delivering pro-poor growth. They will be particularly willing to assist with the design of a matrix that links objectives to concrete policy reform measures. And they are also interested in helping to integrate a proper M&E framework into the SEDP, ensuring such a framework includes a set of input, output and outcome indicators linked to the core objectives. A final area of interest is ensuring a better link between plans and budgeting and strengthening the connection between performance indicators and budgetary decisions.

2. The Vietnam Academy of Social Sciences (VASS) has assembled a team of researchers who will prepare a ‘poverty update’, using the latest living standard data from the VHLSS 2004.  The findings of this work would need to be presented to key stakeholders for the researchers to collect feedback on the results and to generate consensus around the current poverty situation in Vietnam.

3. Lastly, as donor efforts to develop a coherent approach to supporting MPI in its efforts to strengthen provincial level planning continue to make progress, there is likely to be a need to discuss such efforts with stakeholders. This would count in particular for the plans for establishing a comprehensive facility for Strengthening Provincial Planning Reforms (SPPR) with MPI.

PARTNERSHIP TO SUPPORT THE NATIONAL TARGET PROGRAMME ON POVERTY REDUCTION

AND PROGRAMME 135

1.	What progress has your partnership made over the past twelve months?

The key activities and achievements of the Partnership are:

- Support to programme development by Technical Design Working Groups

Seven Technical Design Working Groups (TDWG) with members from line ministries, donors and NGOs were established to provide technical assistance to the government to support the design of both the National Targeted Programme for Poverty Reduction (NTP-PR) and the Socio-Economic Development Programme for Most Difficult Communes in Ethnic Minority and Mountainous Areas (SEDEMA) for 2006-2010. The TDWGs helped consolidate existing experiences and lessons under NTP-HEPR 2001-2005 and Programme 135 and provided technical inputs to the design of the new programmes in the following areas:

1.   Financial management and budget allocation.

2.   Monitoring and evaluation.

3.   Targeting and establishment of poverty line.

4.   Capacity building, participation and vocational training

5.   Small scale infrastructure.

6.   Rural livelihood services.

7.   Social services (health, education, water supply and sanitation).

This support also included the identification of poor households using the new poverty criteria through a process supported by both UNDP and the World Bank.

In support of the design process for the poverty reduction programmes a series of consultations with local people, mass organisations, Government of Viet Nam Ministries and Agencies, donors and NGOs also took place at national, regional and local levels.

Working processes were developed to assist the preparation of SEDEMA and NTP-PR, taking into account the needs of the lead agencies, target groups, content and implementation arrangements. A national consultation conference was held by the Committee for Ethnic Minorities (CEM) on 21st June 2005 to discuss the recommendations made on the draft SEDEMA programme document.

The process of consultation for the NTP-PR culminated in a national conference held in Hanoi on 1st July 2005, inaugurated by Deputy Prime Minister Pham Gia Khiem. The conference was organised by the Ministry of Labour, Invalids and Social Affairs (MOLISA) and involved participants from key Party, National Assembly and Government Agencies, officials from provinces throughout Viet Nam, representatives from mass organisations, donors and international NGOs. The comments and suggestions made though the consultation processes provided a comprehensive approach, systematic views, and integrated methods in designing the programmes. As a result, amendments were made to the programme documents to make the two programmes become more comprehensive, more potentially successful and internationally acceptable before their submission to the government for formal approval in September 2005.

- Support to programme implementation through Technical Working Groups

Building on the work of the earlier Technical Design Working Groups, in addition to other specific donors’ support, TWGs have now been formed to support implementation of two programmes. The TWGs are proposed to support the provision of technical assistance in the development of guidelines and policies and the formulation and implementation of capacity building strategies, monitoring and evaluation systems, participatory planning, management and monitoring, and, financial planning and management. The TWGs will also support the development of these systems and processes in the localities.

- Development of the Partnership

Early draft programme documents of NTP-PR and SEDEMA were shared at a government-donor workshop held on 1st April 2005. This workshop marked the establishment of the joint government-donor partnership process for both programmes.

A Decision of the Prime Minister was made to set up the joint Government Steering Committee for both NTP-PR and SEDEMA. Following this, over the past three months, a series of discussions have been held with key donors and government on the formalisation of a single joint government-donor partnership to support the implementation of the programmes.

Background notes have been prepared and circulated for comments, reviewing the structure and operation of other similar partnerships and various models of agreement. A matrix was prepared comparing the various partnerships and out of this a framework for the partnership was developed.

A workshop was held on 26 October 2005 to discuss the purposes and framework of the joint government-donor partnership for the implementation of the NTP-PR and SEDEMA. Participants included government line ministries and agencies, donors, international and national NGOs and the media. The key priorities for the implementation of NTP-PR and SEDEMA and possible areas of support from the partnership included participatory planning, research and resource mobilisation, experience sharing and capacity building, monitoring and evaluation, people’s participation in implementation and learning from international experiences. The draft framework was presented to the workshop for further discussion and included the purpose of the partnership, its objectives, proposed partnership activities, working principles including its operation within the framework of the Hanoi Core Statement, membership, arrangements for a Secretariat, success criteria and the need for an action plan to be developed for 2006. A task force was formed to continue the development and implementation of the Partnership framework, its activities and work plan.

There was general support for the formalization of the single joint government-donor partnership for both programmes. NGOs also expressed their interest in sharing experiences and supporting the government’s poverty reduction programmes. It was pointed out that the programmes’ preparation and the Partnership have reached the stage when it is important to focus on specific, technical issues in considerable detail. A focus on regular, working-level information sharing and consultations among the government agencies, donor and NGOs, who are directly involved in the programme preparation and implementation, would allow more efficient, trust-based working relationships and improvements in the quality of the partnership dialogues. This would also avoid potential overlaps with other existing processes related to the support for general poverty reduction, e.g. the Consultative Group, the PRGS and the Poverty Task Force, or specific groups such as the sectoral partnerships for natural disaster mitigation, forest sector support and education.

At follow-up meetings between Mr Jordan Ryan, UN Resident Coordinator and Madam Nguyen Thi Hang, Minister of MOLISA the importance of joint government-donor partnership was discussed and agreed by both parties. Madam Nguyen Thi Hang, Minister of MOLISA, and CEM leader will be hosting a follow-up workshop to emphasise the government’s support for this partnership.

The draft framework for the partnership has now been circulated for comments from government, donors and NGOs and a formal inauguration of the partnership will take place in December.

2.	What work has your partnership carried out in supporting the government, central and provincial agencies to prepare the draft of the new SEDP for 2006-2010?

The NTP-PR and SEDEMA programmes are an integral part of the SEDP’s. Work in support of the development of the poverty reduction programmes, including the research, which resulted in the redefinition of the poverty line and the surveys to identify poor households has been used as a basis for identifying poverty reduction targets in the SEDP at national and provincial levels.

3.	Over the next twelve months, what concrete actions will your group take, including to align donor support to sectoral strategies and Vietnam’s socio-economic development plan?

The key activities/outputs of the Partnership over the next twelve months will include:

- Conduct consultations and provide technical support through the coordinated efforts of government agencies, donors and NGOs involved via the Technical Working Groups and other donor-supported activities for:

- The development of implementation and management guidelines for the programmes focusing on improving their targeting, participation and empowerment of the poor, prudent procurement and financial management, sustainability and strengthened result-oriented M&E.

- Strengthening capacity for programme planning, implementation, management and                participation at all levels, but especially at the commune level including support to localities to make their own plans for the next five years, developing a mechanism for program implementation including coordination activities, planning for research, resource mobilization and methods for effective utilization of resources; strengthening and enhancing training and practical skills for the officers of both programmes, as well as organize effective training activities;

- Establishment of information dissemination and learning practices including setting up a mechanism for experience sharing, consolidation and capacity building for poverty reduction program implementation; studying and learning from experiences of international organizations in poverty reduction.

- Facilitate localities to integrate these two programs as well as other programmes supported by donors in order to avoid wasting resources;

- Implement the work plan of the Partnership based upon the government’s work plan and including the formalisation of the Partnership framework, including a code of conduct, principles of operation and joint work planning when it is appropriate e.g. in M&E and its implementation.

- Identification by GOVN of other specific needs for donor support including needs for harmonisation, coordination and alignment by donors and NGOs in support of the programmes.

4.	What are your revised success criteria for 2006 to ensure your partnership group reaches its development outcomes?

The success criteria for the partnership are under discussion but will include the Government of Viet Nam’s ownership and leadership of the partnership; working mechanism within governmental organisations themselves and donors and NGOs; the development of partnership network; the level and quality of technical support provided through the Partnership for improving the implementation guidelines of both programmes; the active involvement of government, mass organisations and provincial representatives, donors and NGOs; increased harmonisation of donor support to the government’s poverty reduction programmes; and, the extent to which the formation of national and provincial level groups of donors and NGOs are providing support to the implementation of the two programmes.

Government should feel that the partnership is “adding value” to the successful development, implementation and management of its programmes and that the partnership brings about a significant reduction in transaction costs on all sides.

# Partnership assessment

Over the past twelve months key changes have included the development of the design of the two programmes through support to the evaluation of the first phases, support to the process becoming more participatory and consultative and creating a forum for experience sharing through support through the Technical Working Groups. These outputs have now led to the formalisation of the Partnership.

The Technical Working Groups are now providing active support to the key priority areas identified by MOLISA and CEM and over the next month the Partnership’s formal mechanism will be established.

In order for the work of the Partnership to be effective and to be able to meet the government’s priorities, its activities need to be based on the government’s work plan and with the active participation of government representatives in the Technical Working Groups.

The Partnership needs to develop a flexible working approach so that the wide range of stakeholder needs can be met.

PARTNERSHIP TO ASSIST THE POOREST COMMUNES (PAC)

Progress Report 2005

&

Concept Note (2006 to 2008)

PAC Secretariat

Department of Agricultural Economy

Ministry of Planning and Investment

Email: dagiamngheo@netnam.vn

## Progress Report 2005

  - Completion of the ASEM-EU Trust Fund

The previous work program of the Partnership to Assist the Poorest Communes (from 2002 to 2004) came to an end at the beginning of the year. In this period PAC was funded by an ASEM-EU Trust Fund (Grant Number TF050255). This grant agreement was signed between the Government and the International Development Association (IDA) in July 2002. Following two extensions to the grant period as approved by the Government and IDA, the grant expired on 31 January 2005. By this time, all the activities in the procurement plan were successfully completed with full disbursement from the Trust Fund, and the account was closed in April 2005.

  - Publications

A Final Report on the ASEM-EU Grant utilization was published in February 2005, which summarized the main outputs, progress and achievements of the partnership in this period. Several other reports were published, together with a CD containing all the studies conducted between 2002 and 2004 and the proceedings of the National Conference organized by PAC in November 2004:

- Socio-economic Development of the Poorest Communes: community perspectives and future prospects – PAC Synthesis Report (2002 to 2004) and National Conference Summary;

- PAC-CD: Proceedings of the National Conference on Socio-economic Development of Poor Communes held in November 2004;

- Studies on Commune and Village Cadre Training (PAC study);

- Sustainable Livelihood Opportunities and Resource Management in Coastline Communes Facing Special Difficulties (PAC Study);

- Handbook for Planning, Management and Supervision of Community Based Infrastructure (Handbook for commune and village cadres).

  - Effectiveness and impacts

The partnership activities were reviewed at a Summary Workshop held in January 2005. Based on the outputs from this workshop, an assessment of the overall effectiveness and impacts of the partnership as related to the objectives of the previous work program can be made as follows:

| PAC Objectives 2002 to 2004 | Effectiveness | Impacts |
| --- | --- | --- |
| Lesson learning from development projects and programs | +++ | ++ |
| More effective approaches and procedures | ++ | ++ |
| Improved coordination between projects and programs | + | + |
| Integration of lessons into policy and future programs | (on-going) | (on-going) |

- Strengths of the partnership

- The operation of PAC as an in-formal forum has had many advantages, because it has encouraged the participation of a large number and wide variety of different types of agencies, as well as allowing for new issues and topics to be raised and discussed in an open context.

- A good mechanism, methodological approach and momentum has been created for linking grassroots lessons and experience to policy advice with Government ownership.

- There has been pro-active participation of many stakeholders including development projects and programs, provinces, and some central agencies etc. In particular, there has been a generally higher level of involvement of provinces, districts and communes in PAC activities as compared to other partnership forums in Viet Nam.

- The partnership has contributed to improved approaches and procedures through the documentation of lessons, best-practices and policy recommendations in a number of important topics (such as operations and maintenance of community infrastructure, commune cadre training, commune development budgets, sustainable livelihoods methods etc).

- The partnership has an effective and systematic dissemination strategy through consultation workshops held at different levels, and through the production and dissemination of high quality publications. These outputs and publications have a practical focus, and are useful for policy makers as well as project managers and development workers on the ground.

- Weaknesses of the partnership

- Because PAC has not been directly linked to any specific policy-making context at national level, the impacts on policy formulation and on the design of future programs are largely in-direct. At the same time, on-going efforts have been made to widely disseminate the lessons and recommendations from PAC studies and to integrate them into the re-design of the Government’s National Target Programs on Poverty Reduction for the period 2006 to 2010.

- There has been limited, or at least not consistent, involvement of some central Government agencies, as well as some donors and INGOs, in the partnership activities. This has meant that awareness of the partnership at central level is in some cases still quite limited.

- It is recognized that in the future, greater efforts should be made to mainstream the partnership and its activities in order to improve these central level linkages, as well as to increase the impacts of the partnership activities on the policy making process.

- From a regional perspective, PAC studies and activities have adequately covered some regions of the country (including the Northern Mountain Region and the Central Coastal Region). Some other regions (the Central Highlands and the Mekong Delta) have not been adequately represented either in PAC studies or in terms of participation in PAC activities.

- PAC has been less successful in fulfilling its objective related to improved coordination of Government and donor projects and programs working on rural development and poverty reduction in the poor communes. In this respect, it can be suggested that the original objectives of the partnership were perhaps too broadly conceived – and that it can be difficult for one forum to serve these different functions of ‘improved coordination’ and ‘lesson learning’.

## Concept Note (2006 to 2008)

  - Strategic considerations

PAC was originally established in 1999 at the same time as the Poverty Task Force, and is therefore one of the longer-running partnerships. However, it is recognized that the partnership context has changed considerably since then, and since preparation of the previous work program (in 2001).  Accordingly, at this point in time, it is important to reassess role that PAC could play in this new context, and what added-value the partnership may bring to future poverty reduction efforts.

The main difference between these two partnerships is that whereas the Poverty Task Force has concentrated primarily on macro-level policy issues (related to the national poverty assessments, preparation of the CPRGS, and more recently the Socio-Economic Development Plan process), PAC has focused more on lesson learning on technical issues, on the practical aspects of project and program operations, and on grassroots capacity building for program implementation.

In recent years, a number of related sector-specific partnerships have also been established and have become more active (including the partnerships in forestry, water, enterprise development etc). Discussions are also underway regarding formation of a partnership to support implementation of the National Target Programs on Poverty Reduction (2006 to 2010). The establishment of these partnerships also has implications for the potential future role of PAC as a cross-cutting forum.

With the commencement of the Socio-Economic Development Plan (SEDP) for the period 2006 to 2010, increasing attention will need to be given to putting policies into practice, and related lesson learning and monitoring implementation of the SEDP and the National Target Programs on Poverty Reduction. In this respect, the previous experience of PAC in conducting evidence-based field studies, and networking between communes, districts and provinces and other stakeholders provides a good basis for the type of lesson learning that may be required in future.

  - Future directions

Taking the above mentioned points into consideration, it is proposed that the main objectives and focus of the partnership activities in the future would be as follows:

- Focus on sustainable socio-economic livelihoods for the poorest rural communities. It is suggested that the overall objective of PAC should be to serve as a broad-based inter-agency forum for the exchange of practical lessons and experience on the implementation of policies and programs in support of sustainable socio-economic livelihoods for the poorest rural communities (defined as poor rural communes, villages, population groups, and producer groups). This reflects the increasing emphasis being given by the Government and donors to the livelihood aspects of the poverty reduction programs. The location of PAC under the Department of Agriculture Economy in MPI also justifies this increased focus of economic livelihoods of the poor.

- Focus on cross-sectoral issues related to socio-economic livelihoods. In particular, it is proposed that PAC should focus on critical cross-sectoral issues that impact upon the socio-economic livelihoods of poor rural communities. In this respect, cross-sectoral can be defined in two ways: (i) as resource management issues that span the divide between different sectors such as water, fisheries, agriculture, environment and land; and (ii) which cover both ‘public’, ‘private’ and ‘voluntary’ sector investment policies, development practices and agencies.

- At higher levels (centre and province), PAC would focus in particular on channeling lessons and experience on these livelihood related policies and practices into the on-going implementation of the Government’s National Target Programs for Poverty Reduction and the provincial and sector socio-economic development plans. In this respect, PAC would serve as a ‘vehicle’ for bringing together, documenting and disseminating ‘successful models’, ‘best practices’ and ‘new approaches’. This will be based on thematic field-studies on important topics and issues that are identified and undertaken in collaboration with PAC partners.

- At local levels (district and commune), PAC would focus in particular on making information on these successful models, best practices and new approaches available to local leaders, planners, service providers and poor rural communities etc. in a format that can be widely disseminated and easily used. This would be through a documentation and dissemination strategy that utilizes audio-visual media linked to both mass media channels (e.g. provincial television) and information technology (e.g. commune information centres). This would also be combined with a stronger regional focus of the partnership activities – for example, by supporting more cross-learning events in regional centres and provinces.

  - Partnership organization and mode of operations

It is proposed that a basically similar model for the partnership organization should be maintained in the future, consisting of the wider Partnership Group, the Core Group that advises on the direction and activities of the partnership, supported by a small PAC Secretariat within MPI. However, it is recommended there should be some changes in representation on the Core Group, and improvements in the mode of operations of the partnership. This is in order to strengthen both the ‘upward’ policy influencing role of the partnership, and the ‘downward’ influencing role on implementation practice at province, district and commune levels.

Partnership Group. It is suggested that PAC should continue to operate as a broad-based forum – by encouraging the active involvement of a wide range of different organizations, and achieving wide out-reach through the dissemination strategy. Activities would be jointly identified and undertaken in collaboration with the various partners, including provinces, projects and programs, NGOs, research and training organizations etc. This would build on the successful model developed in the previous phase in achieving broad-based participation in the partnership activities.

Core Group. It is suggested the Core Group should have a wider range of members than in the previous phase. This would be in order to: (i) to create stronger and more formal horizontal linkages with other central Government agencies responsible for rural development and poverty reduction; (ii) to represent the range of different types of organizations involved in the partnership (e.g. by involving research and training organizations); (iii) to represent regional interests more fully on the partnership (e.g. by involving organizations from the centre and south of the country); and (iv) to create linkages with other associated forums (e.g. the NGO Working Groups on extension and ethnic minorities). Each of these organizations would be invited to nominate a representative to become a member of the Core Group in order to ensure consistency in these linkages. The Core Group would meet every 6-months, with the following main tasks: (i) to put forward, discuss and agree the Annual Work Plans (in December); and (ii) to review progress on activities mid-year (in July).

  - Name of the partnership

It is proposed that in the future work program the name of the partnership should be changed from the Partnership to Assist the Poorest Communes to a new name – the Partnership to Assist the Poorest Rural Communities. The reasons for this proposed name change are as follows: (i) recognition that rural poverty situations are increasingly concentrated below commune level (poor villages, poor communities and population groups); (ii) poverty situations are not only found in the poor communes, but also in more prosperous rural areas of the country; and (ii) to reflect the shift in focus of partnership activities to concentrate more on socio-economic livelihoods of the poor.

  - Main themes

Five main themes are initially proposed for the future PAC work program. These themes have been identified from a number of different sources, including: (i) suggestions made by partners at the PAC Summary Workshop held in January 2005 on priorities for the future work program; (ii) priorities identified through the previous work program and by identifying gaps in current policy analysis; (iii) specific suggestions from the PAC Core Group members; and (iv) specific suggestions from province and project partners made at the National Conference held in November 2004. These five main themes are as follows:

- Theme 1: Promoting socio-economic livelihoods of the poorest rural communities – situation analysis, needs assessment and promising approaches. Sub-topics that have been proposed under this theme include: (i) study on the most disadvantaged villages and hamlets in the uplands (to make recommendations for how poverty reduction and rural development programs can better target and address the needs and circumstances of these disadvantaged communities); (ii) study on the poorest (destitute) households in the uplands (to make recommendations on how the needs and circumstances of these destitute households can be better targeted and addressed through either social welfare mechanisms, livelihood related services, or through community support initiatives); and (iii) study on vocational skills training opportunities for the poorest people (to assess the efficacy of vocational skills training initiatives for ethnic minority groups and for poor women in particular, and to make recommendations for how vocational skills training opportunities can be made more accessible to the poorest people).

- Theme 2: Cross-sector and integrated resource management issues relating to rural poverty reduction and socio-economic livelihoods. Sub-topics that have been proposed under this theme include: (i) study on community development issues in the Mekong Delta (as related to environmental protection, pollution control, water resources management, and access to resources for the poor); and (ii) study on integrated resource management systems in the uplands (as related to the integration of agriculture, livestock production and forest sector policies and land management systems, and access to these resources for the poor).

- Theme 3: The role of community based organizations, farmer and producer associations, and small-scale agro-enterprises in promoting sustainable economic livelihoods for poor rural communities. The aim of this theme would be to better understand the current situation on the extent to which community-based organizations of different types and in different sectors are assisting poor households and communities in getting better access to livelihood related services and markets, and to put forward policy recommendations on the regulatory framework and support mechanisms for the development of these local organizations.

- Theme 4: International trade and biodiversity agreements and their implications for agricultural livelihood development and rural poverty reduction – building-up local knowledge and capacity. Information provision and the awareness of local leaders and officials (at district and commune levels) on the content of international trade and biodiversity agreements is in many cases limited. The aim of this theme is to research and more widely disseminate information to these stakeholder groups on the implications of these agreements for the development of agricultural livelihoods.

- Theme 5: Commune investment ownership and management – dissemination and scaling-up of lessons and best-practices. This theme would represent a further consolidation of work undertaken in the previous work program (2002 to 2004) by more widely disseminating lessons to district and commune levels on good approaches to capacity building and training for commune investment ownership, community supervision, and operations and maintenance of community infrastructure etc.

  - Proposed funding arrangements

It is proposed that the Ministry of Planning and Investment would establish a Trust Fund mechanism for the partnership that would be managed and operated according to guidelines agreed between the partners and funding agencies. Two types of funding may be sought for the partnership, including: (i) Core funding for partnership running costs (including hiring administrative support staff, technical assistance, Core Group meetings, regular travel for networking, establishing and running a PAC website, audits etc); and (ii) Co-financing for different themes which may be financed from different sources according to donor interest (including commissioning thematic studies, review workshops and publications).

It is the sincere hope of the PAC Secretariat that due consideration will be given by the Government, and by international donors and INGOs, for their continuing support and cooperation to maintain the Partnership in the important task of continuous study of the reality of livelihoods and socio-economic development of the poorest rural communities, promoting successful programs, and capacity building for the poor communes and villages.

GENDER ACTION PARTNERSHIP (GAP)

##### Introduction

The Gender Action Partnership (GAP) is an open forum for discussions on key development issues related to gender, for all members of the development community. GAP’s membership comprises representatives from government agencies, international and Vietnamese non-governmental organizations, bilateral donors, United Nations and other multilateral agencies that assist in Viet Nam’s development. The group contributes to equitable development and poverty reduction in Viet Nam by supporting gender-responsive policies, practices and approaches in the national development process.

Because gender equality plays a central role in poverty reduction and sustainable development, GAP’s work focuses around promoting gender equality outcomes.  It does this through dialogue, policy review and specific development initiatives on gender issues between partners and government, and within government. The National Committee for the Advancement of Women in Vietnam (NCFAW), the key government agency responsible for the provision of policy advice to government on gender equality in national policy and planning, acts as the GAP Secretariat.  GAP meetings are hosted and facilitated on a rotating basis by member organizations.

Key gender-related developments over the past six months:

Gender Equality Law

A third draft of the Gender Equality Law (GEL) has been developed by the Drafting Committee of the GEL chaired by the VWU with technical assistance from ADB and MPDF (IFC).  A number of consultation workshops have been held with NGOs, academics, international lawyers, gender experts, international donors and women entrepreneurs throughout the country. The latest draft is currently being circulated for comments.

Promoting Women’s Human Rights and Gender Equality

The UNIFEM CEDAW SEAP has conducted a series of activities promoting women's human rights and CEDAW awareness in Vietnam such as organizing the first multi-stakeholder workshop on CEDAW for government organizations and NGOs; assessing gender equality situation in Vietnam; providing technical assistance for the process of developing the GEL from CEDAW perspectives, and training on CEDAW to 20 national and international NGOs in Vietnam. .

Support to the Five-Year Socio-Economic Development Plan (2006-2010)

The GAP, with support from CIDA, World Bank and ADB, has been working with NCFAW through a series of consultations to ensure that the five-year Socio-Economic Development Plan (SEDP) for 2006-2010 is gender responsive.  Four workshops were conducted throughout the country.  NCFAW has provided its third set of comments on the draft SEDP to MPI.

#### Mainstreaming Gender in Poverty Reduction Support Credits

- A policy action on integrating gender into planning manual for ministries and provinces has been included into PRSC4. The gender sensitive planning manual has been drafted and being consulted before finalizing for publication by December 2005.

Framework Mapping of Key Gender-Related Activities in Viet Nam

GAP members with NCFAW coordination have mapped key gender activities currently being carried out by government, donors, NGOs and other development partners. The mapping is intended to help identify possible strategic areas for collaboration as well as major gaps in programmatic activities among all development partners.

Next six months

Gender Equality Law

GAP sub-group meetings will be organized on the GEL, with continued discussion on the Law’s substance at GAP plenary meetings. The NCFAW with support from SDC and the Swiss Embassy plans to conduct some activities to learn more experiences on law enforcement mechanism from Switzerland and other countries. International donors intend to provide support for the implementation of the law. The GEL will be submitted to the standing committee of the National Assembly in February 2006.

Gender Mainstreaming and Gender Programming

- Through their respective organisations and commitments, GAP members will continue to work on gender mainstreaming within broader development programmes across sectors as diverse as health and HIV/AIDS and public administration within the MARD. Gender is also expected to be included into Vietnam Development Report 2006 on Business. In addition to gender mainstreaming, some GAP members are also working on specific gender equality initiatives such as conducting research among women entrepreneurs in Vietnam, trafficking of women, capacity building on gender budgeting in the Academy of Finance and the implementation of the gender plan of action in MARD.

Gender and PRSC5

During the preparation of the PRSC-5, the GAP will discuss to find out a priority gender policy action to propose for including into upcoming PRSC.

Vietnam Gender Situation Analysis

At the time being many pieces of surveys and researches, studies on gender equality situation have been or being conducted. It is expected that a comprehensive gender situation analysis, included all available documents/reports on gender equality will be done to serve as a common platform for anybody working on gender in Vietnam

Plan of Action 2 Review and Development of POA 3

The Beijing+10 Conference took place in New York in March 2005, to review ten years of implementation of the Beijing Platform for Action. In follow up to this, MPI in collaboration with NCFAW will continue to conduct review of the POA2 and begin preparations for developing the third POA to realize the National Strategy for the Advancement of Women in Vietnam by 2010.  A bottom - up approach to planning will be carried out based on the guidelines developed by MPI and NCFAW. In addition, NCFAW will take a leading role in reviewing the national machinery for the advancement of women.  It is expected that the national report on reviewing POA 2 and POA 3 will be available in April 2006.

###### SEDP

Under support for SEDP mentioned above, a framework of gender indicators from the SEDP will be developed and provide inputs for the development of the next Plan of Action POA3.  A manual on gender integration into planning processes will be prepared by MPI with technical assistance from a gender consultant and is aimed to guide all sectoral and provincial planning processes.  It will take into account the National Gender Mainstreaming (GMS) Guidelines developed under NCFAW in 2004 which provides a practical handbook for officials to develop gender-responsive plans and policies at different levels. There are tentative plans to pilot the new manual within one sector per province. This initiative will build on the applied gender mainstreaming work piloted by NCFAW in 2004 in Tra Vinh which supported the development of a gender-responsive annual plan at the provincial level.

APEC's Gender Focal Point Network – Vietnam to Chair 2006

In 2006 NCFAW will chair the 4th Gender Focal Point Network (GFPN). As chair, NCFAW will advise Senior Official Meetings, organize meetings with Leaders and Ministerial committees about women’s integration in APEC and participate in different APEC fora and working group meetings. GAP members will support NCFAW to fulfil their role as chair of the GFPN.

GAP Secretariat - National Committee for the Advancement of Women in Vietnam

39 Hang Chuoi, Hanoi.  Tel: (84 4) 971 1349, fax: (84 4) 971 1348

# E-mail: ncfaw@hn.vnn.vn

## INTERNATIONAL SUPPORT GROUP ON NATURAL RESOURCES AND ENVIRONMENT (ISGE)

## Partnership Note, December 2005

Introduction

# Vision

Government and donor activities on environment and natural resources management are harmonized and coordinated, leading to effective pollution prevention, high environmental quality, and the sustainable use and conservation of natural resources in Vietnam.

## Mission

ISGE is a catalyst and focal point for aid harmonization and policy dialogue. It initiates discussion, support the co-ordinations of the Government and donors activities in the field of environmental and natural resources management, and helps building consensus on environment and natural resources priorities, strategies, legislation, institutional capacity building, and development programs among key stakeholders such as line ministries, businesses, civil society, and the donor community.

###### ISGE Progress

# ISGE, with its above vision and mission, has been a concern of and supported by the Ministry of Natural Resources and Environment (MONRE), other ministries, sectors, donors and other international organizations. Since its formation, ISGE has successfully become a forum for policy dialogue and information sharing. An initial organizational structure of ISGE included (i) ISGE Steering Committee; (ii) ISGE Secretariat, and (iii) three Thematic Ad-hoc Groups (TAG).

ISGE was guided through meeting of the ISGE Steering Committee and ISGE Plenary Meeting. These meetings provided significant direction to ISGE at two stages: i) year 2004: consolidating ISGE and commencing activities of 3 TAGs, and ii) year 2005: assisting MONRE in developing the five-year plan of MONRE and the natural resources and environment sector (hereinafter called five-year plan), and reviewing legal system for natural resources and environment (NRE).

The Secretariat now has an organization and funding mechanism in place allowing it to work efficiently.

Three TAGs were formed: TAG1 “Water resources and water environment”, TAG2 “Poverty – growth – environment” and TAG3 “Capacity building and institutional strengthening for natural resources and environment”. Following Work Plans developed, the TAGs have already developed reports on state assessment and proposed priorities for policy dialogue on relevant issues relating to each TAG. TAGs are now able to provide a platform for broad discussion of these issues.

Activities in 2005

- ISGE has assisted effectively the development of the five-year plan. The assistance of ISGE included: involvement of forming a Joint Task Force to support the development of five-year plan; development of log-frame of five year plan using the logical framework approach. This log-frame was highly appreciated by both MONRE and donor community. ISGE also involved and assisted a number of meetings, which were held for various consultations to drafts of five-year plan.

- A workshop “National Action Plan on Biodiversity” was held for broad comments to the Draft of Plan.

- A workshop “Environmental issues during and after mining” also was held to draw attention of donors to this issue.

- There are 02 meetings within TAG 2 were held regarding issue ‘poverty – growth – environment’; 03 meetings within TAG 3 for consultation and sharing information regards ‘Formation of Institute of NRE policy and strategy’ and ‘Strengthening capacity and decentralization of NRE managing agencies’.

- ISGE Plenary Meeting was held on February 1, 2005; ISGE Steering Committee was held on June 14, 2005

On-going activities 2005

- To continue assistance of five-year plan development;

- To assist to hold a National Consultation Workshop for Biodiversity Action Plan;

- To assist reviewing and development of legal documents on NRE through close cooperation with the Department of Legislation, MONRE;

- To develop a “Roadmap on NRE”, which will be used as framework document for policy dialogue on NRE at ISGE;

- To update information for ISGE website and publish regular ISGE newsletter.

# International Support Group on Natural Resources and Environment

# Room #215, No. 83, Nguyen Chi Thanh, Ha Noi

# Tel: 04-7735510; Fax: 04-7735509: Email: isge@monre.gov.vn and isgemonre@fpt.vn

# Website: www.isge.monre.gov.vn

PEOPLE’S PARTICIPATION’S WORKING GROUP

Partnership Note

Hanoi, November 2005

The People's Participation Working Group (PPWG) was established in 1999 and provides an informal forum for organisations and professionals - including donors, NGOs, projects and consultants and researchers - to meet and exchange information and ideas on issues relating to people’s participation, grass-roots democracy and civil society. Participants are encouraged to share information relevant and interesting to other people of the network

The overall goal of the group is to support the Government of Vietnam in its efforts to enhance people’s participation in their own development and the development process in Vietnam including participation in development policy design, implementation and monitoring.

The immediate objectives the group are to promote i) an enabling environment and capacity building for enhanced people’s participation and ii) co-ordination of activities for efficient use of resources invested in this area.

# Update on PPWG activities in 2005

In 2005, the PPWG continued to provide a forum for exchange of information and networking between international and Vietnamese organisations engaged in promoting people's participation. During this year the PPWG has attracted more participation from Vietnamese governmental bodies and civil organisations. In particular, the four main thematic meetings described below have provided a forum for dialogue between different stakeholders.

- Co-ordination

The PPWG is co-ordinated by an elected Chairperson assisted by a voluntary core group. This core group currently consists of 10 members from UN agencies, International NGOs, Research Institute, and Vietnamese NGOs, who met regularly throughout the year to organise thematic workshops and other events. The current Chairperson is Ms. Nguyen Thi Le Hoa from Oxfam Great Britain.

- Thematic meetings organised by PPWG in 2005

- Workshop 1: The Civil Code and its relation to civil society organisations

This workshop was organised on 15 March 2005 with participation from 30 international and national agencies. It provided participants with an overview on the current revisions to the Civil Code, especially its “legal person” definitions that relate to civil organisations, and its relevance to other legislation on civil organisations. The invited speakers included a member of the Ministry of Justice drafting team and a Civil Code law professor from the National University who is a technical contributor to the revision.

Participants were invited to make comments and give recommendations on the draft revision. Vietnam Assistance to the Handicapped (VNAH) followed up with the drafting team with comments and feedback from PPWG participants.

- Workshop 2: Participation

This workshop was organised on 27 May 2005 with participation from more than 80 people from Government agencies, National and International NGOs, Donors and Research Institutes. The focus of the workshop was to share information and gather feedback on two current studies in Vietnam:

- Grassroots Democracy Research Project - United Nations Development Program (UNDP)

- Civicus Civil Society Index Study - Vietnam Institute of Development Studies, UNDP and SNV-The Netherlands Development Organisation

Both projects were presented in an early phase to provide information and encourage input and discussions from a broader group of interested people. They will both be completed within 2005 and will be presented at workshops.

This workshop also promoted discussion towards developing a shared understanding among diverse development agencies (Government, Donors, Vietnamese and International NGOs) on participation and study linkages between participatory processes and indicators, organisational programme approaches and civil society

- Workshop 3: Rural Collaborative Groups

This workshop was organised on 16 September 2005 to share information on the policies and legal framework for rural collaborative groups (voluntary simple associations of rural people for common economic purposes or community-based organisations with the purpose of income generation). Two speakers were invited from the Central Institute of Economic (CIEM) under the Ministry of Planning and Investment (MPI) and from the Management Department of Cooperatives and Rural Development of the Ministry for Agriculture and Rural Development (MARD).

Participants discussed the current development status and trends of rural collaborative groups as well as their advantages and opportunities. Constraints that rural collaborative groups are facing were also discussed based on the experiences of some organisations that have been working with these groups.

The International Fund for Agriculture Development (IFAD) presented an initial idea for development of a research plan on the legal framework for rural community-based organisations (CBOs) to be jointly organised by MARD and CIEM with support from interested donors and NGOs. PPWG members were invited to give comments and encouraged to support and contribute to the implementation of this research and the formulation of the legal framework.

- Workshop 4: Networking amongst Vietnamese NGOs

This workshop is planned for the last week of November. Speakers from some Vietnamese NGOs will be invited to share their experiences on networking. Topics to be addressed will include formation of networks, structure and capacity, activities, contributions to the development process, and challenges faced in promoting these networks. It is also planned to invite a resource person who is doing a study on Vietnamese NGO networking to provide some initial findings and reflection.

- Ongoing update of the PPWG Website

http://www.un.org.vn/donor/civil.htm   (including ‘civil society readings’)

A part from accessing to information posted in the Website, PPWG members also exchange information on related experience, lessons learnt as well as relevant events/news through PPWG group mail. One example: The “Chia Se” program of Sida has used this channel for disseminating information on its Local Partnership Fund.

- Preparation of a Partnership Note for the bi-annual Consultative Group meetings

- Formulation of the PPWG work plan for 2006

The core group has identified the following topics for possible thematic workshops:

- Public participation and the socialisation of service provision - user fees, public monitoring of service quality, tax issues

- Village Development Planning

- The Law on Associations

- The 2006-2010 Socio-Economic Development Plan - finalisation and implementation

- Presentation of the CIVICUS report on a Vietnam Civil Society Index

- Understanding the status and roles of the Mass Organisations

# Recent developments related to Grassroots Democracy and People's Participation

- Legal framework for Civil Society Organisations

The revised Civil Code passed in May 2005 is an important document for the legal framework for civil organisations in Vietnam. The Civil Code identifies social/charity funds and associations as the two legal entities with distinct civil society characteristics in the sense of being nongovernmental, not-for-profit, and non-political.

Over the past two years, the Ministry of Home Affairs (MOHA) has been leading efforts to draft a new Law on Associations. Submission to the National Assembly is aimed for 2006. The new Law (at the 6th draft as of November 2005) is expected to simplify establishment procedures, allow foreign membership, decentralize oversight of associations and introduce tax preferences for not-for-profit activities and donations. We understand that there are some remaining issues for consideration such as whether or not to include all official socio-political associations under the scope of this law. Some stakeholders have also raised questions about whether the draft Law will actually facilitate registration procedures or make them more complicated.

The PPWG has also been following with interest the development of taxation law in Vietnam with regard to non-profit activities, donations and civil organisations. At present, although tax exemption is applicable to certain not-for-profit activities, the tax regime of Viet Nam does not include any special provisions for civil society organisations or donation to this sector.  As Viet Nam has plans to review and revise several tax regimes, it is important to improve those affecting the civil society sector. This is an important issue for Vietnam to address in the context of the current review and revision of the tax regime.

- National macro-level planning

During 2005, the PPWG has followed with interest the development of Vietnam's 5-year Socio-Economic Development Plan 2006-2010 (SEDP). We have noted in particular the initiative led by the Prime Minister to further decentralise the planning process to ministries and localities, to involve a wider range of participants (including research institutions, non-governmental organisations, and social and business groups), and to incorporate the Comprehensive Poverty Reduction and Growth Strategy (CPRGS) and the Vietnam Millenium Development Goals (VDGs).

Many organisations participating in the PPWG have provided support to the overall SEDP drafting process, including:

- cooperation with MPI to conduct community-level participatory poverty assessments and consultations on the draft SEDP

- support to specific sectors and localities in the preparation of their 5-year plans, including incorporation of the Comprehensive Poverty Reduction and Growth Strategy (CPRGS)

- support to the organisation of various consultation meetings and preparation of written inputs for the drafting team under MPI, including limited support to civil organisations to implement internal consultation workshop with their members

- participation in national consultation workshops including the consultation with Vietnam's international partners organised by MPI and the World Bank on 8-9 September in Hanoi, and other events such as the high-level consultation on the inclusion of children's issues in the SEDP

PPWG participants are also waiting to see how the inputs that have been given during these consultation processes are incorporated into later drafts and the final SEDP. The PPWG note that involvement from civil organisations such as Vietnamese NGOs has been limited, especially at local levels. This is partly due to the limited time allocated for consultations, as these organisations are unfamiliar with such practices. It is also important to make such processes 'bottom-up' and focus on local rather than national plans. It is important to consider how to involve these organisations in SEDP implementation.

PPWG participants have also participated in consultations and discussions on the implementation of the National Targeted Programs (NTPs) on Poverty Reduction (HEPR and Program 135) during 2001-2005 and on the development of plans for 2006-2010.

PPWG participants observed a very significant improvement in planning processes for the NTPs, especially for the HEPR program. There was a very thorough assessment on implementation during the past 5 years, including issues like public participation and targeting. This assessment provided good experience and lessons learnt for developing the next 5-year plan. A series of consultation workshops were organised with a wide range of stakeholders participating at different levels and at different stages of program planning. PPWG participants participated in workshops in Hai Phong, Dak Lak and Long An provinces.

Improvements were seen both in the preparation process and in the content of the plan. Later versions have incorporated many comments and feedback from the consultations. There is also a positive signal on partnership between Government, Donors and International and National NGOs to support the implementation of these NTPs in the coming 5 years.

- Decentralisation and promotion of people’s participation:

During recent years a number of steps have been taken to decentralise governance and improve the framework for people's participation in terms of economic resources, public administration and participation in decision-making. More resources are now decentralised within the State budget (currently 44 percent), and the grassroots democracy decree provides a legal framework for increasing people's participation and transparency at the local level.

Agencies participating in the PPWG are supporting a wide range of activities related to promotion of people's participation and decentralisation, including (but not limited to the following):

- Support to the implementation of the grassroots democracy decree and local participation

- supporting the local government to develop awareness raising tools on grassroots democracy in Viet and ethnic languages, improving the grassroots democracy decree introduction and facilitation skills of local cadres/village heads, and developing a specific monitoring mechanism (Helvetas)

- exploring the application of the grassroots democracy decree in implementing commune budget law in Quang Tri, integrating grassroots democracy principles in livelihoods activities in Lao Cai and enhancing the exercise of grassroots democracy principles by officials and citizens in Kon Tum province through legal consultations and legal and development clubs (Finland)

- Village Development Planning and Commune Development Planning initiatives (e.g. IFAD, Helvetas, GTZ, SIDA)

- Applying the principles of grassroots democracy to livelihoods activities in Lao Cai (supported by Finland)

- Capacity Building and support for participation in planning and policy processes

- Capacity building for mass organisations (Women's Union and Farmer's Association) in Tra Vinh on policy monitoring and evaluation (Oxfam GB)

- Supporting the establishment of a Vietnam NGO network (under VUSTA) on Anti Poverty Policy Study (Oxfam GB)

- Supporting local consultation on the national SEDP in Ninh Thuan province (Oxfam GB)

- Supporting provincial policy dialogues among twelve provinces on community participation in planning and implementation of integrated rural development (IFAD)

- Piloting the adoption of CPRGS principles in the SED planning process in Bac Ai district, Ninh Thuan province (Oxfam GB)

- Capacity building and support for networking, information sharing and advocacy by Vietnamese NGOs via training and partnerships for project implementation (CARE, ICCO, ActionAid Vietnam)

- Support to improvement of local governance at the provincial and lower levels, including pilot activities aiming to apply the participatory approaches developed at village and commune levels to the district and provincial level (e.g. Oxfam and UNDP in Tra Vinh, SNV in Thua-Thien Hue)

- Supporting community based organisations and rural collaborative groups within development programmes, including farmers' groups, collaboration groups, interest groups, self-help groups of people with disabilities and people living with HIV/AIDS (e.g. STRONGER and CASI programs of CARE, IPM projects by ADDA, IFAD-supported projects in Ha Tinh and Tuyen Quang)

- STATE OWNED ENTERPRISE REFORM

1.	The working group on SOE reform continues to mobilize and coordinate technical assistance for the formulation of the SOE reform and equitization program, even though the frequency of meetings of the SOE reform group has been irregular.

2.	A weakness of the working group previously identified has been its inability to secure representation of the Government on a regular basis, in part because relevant agencies were engrossed in developing greater consensus in the Party and re-organizing their machinery for implementing SOE reform.

3.	However, the group has been very effective in disseminating and sharing information and in mobilizing assistance.  Donors have used several mechanisms for spreading information.  Also, they have helped to mobilize assistance for both formulation and implementation of the program.

# Meeting the success criteria and supporting the CPRGS

- The implementation of the multi-year SOE reform program continues.  The numbers of SOEs equitised continues at a rate of more than one per day.  2004 was a record year when more than 600 equitisations were completed.  More equitisations have been completed so far this year compared to the same stage last year indicating that 2005 may well turn out even better than 2004.  Planning is under way for more transformations as a result of reducing the numbers of SOEs in which the State will retain 100% ownership.  The equitisation of large SOEs is conspicuous by its absence.

- The Social Safety Net set up for employees leaving SOEs has been operational throughout the last six months.  So far more than 110,000 former employees have benefited.

- In January 2003, work began at 3 General Corporations: Vinatex, Vinacafe and Seaprodex directed at producing restructuring plans for the General Corporations themselves and, thereafter, restructuring assistance to several of the SOEs at each of the three industry groupings.  This work is being funded by DFID.  The restructuring plans for the 3 General Corporations were presented in June 2003 and were adopted by Government.  There are several recommendations including converting each of the 3 General Corporations into holding companies.  Decree 153 to facilitate the formation of “mother-child” companies was signed in August 2004.   The work has now been extended to continue at Vinatex and Vinacafe until May 2006.

- 2005 has seen the auctioning of shares in larger SOEs via the stock exchanges in HCMC and Hanoi.  More than $60 million was raised through the sales of shares at 2 enterprises: Vinamilk and Vinh Son-Song Hinh hydropower company.

Aligning support to the CPRGS over the next six months

- The remaining agenda for SOE reform as listed in the CPRGS has been largely completed.

- The Government’s implementation of the plans to transform smaller SOEs will continue.

- It is programmed to continue the implementation of the restructuring plans for the Vinatex, Vinacafe and Seaprodex and commence upon the reform work at other associated SOEs.

- Work is also in progress to improve the reporting of financial data by SOEs and to develop a set of criteria for supervising and evaluating the business performance and effectiveness of SOEs under Decision 271.

# Success criteria for 2005 and beyond

A second survey of the performance of equitised SOEs has been carried out (the first was in 2002).  Since the equitisation only began in earnest in 1999, it was still early in 2002 to assess whether or not the performance of SOEs was largely prompted by the tax incentives or was sustainable.  In this survey over 500 enterprises were contacted.87% of the firms surveyed said that their financial situation had improved, turnover had increased, pre tax profits had increased.  These improvements were greater than those achieved by unequitised SOEs, suggesting strongly that it was equitisation itself that had been responsible.  There had been reinvestment and salaries had increased.  For the most part this was achieved by the same managers who had run the SOEs prior to their equitisation.  It is concluded that there improvements result from the greater autonomy that managers are given to run the companies and that this greater autonomy more than outweighs the handicaps that equitised enterprises find having lost their privileged status.  A well attended workshop was held at the conclusion of this project.

Progress measured against the criteria in the CPRGS has been good.  SOE reform continues to be regarded as a “litmus test” of reform and is frequently cited by both donors and Vietnamese officials as an area that should be given special attention.  As well as tackling the remaining tasks, attention should be focused on:

- Reforming larger SOEs.

- Greater participation of Government, including a leadership role in the working group.

Assistance to SOE reform

| ###### Donor & ###### Grant Amount | Purpose (Implementing Agency) | ###### Status |
| --- | --- | --- |
| ASEM 1 European (WB administered) US$ 100,000 | Social safety net program to deal with labor displaced by SOE reform (CIEM in coordination with NSCERD) | Completed |
| ASEM II European (WB administered) US$ 600,000 | Project Monitoring of SOE Transformations and new establishments (NSCERD). | Extended and still in progress |
| Danida (Denmark) administered US$ 3,100,000 | Support to Industry Restructuring and Enterprise Development by implementing equitization plans and providing post equitization assistance (Ministry of Fisheries). | Ongoing |
| Danida (Denmark) US$ 1,700,000 | Support to capacity building in NSCERD in the SOE reform process (NSCERD). | Completed. |
| DFID (UK) UK£ 4,800,000 | Pilot restructuring of three general corporations – Vinatex, Vinacafe, and the Seaprodex (NSCERD). | Ongoing |
| Japan PHRD, AusAID, Danida US$ 7,900,000 | Diagnostic audits to assess financial health and performance of selected SOEs, and recommend restructuring plans to turn around enterprises. | Completed: December 2004. |
| ASEM II European (WB administered) US$300,000 | Support to assist the operation of the Debt and Asset Trading Company | Ongoing |
| DFID | Survey of performance of companies following their equitisation | Just completed |

THE PARTNERSHIP GROUP FOR SME PROMOTION AND PRIVATE SECTOR DEVELOPMENT (SMEPG)

# Ministry of Planning and Investment, 17 November 2005

# Report To The Consultative Group

On 17 November 2005, the members of the Partnership Group gathered at the MPI.

The event was co-chaired by the MPI's Agency for SME Development (ASMED), the Embassy of Japan, and UNIDO. Mr To Dinh Thai, Manager of the International Cooperation Division of ASMED warmly welcomed the 60-odd representatives from the donor community and Government agencies. From the Government side, representatives from MPI, ASMED, and the Vietnam Chamber of Commerce and Industry (VCCI) participated in the event.

From donors and international organizations, the meeting was attended by representatives of Denmark, Finland, Germany (GTZ), Italy, Japan (EOJ, JICA, JBIC), the Netherlands (SNV), Switzerland (SDC), and the United States (USAID); Asian Development Bank, the European Commission, International Labour Organization, United Nations Industrial Development Organization, World Bank.

In his opening remarks, Mr Nguyen Ngoc Phuc, MPI Vice-Minister highlighted the importance of the Partnership at a time when the country is entering a new five-year SME Development Plan. He congratulated the different projects for the good results achieved during the year and invited the audience to look back at these results in order to better address future challenges. The Government, he continued, is implementing for the first time the SME development Plan (SMEDP), which is now at its final stage and will be submitted to the leadership of MPI and the PM for approval before the Consultative Group (CG) Meeting in December. The Plan, which also includes an action plan for its implementation, provides measures to be executed not only by the MPI but also by other line Ministries. In this respect, he invited donors to provide more contribution in the implementation phase of the SMEDP 2006-2010.

Mr Phuc added that next year, Vietnam will be the host economy for APEC 2006 and is expected to organize several of international meetings and seminars under the framework of APEC. He announced that as far as the SME sector is concerned, a total of five events will be organized: a Micro-Enterprise Sub-group (MESG) and a SME Working Group (SMEWG) meeting are to be held late March 2006 in Beijing, China; a MESG, a SMEWG, and a SME Ministerial Meeting (SMEMM) (one of four APEC sectoral Ministerial Meetings) will be held in Hanoi late September 2006. He concluded by inviting partner donors to provide assistance in this respect.

Remarks by the co-chairs

• Mr Scholtès remarked the importance of the work of Partnership Group. Indeed, Vietnam has been working along the three pillars of the Paris Declaration on Aid Effectiveness and was the first country to localize the three principles of ownership, alignment and harmonization and translate them into practice by releasing the Hanoi Core Statement (HCS) that was submitted to the donor community in June 2005 on the occasion of the Mid-term CG Meeting. The document was received very favorably by donors and was approved in principle at the end of September by the Prime-Minister who requested MPI to monitor its implementation. MPI and the Partnership Group on Aid Effectiveness launched a donors’ baseline survey articulated along 14 indicators of the HCS against which future progress will be assessed.

The baseline survey, Mr Scholtès added, is a complex endeavour since donors assistance is heterogeneous in nature, and often includes a mix of loans and grant aid covering possibly a wide range of issues. A more tractable alternative if the aim is to gauge the extent of ownership, alignment and harmonization in ODA is to focus on target groups such as a particular sector, or region. The SME sector for one has seen in recent years commendable attempts along the three pillars of HCS, and boasts today three solid instruments to that end:  the SME Strategy discussed in June that symbolizes the ownership by Vietnamese parties of development strategies in this sector, the Partnership Group offering the possibility of alignment amongst donors and Government’s objectives and programmes, and the sub-Working Groups, looking into harmonization opportunities amongst projects. The next step is to reach a consensus on how to contribute to the achievement of the principles. Mr Scholtès announced that on November 18, the co-chairs of the CG will be holding a meeting to brief the chairs of the partnership groups on the HCS, and enroll the Partnerships in its implementation.

He then circulated a note describing the fourteen defined indicators and their corresponding application to the SME sector and invited the donor community to return their ideas and comments (see Annex 1).

• Mr Iryu, First Secretary of the Embassy of Japan, greeted the participants and introduced himself as the new representative in the Partnership Group.

• Mr Phuc welcomed the new co-chair and thanked Japan for its help in the preparation of feasibility studies whose results would hopefully bring Japan to decide to financially support the Technical Assistance Centres. He said that the approval should be obtained soon by both the Vietnamese and Japanese Governments.

• Mr Nguyen Van Trung, ASMED Director General (DG) praised the Partnership for its efforts to coordinate available resources for best achieving SME development targets. ASMED reached a number of achievements in the past six months: ASMED and other departments of MPI have finalized the draft Unified Enterprise Law (UEL) and Common Investment Law (CIL) that are expected to be approved during the current session of the National Assembly, ASMED was the main unit that drafted the implementing Decree of the Unified Enterprise Law (UEL); it completed the SMEDP after a highly consultative process; it continued to implement the Comprehensive Support Programme for Human Resource Training in central and southern provinces and finalized the Guidelines for the Programme Management and Implementation in collaboration with the Ministry of Finance (MOF); it developed the plan for the expansion of the National Business Information Network and SME portal, this being an important work with national coverage therefore he invited donors to support it; ASMED is also gearing to undertake international tasks such as hosting the ASEAN SME Working Group in Ho Chi Minh City at the end of the month and hosting and chairing five SME conferences under APEC 2006 in Hanoi, in this respect, assistance from donors would also be welcome. Finally, he concluded by informing that ASMED would assign staffs to attend every sub-Working Groups meetings and invited the WGs to strengthen their cooperation and help the Government better address current SME issues that are high on the Agenda.

ASMED priorities

• Ms Pham Thi Thanh Ha, Deputy Division Manager of the General Issues and Domestic Investment Incentives of ASMED, presented the results achieved in the formulation of the SEDP 2006-2010. She commended all SME stakeholders that have shown great interest and provided valuable contribution to the Plan. Along the formulation process, contributions to the Plan were made in three regional workshops that brought together provincial authorities, research institutes and local business associations from 64 provinces. Comments were also received by 15 Ministries and Agencies, 34 business associations, high level advisors from the Party, the Prime Minister’s Research Commission, MPI and a number of donors. Over 60 written comments and numerous verbal contributions led to a highly participatory process and a constructive dialogue among some 550 stakeholders. ASMED submitted the draft to the SME Development Promotion Council (SMEDPC) and presented the document on the regular session on 9 September. The Council members instructed ASMED to refine the Plan for its submission to the PM; for this purpose, five experts’ roundtables were organized to finalize the Plan. She then concluded by listing the three main improvements in the content of the Plan: a) increased coordinating role of provincial authorities and the set up of public-private provincial Steering Committee to monitor provincial level regulatory reforms and implementation of SME support programmes; b) increased role of business associations in the implementation of the SMEDP; c) alignment of Government agencies and donor objectives under a common framework for improved coordination and resource efficiency. While thanking UNIDO project for the extensive support along the process, she announced that ASMED would be ready to submit the document to PM by the next CG Meeting.

• Mr Nguyen Hoa Cuong, from the International Cooperation Division made a presentation on the upcoming 2006 APEC Meetings to be held in Vietnam and related ASMED tasks. The Asia Pacific Economic Cooperation (APEC) was established in 1989 and consists of 21 member economies representing 57% of the world GDP, 46% trade, 45% population; its main goal is to achieve trade and investment liberalization in the decade 2010-2020. Vietnam has been active member since 1998 and since its establishment in 2002, ASMED has participated in different meetings and conferences. On the occasion of the 14th Ministerial Meeting in Mexico (2002), it was agreed that Vietnam would be the host economy for APEC 2006, and a number of SME-related events would take place (MESG, SMEWG, SMEMM) in Vietnam under this framework. Along the process, it was identified for APEC 2006 the ‘overall competitiveness improvement for SME’ as the main theme and ‘enabling business environment for all enterprises’, ‘human resource development for SME’, and ‘better access to basic resources for SME’ as sub-themes. Among its major tasks, ASMED will coordinate with APEC Secretariat and member economies, prepare SMEWG Work Plan for 2006 and Viet Nam’s Action Plan for 2006, follow up the Daegu Initiative on innovation for SMEs, host MESG, SMEWG in Beijing in late March 2006, host the MESG, SMEWG, and assist MPI in hosting SMEMM in Hanoi in late September 2006. In the preparation phase, ASMED will have to draft a detailed plan for submission to MPI leaders as well as to the National Committee for APEC 2006 (headed by Deputy PM); ASMED has already conducted capability assessment for ASMED staffs and organized different coordination

groups; ASMED will conduct training for ASMED staff and mobilize 200 volunteers; and finally develop detailed proposals and main priorities. The support of donors will be solicited in due course.

In conclusion, Mr Cuong affirmed, the process needs support in capacity building for ASMED staffs (20 Group Coordinators) and for volunteers, equipments for ASMED and APEC meetings, and expertise in developing priorities and projects proposals.

In addition, Mr Cuong inform the thematic Working Groups the names of the seven ASMED staffs who have been assigned to attend the meetings of these Working Groups.

• Ms Pham Thi Thu Hang, General Director of VCCI’s SME Promotion Centre commented that a number of side events will be organized during the APEC Meetings, such as microfinance for SMEs, the Women Leaders Network, the APEC Business Advisory Council, SME and digital economy, incubators forum, etc and called for a close coordination between Vietnamese agencies to host these events. She encouraged both ASMED and donors to focus on these initiatives and coordinate with relevant bodies (Women Unions, etc.). Ms Hang proposed that Vietnam could host many side events, including the incubator forum.

• Mr Cuong commented that contacts with relevant agencies were initiated and informed that the Women Leaders Network would be organized by the Vietnam’s Women Union in late August next year; and VCCI will host the APEC Business Advisory Council sometimes in November. Other events such as the Business Forum have not been planned for organization by any Vietnamese agency. Mr Cuong welcomed Ms Hang’s proposal and invited VCCI for a closer collaboration.

Presentations of the thematic Working Groups

• Working Group on Local economic governance

The main objective of the working group is to provide a platform of coordination for technical cooperation programmes dealing with economic development and regulatory reform issues at the provincial level, Ms Kuesel (GTZ) group focal point explained. Two meetings were organized and some output already achieved; in particular an intervention matrix of programmes was developed, and priority activities for exchange and coordination identified. When describing the modus operandi of the group, she pointed out that the meetings are focused on specific topics, with inputs from different programmes and discussion on the approach to be followed (e.g. discussion on Provincial Competitiveness Index for 2006). The first findings showed that there is a very good basis and high needs for cooperation and stressed the need to involve Vietnamese counterparts. With donors ready to follow a similar approach and components (local investment climate, local economic development, value chains, business associations and business development services), potential areas for cooperation are the use of benchmark and monitoring tool, such as PCI, use of a complementary approach in developing specific intervention and advisory approach as well as other tools (PACA), policy dialogue instruments, and cooperation with Public administration reform approaches. She announced that the next WG meeting will be chaired by Mr David Ray, VNCI Director.

• Working Group on Business regulatory reform

David Ray (USAID’s VNCI) manifested his interest to lead the group , as several projects, such as USAID’ Star, are under implementation and there is the possibility for this group to emerge; he also welcomed the idea to let another organization lead the WG as he also volunteered to be the focal point for the WG on Local economic governance.

• Mr Scholtès provided additional information on the CG co-chairs meeting, clarifying that the draft distributed for comments (Annex 1) will represent the basis for discussion for the 18 November meeting; when explaining the scope of work, for the purpose of connecting ODA resources in the SME sector to the HCS, the general scope of the indicators is described in the left hand column, whereas the application of each one of them to the SME sector is presented in the right-hand column. This latter column helps highlight a possible positioning of projects vis-a-vis each indicator. As an example, he mentioned that the work being done at the sub-WG level can be referred to Indicator # 9 “common analytical tools”.

• Working Group on Business development services

Mr Vistinsen (DANIDA) referred to the first meeting of the WG held on 16 November; on this occasion the draft ToR for the group’s future work together with a draft matrix on BDS support and interventions was presented. He announced that the DANIDA programme has not been approved yet and that the next WG meeting will be held on November 22.

• Working group on Sector approaches

Ms Meissner (EU) provided a presentation on the status of the WG; the focus of the WG is on the support to collective competitiveness of sectors. The group’s mandate is to coordinate and cooperate on methods and activities in sub-sector promotion in the areas of clusters, value chains, linkages, technology-related topics, incubators, general sub-sectors. The group has planned to focus on a number of joint initiatives aimed at sharing information, lessons learned and approaches; clarifying terminology and concepts, developing new good practices; providing joint inputs, training, and clarification in the subject for counterparts; conducting peer review and feedback sessions; and mobilizing know-how on newest development in the area and from the private sectors. So far, the working group has met twice; at the project level, a first project presentation on Observation from the dragon fruit GAP project was held; also, the basic design and concept for a Joint Online Database was developed with the idea of linking up to ASMED database; topics being discussed are how to create collaboration among different Value Chains players, what capacity building instruments to use, how to integrate policy issues in sectors and chains, etc.. She informed the participants that the next meeting will be held on 24 November

and on this occasion there will be presentations from MPDF project on “Agri-sector linkages”, ILO’s instruments on value chain promotions and the process of starting to collect inputs for the webpages/database launched. In conclusion, a quick evaluation highlights that the value added of the WG are the fast and efficient mobilization of resources and know how, the avoidance of overlapping, the organization of concerted actions. The vision of the future will be to focus on the peer review and feedback mobilization.

• Working group on SME finance

Mr Kohata (JICA), focal point of the group introduced the purpose of creating favorable financial conditions for SME in Vietnam, such as SME funds, Credit Guarantee Fund system, banking procedures, etc. He then presented the key aspects of SME policy in USA, Korea and Japan and the position of ASMED with respect to SME financial policy. As far as donor coordination is concerned, there exist three funds for SME development (JBIC Fund, ADB-AFD-KfW Fund, and EU Fund). According to the scheme presented, ASMED should cooperate with MoF and the State Bank of Vietnam (SBV) in collaboration with the three above mentioned Funds. He then introduced the SME finance projects that consist in a loan program and technical assistance and congratulated with the parties that have gathered in individual and group meetings since April 2005. He finally thanked the partners for the continued cooperation.

• Mr Trung clarified that ASMED functions do not deal specifically with financial issues, and that MOF is the competent authority; he finally invited Mr Kohata to share the relevant information with ASMED.

• Ms Lao-Araya, ADB Head of Finance, Trade, Governance and Private Sector intervened by stressing that ADB was providing budget support, in the form of a programme loan that is supporting different SME-related field such as land, registration, etc and not directly SMEs.

• Working group on Sustainable business practice

Ms Tas (UNIDO) informed that the Sustainable business practice WG will be convening in

January as per information provided by Ms Trang (MPDF), group focal point.

• Working group on Business research and monitoring

As for the Business research and monitoring WG, Ms Tas, group focal point explained that the Group has been waiting for the SMEDP to be completed and issued. She affirmed that the business research issue will be of benefit to other groups as it will handle overall issues, such as the statistical issue. Regarding monitoring, it is important to have a framework, such as the SMEDP; she informed that the WG will meet early January as soon as the SMEDP is issued. As to the UNIDO-ASMED project, she provided a snapshot of the major activities under way: an assessment of capacity building of ASMED will be finalized and its results available in the second half of December. Within the scope of this assessment, assistance has been provided to help ASMED conduct the assessment of its staff for the setting up of the ASMED-APEC secretariat. The project is also assisting ASMED to conduct the visit to Singapore during the week 21-25 November for the preparation of the APEC SME Meetings. She also echoed Mr Trung’s call for support from other donors. Another initiative that is being carried out by the project is related to the SME portal. With this regard, Ms Tas introduced Ms Nguyen Hong Lien, Director of ASMED’s Business Information Centre and team leader of the SME portal work, who is currently working with 13 national consultants. The portal will be structured along three main elements that are institutions, practical business advice, and business regulations. Within the context of the latter, ASMED has launched an extensive review of business licenses and conditions with the objective of hosting all these information on the portal for improving the transparency of the licensing system. A meeting of donors will be called by Ms Lien in December. Upon issuance of the SMEDP, the project will continue its support to SMEDP by assisting ASMED in mobilizing national level coordination mechanism under the Council. At provincial level, the SMEDP foresees public private steering committee for SME development which, she believed, will be welcomed by most projects as they intend to support public-private dialogue. The project is providing, as per policy advice, assistance to the Inter-Ministerial WG on “Personal ID of Business Founders”, and to the drafting of the Business-Investment Registration Decree under UEL. Finally as per request of ASMED and as priority set out by the Council in its meting of 9 September, the project will work on organizing an international seminar on Credit Guaranteed Funds/SME finance early second quarter next year, and therefore will look forward to dialoguing with the SME finance WG.

• Mr Trung, thanked UNIDO for the quick response to ASMED’ s assistance request within the scope of APEC 2006.

• Mr Scholtès stated that coordination in terms of approaches, methodology, tools from the WGs is ongoing and stressed the importance to have a collective monitoring system. It would be important in this respect to gear to the indicators set out in the SMEDP.

Another type of coordination, he proposed, can be related to the joint procurement of

equipment and setting up of information systems; at present, six project Management Units (PMUs) are established at ASMED, and therefore there might be room for the projects to share knowledge, local area network, etc. While he appreciated that setting up a common basket of resources for quick disbursement along the needs ASMED may be impeded by donors’ varying regulations, an effort should be made to identify, within these very regulations, workable procedures for the parallel deployment of resources such as expertise, training or equipment in a speedy and coherent manner, as per emerging needs at the partner institution.

• Mr Thai presented ASMED proposal for the improvement of the SMEPG. On the basis of MPDFfunded gap analysis, one recommendation referred to the rotation of the chairmanship of the Partnership Group. ASMED proposed that in every meeting, one new donor will be identified to co-chair the next meeting. For the next year meeting, ASMED proposed ADB and UNIDO to act as co-chairs together with ASMED. As for the frequency, the SMEPG can consider to gather once or twice a year. In his conclusion, Mr Thai encouraged the seven sub-WGs to perform more actively.

• Ms Lao-Araya, welcomed the idea for the rotation, and proposed the use of email chains for information-sharing, and that WG reports be circulated before each Partnership Meeting. She affirmed that the Partnership should be aligned to the CG process and meet twice a year.

• Ms Tas commented on the information sharing issue, by adding that the SMEDP is to provide a facility for the Partnership and WG under the SME info portal. Ms Lien will discuss with the programme partners this issue together with the provincial level work. She also informed that the by early next year the SME portal will host such information.

• Mr Van Der Ree, CTA of the ILO’s Integrated Small Enterprise Development project provided comments on the need for the Partnership to go beyond information sharing and be more effective on the substantive part in order to yield the discussion on concrete commitments.

• Ms Meissner requested ASMED to circulate the agenda of the APEC conferences so that to link to the work of the WGs for their contribution.

• Mr Trung informed that MPI is working with the Ministry of Foreign Affairs and the Ministry of Trade to define the agenda; subsequently, they will inform the donor community also on the necessary assistance need for APEC events.

• Mr Vistisen commended ASMED for the increased ownership in the coordination efforts and for holding the Partnership Meeting within the premises of MPI.

• Mr Iryu congratulated ADB on the next co-chairmanship and affirmed that Japan would continue providing support to the Partnership.

• Mr Thai thanked the Embassy of Japan for its support to the SMEPG and its overall technical and financial assistance to the SME sector at wide. He finally welcomed the new co-chair.

Concluding remarks

• Mr Scholtès noted with appreciation the results achieved by ASMED over the last two and half years since its establishment and since the first Meeting of the Partnership Group in April 2003. During this period, the profile and substance of the Partnership have evolved, and so as the role of the Agency that, he added, will take the leadership in the process. He wrapped up the meeting by saying that the Agency was confronted with a very heavy agenda, marked by important external commitments such as APEC 2006; progress were achieved in the coordination effort in the WGs. Regarding the way forward, there are changes in terms of organization with the rotating chairmanship, and the frequency will continue in sync with the CG process. The SME portal, the setting up of joint databases by the WGs, and attempts to harmonize policy programmes and procedures were welcomed initiatives. In addition to the portal, he informed that a mailbox for the PG had been created (sme.partnership@gmail.com) to receive comments or suggestions by stakeholders.

• Mr Iryu expressed its appreciation of the debates and thanked the participants for their active cooperation.

• Mr Trung thanked the SME partners and said that next meeting would be held at the MPI around April-May 2006.

Annex 1 - The SME Partnership and the Hanoi Core Statement

Contribution to the implementation of the Hanoi Core Statement

Background

The High-Level Forum on Aid Effectiveness held in February-March 2005 under the auspices of the OECD/Development Assistance Committee concluded with the Paris Declaration on Aid Effectiveness, a farreaching commitment by donors and partner countries to increase the effectiveness of aid through the three principles of ownership, alignment and harmonization. The same commitment was reiterated in September at the UN General Assembly in New-York. A few weeks later, the Vietnamese Government submitted the donor community assembled in Can Tho for the mid-term CG meeting a localized variant of the Paris Declaration, the Hanoi Core Statement (HCS) that builds upon the same tenets and defines a set of targets and indicators to measure progress along the way. The HCS was received very favourably by the donor community in Vietnam, and approved in principle at the end of September by the Prime-Minister who requested MPI to monitor its implementation. MPI and the Partnership Group on Aid effectiveness launched in May 2005 a donors’ baseline survey against which future progress will be assessed; the survey was conducted in two phases and completed on Nov 15.

Meanwhile, the co-chairs of the Consultative Group have called a meeting on Nov 18 to brief the chairs of the partnership groups on the HCS, and enrol the partnerships in its implementation.

The MPI baseline survey was articulated along the 14 indicators of the HCS. The purpose of this note by the SME Partnership is to supplement the baseline survey with a few pointed  contributions from the particular perspective of the SME sector, which has seen in recent years commendable attempts at greater coordination both amongst donors and between donors and Government.

ODA in the SME sector, and the HCS

| Indicator General scope | Application to the SME sector |
| --- | --- |
| 1 Authority over development process; leadership in aid coordination | The SME Action Plan formulated in 2005 under the leadership of ASMED, with contribution of over 20 groups of stakeholders |
| 2 Alignment of donors strategies | SME Action Plan used as reference for ODA programming |
| 3 Integrated vs parallel PMUs | Projects located at ASMED rely, at least partly, to PMUs established in the partner agency by the MPI leadership |
| 4 Capacity-building programmes driven by GoV’s capacity-building strategy | Projects located at ASMED are shaped by Decree 90/2001 that established the institution |
| 5 Use of country systems (procurement) | So far, projects at ASMED rely on donors’ own regulations governing procurement |
| 6 Use of country systems (financial management) | Projects at ASMED mostly follow donors’ own regulations on financial management |
| 7 Predictability of ODA disbursements | ASMED compiles donors’ yearly workplans on aid delivery (?) |
| 8 Use of country systems (EIA, SIA) | Not directly applicable to projects aimed at the SME sector (?) |
| 9 Common analytical work | Willingness of donors to use analytical work on SME issues developed by others |
| 10 Common project management tools | Willingness of donors to use common format for project appraisal, logframes, procurement, monitoring and reporting |
| 11 ODA based on national or sector programmes | The SME Action Plan can help mobilize donors’ support along a sector-wide strategy |
| 12 Increased autonomy of donors’ field offices | An issue between donors and their capitals; not sector-specific |
| 13 Results-oriented frameworks | The SME Action Plan features concrete targets, that can serve as collective goals of donors in their SME ODA plans |
| 14 Annual assessment of progress | The SME Partnership can help monitor collective progresstowards the targets of the SME Action Plan |

A presentation along these lines will be made at the meeting of the partnerships on Nov 18, on behalf of the SME Partnership. Kindly return your observations by Fri 18, noon at the latest to the Partnerships’ address sme.partnership@gmail.com . Your cooperation is appreciated.

Annex 2 – Minutes of the SME Partnership Group meeting, Embassy of Japan, 15 June 2005

On 15 June, the SME Partnership members convened at the Embassy of Japan.

As in previous gatherings, the Agency for SME Development, the Embassy of Japan and UNIDO co-chaired the event that drew an attendance of 80 representatives from both Government agencies and Donor community.

From the Government side, the MPI’s ASMED leadership, and the drafting team of the SME Development Plan participated in the forum. Mr Phuc, former Director-General of the Agency for SME Development and in that capacity, co-chair of the Partnership had been meanwhile promoted to the rank of Vice-Minister of MPI and attended the meeting as keynote speaker.

From the donors side, representatives from multi and bi-lateral donors as well as International Non Governmental Organisations attended the event: Canada, Denmark, Finland, Germany (GTZ, KfW), Italy, Japan (JICA), the Netherlands (SNV), Norway, Sweden, Switzerland (SDC), and the United States (USAID); Asian Development Bank, the European Commission, the International Finance Corporation (MPDF), International Labour Organization, United Nations Development Programme, United Nations Industrial development Organization, World Bank were represented.

Three topics shaped the agenda of the meeting: firstly, ASMED’s report to the donor community on the first draft of the SME Development Plan 2006-2010, to be integrated in the SEDP 2006-2010; secondly, the establishment of technical sub-working groups under the Partnership; finally, the presentations of current and planned projects and programmes in the SME field.

In his Opening speech, Vice Minister Nguyen Ngoc Phuc highlighted the importance of the SME sector as engine of Vietnam’s economic growth, being the entrepreneurial activity at the same time source of employment generation and deterrent to poverty, especially in rural and remote areas.

He complimented the work done in partnership with those donors that have been supporting the sector, and stressed the importance of reviewing donors’ assistance for a better coordination and cooperation. Mr Phuc also invited donors to provide their comments on the draft plan before it is submitted to the SME Promotion Council.

Lastly, he thanked the donors for their friendly and fruitful cooperation and introduced to the audience Mr Nguyen Van Trung, the newly-appointed Director-General (DG) of ASMED.

Remarks by the co-chairs

- Mr Trung, DG of ASMED and ex officio co-chair of Partnership briefed the donors on the SME Plan and guidelines of implementation, and pointed out the role of the SME support programme that aims to ease the challenges for both exporters and domestic producers to maximize the positive impact of WTO accession.

- While thanking the donors that constituted the sub-groups and drafted the relative ToRs, he stimulated the discussion on the creation of the sub-groups and their working modalities by raising three issues: participation of additional donors to the already established sub-groups; possibility to set up additional sub-groups; and working modalities and reporting procedures to the Partnership Group.

He concluded with a note of appreciation towards the SME survey and gap analysis run by MPDF that helps identify the needs of SMEs as well as donors target their interventions.

- Mr Fukahori, Head of Economic Division of the Embassy of Japan, reported about the need for cooperation in order to reach WTO accession, the Japan-Vietnam Joint Initiative on Monitoring, and the paper on “Suggestions for Strengthening the Competitiveness of Vietnamese Industries” that provides a summary of recommendations and comments for the next SEDP. He concluded by supporting the idea of linking up the SMEPG to the Partnership Group for Aid Effectiveness (PGAE).

- Mr Scholtès, UNIDO Representative, congratulated Mr Phuc for his appointment. Considering the importance of the SME Development Plan, he informed the Partnership that the three co-chairs had chosen not to convene a meeting of the Partnership before the mid-year CG meeting in Can Tho, but to wait for the release of a first draft of the SME Strategy and Action Plan scheduled for early June in order to make the meeting more effective. Mr Scholtès also stressed that UNIDO saw this particular meeting as a turning point in the history of the Partnership, on three counts: first, the constitution of technical sub-groups amongst experts and practitioners will make the Partnership more action-oriented; second, Vietnam is making rapid progress overall on the front of harmonization and aid effectiveness: the conclusions of a high-level meeting (Paris, February 2005) under the aegis of the OECD/DAC were localized in a matter of weeks in the April 2005 Hanoi Core Statement, and the SME Partnership is in a good position to contribute, with its expected results in the fields of harmonization, simplification of procedures and a monitoring system of indicators, a valuable case-study on aid effectiveness; third, the possibility of linking up the Vietnam SME Partnership to the Committee of Donor Agency for SME Development (SEDONORS), and more generally to the SME donor community at the global level, would provide guidance on best practices for the benefit of all technical assistance projects and programmes.

Presentation of the first draft of the SME Development Plan 2006-2010

- Ms Pham Thanh Ha, Deputy Division Manager, General Issues & Domestic Investment Encouragement Division of ASMED, on behalf of the Drafting Team, presented the first draft of the SME Development Plan 2006-2010 and Action Plan for its implementation.

She introduced the latest census and survey statistics that show the role and potential of SMEs and the Government strategy for the sector; she also described the process and the drafting team work that has led to the Plan and invited the participants to refer to the website www.business.gov.vn for the details regarding SME Development Reports by Ministries, Agencies, and Cities.

She then listed the SME Plan’s seven major priorities related to business regulations, access to land, access to finance, access to tools for increased competitiveness, access to skilled labour, entrepreneurship culture, management of implementation of the plan.

For each priority, a number of measures and activities were presented along with success indicators and two support programmes on “Maximizing the impact of WTO accession in four selected sectors” and “Creating employment in rural areas, disadvantaged areas and amongst minorities”.

The financial plan was also presented for consideration of all stakeholders: private sector and donors were invited to conceive their contribution according to that plan.

As concluding part, Ms Ha illustrated the next steps needed for the completion of the final draft before the submission to the Prime Minister.

Comments from donors

- Mr Kohata, Chief Technical Advisor of the JICA project aimed at supporting the three TACs, expressed his compliments for the comprehensiveness of the draft and put forward some observations: in relation to policy measure and taxation, (page 17 of the June 08 version of the SME Strategy and Action plan) while considering ASMED as the leading Agency on the issue, he noted that there were no indications about possible ASMED divisions in charge of the matter; as far as credit funds are concerned (page 32), he asked ASMED leadership to promote and accelerate their establishment throughout the country; (page 36) as regard to the institutional setting, he observed that ASMED should be the key agency under the MPI; (page 76) he stressed the importance of data collection; (page 70) on the guarantee fund, he asked to consider the setting up of financial institutes as priority.

- Ms Araya, ADB Head of Finance, Trade, Governance and Private Sector, commended the Government to assume full ownership in developing the strategy, and informed that ADB technical assistance is targeting, inter alia, the field of land registration an National Business Information Network (NBIN); the refinement of the monitoring system in the plan by establishing output indicators and the definition of timeline with sequencing and identification of short, mid and long term actions would help the priority groups.

- Ms Meissner, Technical advisor of the EU Private Sector Support Programme, raised two issues: the Plan neglects the role of the private sector whereas good practices show that it has a leading role in designing and implementing strategy and therefore recommended its stronger involvement in support programme design; she affirmed the need for a stronger role of private agencies in implementation as well as for building up capacities of the private sector to formulate strategies; she then referred to the possible catalyst role of large companies as main forces and providers of know how in these strategies.

- Mr. Holde, Advisor of component one of DANIDA’s BSSP, delivered a note of appreciation towards the very participatory process, and asked whether there was a deadline for written comments. He referred to the “Government will take steps to encourage an effective market for BDS and phase out functions…” (page 60) as a very important statement.

- Mr Scholtès, UNIDO Representative, provided the following comments: with regard to the monitoring issue (page 61) the quantitative objectives as they are defined in the draft SME Strategy are neither specific nor verifiable. He also questioned the links between the formulation of SME Strategy on the one hand, and the work in progress towards a Unified Enterprise Law. To the extent that the latter piece of legislation will set the legal framework for SME activity in the years to come, it is somewhat surprising that there should be so little synergy between the two drafting teams: there is little intersection indeed between the experts working on legal issues (Common Investment Law and Unified Enterprise Law) and those working on the SME strategy.

- He also regretted that the SME Plan missed an opportunity to articulate in that sector the Government’s Agenda on Sustainable Development; the implementation of Agenda 21 is moving rapidly at both central and local levels, and the SME Strategy should likewise promote the environmental and social responsibility of enterprises.

- ASMED replied to the issues raised: as far as the deadline is concerned, ASMED requested donors to provide their written comments as soon as possible; the quantitative targets indicated in the SME Strategy are in effect backed by detailed analyses; and the personal involvement of the DG in the field of UEL as an instance of linkage with the SME Plan.

Discussion on the Partnership sub-groups

Acting as a co-chair, Mr To Dinh Thai, Manager of International Cooperation Division of ASMED, opened the discussion on the sub groups that will lead towards a more action-oriented Partnership; he referred to the meetings in March between ASMED and representatives of a number of programme and project managers/advisors. At those occasions, participants proposed on the establishment of seven sub Working Groups under the SME Partnership. Some of the participants volunteered to draft preliminary TORs for the identified sub groups as listed below. Mr Thai also emphasized that at this meeting ASMED proposed these persons to actively initialize the operation of the sub groups and to bring the results of discussion to the next SMEPG meeting about their sub group’s performance):

- 1. WG on Business regulation reform (Mr Ray, USAID)

- 2. WG on Local economic governance (Ms Kuesel, GTZ)

- 3. WG on BDS (Mr Vistisen, DANIDA)

- 4. WG on Sectoral approaches (Ms Meissner, EU)

- 5. WG on SME finance (Mr Kohata, JICA)

- 6. WG on Sustainable business practice (Ms Nguyen, MPDF)

- 7. WG on Business research and monitoring (Ms Tas, UNIDO)

As detailed ToRs are drafted and a driver for each group identified, Mr Scholtès urged the sub-groups to starting working on coordination between projects and to engage in a more proactive involvement in the form of joint activities or pulling resources. He also encouraged other projects with concrete operations underway and interested to be part of any sub-group to touch base with the relevant WG coordinator; however, the sub-groups should remain focussed and include only those donors that have a concrete interest in the respective themes: allowing too broad a participation would undermine their effectiveness and would only duplicate the work of the Partnership itself.

- Ms Nga, UNDP Programme Officer, requested to participate in the group on Business regulation reform (Mr Ray, USAID) since UNDP is involved in regulatory reform projects at central land local level as well as in the work related to CIL and UEL.

- Ms Araya, ADB, proposed that a group on land issue be established, as this is the second priority of the SME Plan; she also affirmed that there are no linkages between the priorities and WGs.

- She added that as the ADB funded project “Making market work better for the poor” and the ADB technical assistance project are dealing respectively with value chain and licensing, representatives from these two projects will be willing to participate in the WG on Sectoral approaches and WG on Business regulation reform.

- Mr Ray added that the establishment of the land sub-working group can depend on the number of interested donors who will indeed join the activities of that particular sub group.

- Mr Guitard, Advisor of SMEDF, observed that representatives from banks are not represented and that would be interesting to link the different projects, including their funding, to the planning strategy.

- Ms Tas, CTA of UNIDO-ASMED project, while responding to the proposal of linking the sub-groups work to the draft of the SME plan, she referred to the need for maintaining full national ownership in the formulation process. She also recommended that those projects/programmes representatives of WGs with critical mass of members to assess their input to the group by the end of June.

- Mr Scholtès thanked the participants for their comments, and suggested that additional sub-groups such as the one on land use proposed by ADB can be created whenever there was sufficient interest amongst several donors and one of them willing to act as a driver of the group.

- Mr Thai concluded by encouraging the WGs to initiate the work and proposed that the future results be submitted and discussed on the occasion of the next Partnership; regarding the formation of additional sub-groups, ASMED will welcome any new idea, but reminded the importance of having practitioners involved. Land policy can be discussed within the WG on Regulatory reform.

Presentation of current and planned project and programmes

- Mr Kohata, made a presentation on “Enterprise survey in northern province and SME policy”. In his presentation, he proposed ASMED to consider the experience and best practices of the main SME policy in advanced countries (US, UK, Japan, etc.), and particularly under each one of the four major components of finance, taxation, technical and management support. He also presented the functions of TACs as key bodies that work in cooperation with the DPI at provincial level and that receive support from ASMED’s different divisions. He announced that the final report will be available in July.

- The independent consultant Nhu-An Tran, MPDF’s “Donor PSD interventions in Vietnam: an analysis of potential gaps and conflicts”. Following donors’ request, this study was carried out in cooperation with ASMED with the objective to identify gaps, overlaps and conflicts, and provide recommendations to harmonize PSD activities. Current PSD activities amount to 58 projects inventoried with 27 donors involved. Findings in terms of technical areas, location, counterparts, beneficiaries, sectors, technical approach, and donor coordination were presented. Finally recommendations to ASMED, the SMEPG, and donor-to-donor were put forward.

- Mr Shrestha presented SNV international activities with a focus on the component “Market to access for the poor”. The activities under this component cover seven provinces (Lai Chau, Lao Cai, Son La, Thai Nguyen, Ninh Binh, Quang Binh, Thua Thien Hue) and are related to value chain development, enabling environment, access to finance (microfinance).

- Ms Kuesel announced that the GTZ programme was signed early June and that she will provide further information on the occasion of the WG presentation in the next Partnership. Besides, as GTZ is involved with UNDP, GTZ, PMRC to support the CIL, UEL, she informed that the available documents will be shared with the partnership members.

- Support to Trade Promotion and Export Development in Vietnam (seco-SIDA)  Mr Chevalier, Technical advisor of the project, underlined the importance of two priorities in the Plan, enterprise culture and competitiveness; the current project, which is being implemented with Vietrade, is concentrating on various aspects of these two prioritises. At present, the project activities are focusing on the assessment of export potential in the handicraft, wood and furniture, plastic, tea and medicinal herb sectors.

- Mr Holde, advisor of BSPS, provided a snapshot of the main activities to be carried out and invited donors to share information on the issue of occupational health and HIV/AIDS in the workplace.

Concluding remarks

The Embassy of Japan co-chair concluded by affirming the need to link whatever decision taken under the SMEPG to the Partnership Group for Aid Effectiveness (PGAE).

In his concluding remarks, UNIDO co-chair made reference to the explicit request from ASMED to look into the management and operational modalities of the JICA project. As these modalities are considered to be a model to be followed by other donors, he invited the organization’s leadership to provide additional information on the issue.

ASMED co-chair wrapped up the meeting by expressing the gratitude for all donors’ and projects’ representative for their presence and efficient comments at the meeting; also, he thanked Embassy of Japan for hosting the event.

FINANCIAL SECTOR PARTNERSHIP

The Government-donor financial sector working group was established in late 1999 to discuss the proposed banking reform program developed by State Bank of Vietnam (SBV), to support implementation of that program, and to coordinate donor support on banking reform.  Since that time, the working group has expanded beyond just banking reform and now covers a wide range of financial sector issues, including capital market development, and representatives of the Ministry of Finance (MOF) and State Securities Commission (SSC) are invited to participate in the meetings.

The partnership on financial sector reform is informal, but serves as an effective forum in which the Government and its partners can periodically share information on the financial sector reform program, provide updates on current financial sector developments, and coordinate various donor assistance activities.  In addition, the working group serves as a forum for seeking donor assistance.

Strong Government Ownership

Implementation of the Government’s financial sector reform program continues with strong donor support as evidenced by an ever increasing number of related assistance projects.  The working group is now meeting on a quarterly basis with the third quarter meeting held in September 2005 to discuss progress on the banking reform agenda and assistance needs of the SBV, as well as an update of donor projects to support change in the financial sector.  The meeting was hosted by the State Bank of Vietnam (SBV), chaired by a Deputy Governor with participation of representatives from 15 donor organizations and donor-funded projects.

Government Banking Reform Program

The SBV introduced the banking reform progress made and the measures being taken to address the lingering problem areas.  The SBV touched on the three core areas of reform that he presented in the April 2005 Donor meeting:

1.	Restructuring the State Owned Commercial Banks (SOCBs):  The banks had 19 billion VND of capital injections to raise capital adequacy and the banks have settled 92% of all Non-Performing Loans (NPLs) accumulated to end-2000.  The new loan classification regulations (Decision 493) were issued on April 22 and the banks have been instructed to apply the new standards and deal with the resulting NPLs.  The new regulations require further study in terms of the application of risk-based classification of loans by banks.  In addition, a new regulation on prudential standards (Decision 457) was issued on April 19 and is expected to help clarify what standards need to be met in terms of capital adequacy.  Most of the SOCBs are working to improve the standards and performance with new management tools, enhanced organizational structures, internal controls, staff training, and other methods. Then banks have implemented IAS audits and are implementing the audit recommendations and all of the SOCBs have credit manuals (2004) and strategies to 2010.

2.	Equitization of the SOCBs:  The equitization plan for Vietcombank (VCB) has been developed and the Prime Minister has approved of the broad roadmap for the bank’s equitization already.  The minimum share of the Government in VCB will be 51% and by the end of December 2005, the bank will have the valuation process completed by international consultants.  The Mekong Housing Bank (MHB) will also be equitized and the plan has been submitted to the Prime Minister for approval.  The valuation of the MHB will also be completed by the end of December 2005.

3.	Accelerating International Integration:  The SBV is reforming many aspects of operating environment for banks to meet international standards.  The SBV has issued or is developing three key regulations that are based international standards, including the Basel Core Principles:  Decision 493 on loan classification, Decision 457 on prudential standards, and a draft Decree to allow the establishment of wholly foreign-invested banks in Vietnam.

Aligning Assistance to the Strategic Development Plans

There continues to be good accord between the sections on financial sector reform in the Government’s strategic development plans, including the Socio-Economic Development Plan to 2010 and the Comprehensive Poverty Reduction and Growth Strategy, and overall donor supported technical and lending assistance.  In addition, the key Government agencies involved in reform implementation, the SBV and SSC, are linking their issued sector development strategies to their assistance needs and priorities.  The Government’s strategic plans, both the overall and sector specific, enjoy strong backing by the members of the working group on banking reform.  This is expected to continue to be the case going forward.  The SBV outlined its assistance programs in a number of key areas of reform in the September meeting as follows:

- Conducting a Basel Core Principles Assessment;

- Establishing a new corporate governance framework for banks;

- Implementing a CAMELS-based rating system for the examination of banks;

- restructuring the Vietnam Bank for Social Policies and the Bank for Investment and Development;

- Enhancing the effectiveness of bank supervision;

- Developing a comprehensive information system for the SBV; and

- Creating a roadmap for reform and future assistance needs.

The SBV also outlined the near-term future assistance needs for SOCBs, which included:  (i) risk management; (ii) asset and liabilities management; (iii) management information systems; (iv) internal audit; and (v) raising capital adequacy.  In addition, the SBV is working two key outputs for delivery to the Government by the first quarter of 2006 – the comprehensive banking reform roadmap and the methods to increase the charter capital of the SOCBs.

Donor Support for the Reform Agenda

At the September meeting, The World Bank presented some of the new projects it is supporting for banking and general financial sector reform.  The Bank presented the Financial Sector Modernization and Information Systems (FSMIS) lending operation for the SBV.  The focus of the FSMIS project is to support the SBV in improving:  bank reporting and monitoring systems, data collection, management, and analyses, management information systems, credit information systems, and other areas of systemic reform at the SBV.  The project is under preparation.  The Bank also explained the technical assistance (TA) project, funded by the ASEM Trust Fund (European Commission), to support the SBV’s efforts to define all technical assistance and capacity building activities needed for the implementation of the “Plan on International Economic Integration of the Banking Sector” and subsequent reform strategies for the SBV and banking sector.  The other major TA projects of the World Bank to support bank restructuring and to improve the supervisory and regulatory frameworks (all supported by the ASEM Trust Fund) were presented:

- In the area of bank restructuring, a technical twinning arrangement for BIDV to support the implementation of the bank’s restructuring plan and the twinning project for VCB closed in August.  The Bank is also supporting two SOCBs (Industrial and Commercial Bank of Vietnam and the MHB) conduct IAS audits for the years 2003 and 2004.

- In the area of supervisory and regulatory frameworks, a project was completed to assist the SBV develop the new regulatory framework for asset classification and loan loss provisioning, as well as prudential standards, for banks.  The regulations are now much closer to international standards and a follow-on project is ongoing to help the SBV pilot the regulations at three joint stock banks.  A Basel Core Principle Assessment will be started and support is being given to the SBV to implement a risk-based supervision system (CAMELS ratings system).  Finally, a project is underway to help the SBV devise a new regulatory framework for corporate governance for banks.

- There are also three other projects in two other areas – accounting and policy lending.  One project that is ongoing is to help the SBV apply IAS accounting standards for banks.  The other two projects are two provide capacity building for the policy lending institutions (the Development Assistance Fund and VBSP).

- Lastly, the Bank is supporting projects in the area of capital market development, including primarily an ASEM Trust Fund for capacity building at the State Securities Commission (SSC) and securities firms to accelerate capital markets development.

The International Finance Corporation (IFC) provided a full summary of the assistance projects that the IFC-MPDF is providing to support financial sector reform.  The IFC-MPDF is providing assistance to Asia Commercial Bank (ACB) and Saigon Commercial Bank (Sacombank) on risk management and asset-liability management, as well as the application of IAS accounting.  Support is also being provided to support the Bank Training Center and their programs in a variety of issue areas, including credit risk management.  Finally, the IFC-MPDF is providing assistance to the SBV to establish a private sector credit bureau.  A strategic framework for the bureau has been presented to the SBV and a second phase on implementing the strategy is being developed.

The US Agency for International Development (USAID) presented its support, through the STAR Project, on financial sector issues, including advisory services on the Law on Credit Institutions, the Law on the SBV, the Law on Negotiable Instruments, and the Securities Law.  USAID may become more engaged in new areas, such as deposit insurance, and suggested that initiatives with private banks would be useful ways of improving the sector.

The Australian Agency of International Development (AusAID) presented an update on the progress of their project on helping the SBV with an international integration study.  The results are two studies – (i) on the competitiveness of the banking sector, and (ii) on the process of international integration.

The Asian Development Bank (ADB) presented the upcoming US$500,000 TA that it will be providing to the SBV to support the implementation of the Anti-Money Laundering (AML) Decree (No. 74/2005/ND-CP of June 7, 2005).  The project has four components: (i) helping implement the decree; (ii) public awareness campaign; (iii) developing guidelines and circulars; (iv) developing the supporting IT infrastructure.

The Swiss State Secretariat for Economic Affairs (SECO) stated it is working with the SSC to support its training center.

The European Commission detailed its Euro 1.5 million project to support banking supervision, which includes three parts: (i) training of supervisors; (ii) training of bankers on new products and regulations; (iii) training partnership with Singapore.

The International Monetary Fund (IMF) presented some of the TA being provided to the SBV, including assistance in drafting the foreign exchange controls ordinance, banking supervision training, development of monetary statistics and improving open market operations and monetary operations, and workshops on AML issues.

Finally, the German Gesellschaft fur Technische Zusammenarbeit (GTZ) GMBH outlined the assistance provided to the SBV and other agencies involved in financial sector development in five areas:  (i) improving monetary policy; (ii) enhancing risk management practices at Joint Stock Banks; (iii) establishing an association for People’s Credit Funds; (iv) training on IAS; and (v) developing the Securities Law and the Securities Depository.

Next Steps for the Working Group

The conclusion of the September meeting was that the working group was a valuable forum to discuss reform issues and share information on projects and the financial sector donor group could serve as a model to other such issue groups.  However, it was suggested that the SBV take full ownership of the group and take initiatives to improve some of the core documents.  The suggestions included:

- Eliminating the old, closed projects from the Financial Sector Assistance Matrix and reorganizing the matrix based on the SBV’s reform priorities.

- Adding more detail to the Matrix to provide a better idea of the size, scope, and duration of the assistance projects in the sector.

- Developing a more user-friendly format and access point for the Matrix and donor working group member list.

- Transitioning the Matrix to the SBV to revise, update, and disseminate regularly.

The comprehensive matrix covering the technical assistance and lending support provided by all donors on the Government’s financial sector reform agenda has been updated, improved, and expanded to cover most areas of financial sector support beyond banking (such as policy lending, microfinance, and non-bank financial institutions).  The Financial Sector Assistance Matrix is organized by financial institution and then by function for easier navigation, with active links to the appropriate contacts for each project, and it is now posted on the on the World Bank Vietnam Country Office (www.worldbank.org.vn).

financial sector Assistance Projects in Vietnam

Financial Sector Donor Working Group

As of November 8, 2005

| REFORM AREA | TASK | DONOR / PROVIDER | STATUS | START DATE | CONTACT |
| --- | --- | --- | --- | --- | --- |
| State Owned Commercial Banks (SOCBs) |  |  |  |  |  |
| Bank Restructuring | Support for Implementation of ICB Restructuring Plan | AFD | Ongoing | Sept. 2003 | Marc Gilbert, AFD gilbertm@groupe-afd.org |
|  | Support for the implementation of the restructuring plan for BIDV – phase 2 | World Bank / European Union ASEM Trust Fund | Approved | 2004 | James Seward, WB jseward@worldbank.org |
|  | Business strategy for VCB | GTZ | Ongoing | 2002 | Andreas Hauskrecht, GTZ hauskrecht@sbcglobal.net |
|  | Reform internal auditing for VCB | GTZ | Ongoing | 2002 | Andreas Hauskrecht, GTZ hauskrecht@sbcglobal.net |
|  | Mekong Housing Bank IAS Audits, Assessment, and Preparation for Strategic Partnering / Equitization | World Bank / European Union ASEM Trust Fund | Approved | 2003 | Amanda Carlier, World Bank acarlier@worldbank.org |
|  | TA on overall strengthening of risk management, assets-liabilities management, conversion to IAS accounting to Asia Commercial Bank (ACB) – US$ 850,000. Major components: 1. Credit Risk Management (including Gap analysis, recommendation, scoring models for corporate and retail loans): completed 2. IFRS reporting training: completed 3. IT mordernization: contract is under negotiation 4. ALM related TA: contract is under negotiation 5. Strategic Planing: consultant selection is under the process 6. Senior resident advisor: consultant selection is under the process | Swiss trust fund Dutch fund Japanese fund IFC MPDF | On-going | 2002 | Lam Bao Quang, IFC lquang@ifc.org |
|  | TA on overall strengthening of risk management, assets-liabilities management, conversion to IAS accounting to Saigon Commercial Bank (Sacombank) – US$ 850,000. Major components: 1. Credit Risk Management: completed 2. IT mordernization: completed 3. ALM: completed 4. Senior resident advisor: consultant selection is under the process. | Swiss trust fund Dutch fund Japanese fund IFC MPDF | On-going | 2002 | Lam Bao Quang, IFC lquang@ifc.org |
|  | Advisory assistance for the Mekong Housing Bank equitization transaction | IFC | Ongoing | 2004 | Sin Foong Wong (IFC) |
|  | Mekong Housing Bank TA for Credit Management, Treasury and Asset Liability Management, HR management, IT,and MIS | Seco / Private Sector | Ongoing | 2004 | Barbara Jäggin, Swiss Embassy Barbara.jaeggin@han.rep.admin.ch Quondam Partners, Juerg Vontobel quondam@bluewin.ch |
|  | Workshops in Bank Restructuring | Seco (Swiss Embassy) / Private Sector | Approved | Dec-03 | Barbara Jäggin, Swiss Embassy Barbara.jaeggin@han.rep.admin.ch Quondam Partners, Juerg Vontobel quondam@bluewin.ch |
| Asset Resolution | Non-performing loan resolutions for Joint Stock Banks | GTZ | Ongoing | 2004 | Andreas Hauskrecht, GTZ hauskrecht@sbcglobal.net |
| Payment System | Payment System and Bank Modernization Project | World Bank | On-going | 1996 | Miguel Navarro-Martin, WB Mnavarromartin@worldbank.org James Seward, World Bank Jseward@worldbank.org |
|  | Second Payment System and Bank Modernization Project | World Bank | Approved | 2005 | Miguel Navarro-Martin, WB Mnavarromartin@worldbank.org James Seward, World Bank Jseward@worldbank.org |
|  | Payment System and Bank Modernization for VBARD (extension of the WB PSBM) | AFD | Ongoing | Sept.2003 | Marc Gllbert, AFD |
|  |  |  |  |  | gilbertm@groupe-afd.org |
| Auditing | IAS Audits 2003-2004 for ICB | World Bank / European Union ASEM Trust Fund | Ongoing | 2003 | James Seward, World Bank |
|  |  |  |  |  | jseward@worldbank.org |
|  | Audit Training series | GTZ | Ongoing | 2003/4 | Andreas Hauskrecht, GTZ |
|  |  |  |  |  | Ahauskrecht@sbcglobal.net |
| Joint Stock Banks (JSBs) |  |  |  |  |  |
| Risk Management | Risk Management for Joint Stock Banks | GTZ | Ongoing | 2003 | Andreas Hauskrecht, GTZ |
|  |  |  |  |  | hauskrecht@sbcglobal.net |
|  | Training of the JSBs credit departments, training of BRC in risk management | Seco (Swiss Embassy) / Private Sector / BTC | Ongoing | 1998 - 2004 | Barbara Jäggin, Swiss Embassy Barbara.jaeggin@han.rep.admin.ch |
|  | Credit Risk Management and Loan Portfolio Management - Workbook - Training manual - Training of trainers - Training courses US$ 60,000 Partner: Bank Training Center (BTC) | IFC-SME department and IFC-MPDF Netherlands trust fund | On-going | Jul-05 | Jacco Minnaar, IFC/MPDF jminnaar@ifc.org |
|  | Training and enforcement of capacities, specially in the fields of credit policies, risk management and sectoral analysis for VBARD | AFD | On-going | Sept. 2003 | Marc Gilbert, AFD gilbertm@groupe-afd.org |
| Organizational Change | Support to Bank Training Center (BTC) to provide quality training to commercial banks Major components: - Building the capacity of trainers - Certification program for credit function US$ 175,000/year Partner: Bank Training Center (BTC) | IFC-MPDF | On-going | 2002 | Jacco Minnaar, IFC/MPDF jminnaar@ifc.org |
| State Bank of Vietnam (SBV) |  |  |  |  |  |
| Organizational Change | SBV restructuring | GTZ | Ongoing | 2002 | Andreas Hauskrecht, GTZ |
|  |  |  |  |  | Hauskrecht@sbcglobal.net |
|  | Long-term training and technical assistance to the SBV on supervisory, regulatory and banking services issues | CIDA | Ongoing | Feb. 2004 | Claude Goulet/CIDA Claude.goulet@dfait-maeci.gc.ca |
|  | SBV Capacity Building in Regulation, Supervision, and Development | World Bank / European Union ASEM Trust Fund | Ongoing | 2003 | James Seward, World Bank |
|  |  |  |  |  | jseward@worldbank.org |
|  | SBV Capacity Building | European Union | Proposed | 2005 | Francisco Fontan, EC Francisco.Fontan@cec.eu.int |
| Supervision/ Safety-Soundness Standards | Establish chair for bank auditing at Banking Institute | GTZ | Ongoing | 2000 | Andreas Hauskrecht, GTZ |
|  |  |  |  |  | Hauskrecht@sbcglobal.net |
|  | Strengthening banking supervision/auditing | GTZ | Ongoing | 2000 | Andreas Hauskrecht, GTZ |
|  |  |  |  |  | Hauskrecht@sbcglobal.net |
|  | Training IAS | GTZ | Ongoing | 2003 | Andreas Hauskrecht |
|  |  |  |  |  | Hauskrecht@sbcglobal.net |
|  | Transition of VAS to IAS for banks and improving financial reporting | World Bank / European Union ASEM Trust Fund | Ongoing | 2003 | James Seward, World Bank |
|  |  |  |  |  | Jseward@worldbank.org |
|  | Anti-money laundering- assessment and assistance for drafting decree, action plan for FIU establishment | ADB | Ongoing | Sept. 2003 | Shigeko Hattori, ADB shattori@adb.org |
|  | Full Basel Core Principle Assessment of the SBV | World Bank / European Union ASEM Trust Fund | Approved | 2003 | James Seward, World Bank jseward@worldbank.org |
|  | Assisted self-assessment of the Basel Core Principles | World Bank/ASEM Trust Fund | Approved | 2004 | James Seward, World Bank Jseward@worldbank.org |
|  | Advisory services for strengthening banking regulation and supervision | IMF/MFD | Ongoing | 2004 | Il Houng Lee, IMF ilee@imf.org |
| Legal Framework for Banking | Review of State Bank and Credit Institutions Laws | GTZ | Ongoing | 2003 | Andreas Hauskrecht, GTZ Hauskrecht@sbcglobal.net |
|  | Technical advice on the State Bank and Credit Institutions Laws | CIDA | Ongoing | Jun-03 | Claude Goulet, CIDA Claude.goulet@dfait-maeci.gc.ca |
|  | Introduction of international standards (Basel Principles) | GTZ | Ongoing |  | Andreas Hauskrecht, GTZ |
|  |  |  |  |  | Hauskrecht@sbcglobal.net |
|  | Workshops, legal analysis and reference materials to support the development by the SBV of the key implementing decrees for the amended Law on Credit Institutions | USAID-STAR Project | Ongoing | Aug. 2004 | Dennis Zvinakis, USAID dzvinakis@usaid.gov Steve Parker, STAR Steve_Parker@DAI.com |
|  | Support for developing Decree on Foreign Banks | USAID (STAR Project) | Ongoing | Aug-04 | Dennis Zvinakis, USAID dzvinakis@usaid.gov Steve Parker, STAR Steve_Parker@DAI.com |
|  | Support for developing the Law on Negotiable Instruments | USAID (STAR Project) | Ongoing | Nov-04 | Dennis Zvinakis, USAID dzvinakis@usaid.gov Steve Parker, STAR Steve_Parker@DAI.com |
| Credit Information | Assessment of the CIC | World Bank / Spanish CTF | Ongoing | Nov. 2003 | James Seward, World Bank Jseward@worldbank.org |
|  | Implementation of strategic framework: drafting legal framework and partnership building: support setup of a private sector credit bureau US$ 70,000 Major components: 1. Technical Assistance: provide legal TA to SBV. This would include: - Developing legal framework - Developing code of conduct - Establishing licensing requirements. - Providing on-going consultation throughout the process and promotion/dissemination activities. 2. Partnership building/Sourcing: The project will seek interest from potential international credit bureaus and commitment from banking community and then as the trust broker, facilitate the establishment of a private credit bureau with participation of a reputable foreign investor/sponsor. Partner: State Bank of Vietnam | MPDF | Proposed | 2005 | Jacco Minnaar, IFC/MPDF jminnaar@ifc.org Nguyen Hanh Nam, IFC/MPDF NNam@ifc.org |
|  | Assessment of and technical workshops on the financial sector implications of the US-Vietnam Bilateral Trade Agreement | USAID-STAR Project | Ongoing | Nov. 2002 | Dennis Zvinakis, USAID dzvinakis@usaid.gov Steve Parker, STAR Steve_Parker@DAI.com |
| International Agreements | Assistance to SBV in formulating the strategy for international integration for the banking sector | AusAID | Ongoing | Oct. 2004 | Graham Alliband, CEG Facility Galliband@ceg.edu.com |
|  | Reserves Management Capacity Building | SIDA/Swedish Central Bank | Ongoing | May-03 | Karl-Anders Larsson, SIDA karl-anders.larsson@sida.se |
|  | Safeguards Assessment | IMF/Treasurer’s Department | Ongoing | 2001 | Il Houng Lee, IMF ilee@imf.org |
| Reserves Management | Assistance in auditing the SBV | IMF/MFD | Ongoing | 2004 | Il Houng Lee, IMF ilee@imf.org |
|  | Introduction of new monetary policy instruments | GTZ | Ongoing | Thru 2003 | Andreas Hauskrecht, GTZ |
|  |  |  |  |  | Hauskrecht@sbcglobal.net |
|  | Financial market/policies Train the trainer, HR management/appraisal, empirical research skills | Seco (Switzerland) / Graduate Institute for International Studies | Ongoing | Phase I: 1997-1999 Phase II: 2000-2002 Phase III: 2003-2005 | Barbara Jäggin, Swiss Embassy Barbara.jaeggin@han.rep.admin.ch Graduate Institute of International Studies Geneva, Prof. Camen Camen@hei.unige.ch |
|  | Training in Macroeconomic model-building and forecasting | INSEE/Banque de France/ ADETEF | Ongoing | 2002 | Alain Fontanel |
|  |  |  |  |  | Afontanel@hotmail.com |
| Monetary Policy | Workshops in Macroeconomic Policy Coordination | IMF | Ongoing | 2002 | Il Houng Lee, IMF ilee@imf.org |
|  | Staff exchange | Sida/Swedish Central Bank | Ongoing | 2003 | Karl-Anders Larsson, SIDA |
|  |  |  |  |  | karl-anders.larsson@sida.se |
|  | Guidance on monetary policy instruments and operations | IMF/MFD | Ongoing | 2004 | Il Houng Lee, IMF ilee@imf.org |
|  | Training SBV and Commercial Bankers, Monetary Instruments | GTZ | Ongoing | 2002 | Andreas Hauskrecht, GTZ Ahauskrecht@aol.com |
|  | Assistance in development of a database for tracking money market transactions | ADB | Approved | May-03 | Alessandro A. Pio, ADB Apio@adb.org |
| Money Market Development | SBV Capacity Building as Executing Agency for SME Credit Policies | JBIC | Ongoing | Dec. 2001 | Takayuki Sato, JBIC ta-sato@jbic.go.jp |
|  | SME Finance Project | JBIC | On-going | 1999 | Takayuki Sato, JBIC ta-sato@jbic.go.jp |
| SME Credit Policies | Pilot Study on Soft Infrastructure development for better Financial Access of SME | JBIC | On-going | Mar-03 | Takayuki Sato, JBIC ta-sato@jbic.go.jp |
|  | SME Credit Line (ICBV) | KfW | Ongoing | 2001 | Helmut Schoen, KfW |
|  |  |  |  |  | helmut.schoen@kfw.de |
|  | SME Development Program Loan (co-financed with ADB and AFD) | KfW | Ongoing | Dec-04 | Helmut Schoen, KfW |
|  |  |  |  |  | helmut.schoen@kfw.de |
|  | SME Revolving Fund | European Union | Ongoing | Oct. 2004 | Francisco Fontan, EC |
|  |  |  |  |  | Francisco.FONTAN@cec.eu.int |
|  | Housing Credit Line through Mekong Housing Bank | AFD | Ongoing | 2004 | Marc Gllbert |
|  |  |  |  |  | gilbertm@groupe-afd.org |
|  | Vietnam Competitiveness Initiative - training and technical assistance to joint stock banks (JSBs) to facilitate access to finance for SMEs | USAID | On-going | 2004 | David Brunell, USAID dbrunell@usaid.gov Bob Webster, DAI Robert_Webster@dai.com |
|  | Provide loan guarantees for Vietnamese joint stock banks to promote (a) credit extended to SMEs and (b) cashflow-based lending practices | USAID | On-going | 2003 | David Brunell, USAID dbrunell@usaid.gov |
|  | Comprehensive TA for the reform and development of the Bank for Social Policies (VBSP) | World Bank / European Union ASEM Trust Fund | Approved | 2003 | James Seward, World Bank Jseward@worldbank.org |
| Banking Supervision | Assist the SBV strengthen risk-based bank supervision, including through simplification of database and staff training. Provide comments on off-site banking supervision plan of the SBV, and asset classification, prudential ratio, and internal audit regulations for commercial banks. | MFD | Ongoing | Apr. 2004 – Nov.2005 | Il Houng Lee, IMF ilee@imf.org Nga Ha, IMF Nha@imf.org |
| Monetary and Exchange Operations | Assist the SBV strengthen OMO, TB, and money market operations. Introduce indirect monetary policy management tools and methods to SBV staff, including on sterilization and setting policy rates. | MFD | Ongoing | April-Nov. 2005 | Il Houng Lee, IMF ilee@imf.org Nga Ha, IMF Nha@imf.org |
| Policy Lending Institutions |  |  |  |  |  |
| Operational Framework | Comprehensive TA for the reform and development of the Bank for Social Policies (VBSP) | World Bank / European Union ASEM Trust Fund | Approved | 2003 | James Seward, World Bank Jseward@worldbank.org |
|  | Comprehensive TA for the reform and development of the Bank for Social Policies (VBSP) | World Bank / European Union ASEM Trust Fund | Approved | 2003 | James Seward, World Bank Jseward@worldbank.org |
| Microfinance Institutions (MFIs) |  |  |  |  |  |
| Access to Microfinance | Legal, regulatory and supervisory framework for MFIs | ADB | Ongoing | Aug. 2002 | Brett Coleman, ADB bcoleman@adb.org |
|  | Modernizing a number of People's Credit Fund and improving the services of the Central People's Credit Fund | Développement international Desjardins (DID)/CIDA | Approved | Feb. 2004 | jmcrevier@did.qc.ca |
|  | Loan and technical assistance to support rural enterprise finance through VBARD and People’s Credit Funds | ADB | Ongoing | Nov. 2000 | Alessandro A. Pio, ADB Apio@adb.org |
|  | Loan to support rural enterprise finance through VBARD | AFD | On-going | Sept. 2003 | Marc Gllbert gilbertm@groupe-afd.org |
|  | Study On Rural Finance | JBIC | On-going | Feb. 2003 | Takayuki Sato, JBIC ta-sato@jbic.go.jp |
|  | Rural Credit and Saving Program (VBARD) | KfW | Ongoing | 2002 | Helmut Schoen, KfW helmut.schoen@kfw.de |
|  | Revolving Credit Fund for Poverty Alleviation (VBARD) | KfW | Ongoing | 2001 | Helmut Schoen, KfW helmut.schoen@kfw.de |
|  | Rural Finance Loan - Micro-finance Loan Fund (MLF) and its implementation agencies (Micro-finance Institutions, MFIs) | World Bank | Ongoing | 2003 | Liza Valenzuela, World Bank lvalenzuela@worldbank.org |
|  | Institutional strengthening for the Vietnam Women’s Union on providing microfinance and advice on the MFI legal framework | Embassy of Belgium | Approved | 2004 | Marcus Leroy, Embassy of Belgium badc@hn.vnn.vn |
|  | Institutional strengthening for the Vietnam Women’s Union on providing microfinance and advice on the MFI legal framework | Embassy of Belgium | Approved | 2004 | Marcus Leroy, Embassy of Belgium badc@hn.vnn.vn |
|  | Institutional strengthening for the Vietnam Women’s Union on providing microfinance and advice on the MFI legal framework | Embassy of Belgium | Approved | 2004 | Marcus Leroy, Embassy of Belgium badc@hn.vnn.vn |
| Non-Bank Financial Institutions (NBFIs) |  |  |  |  |  |
| Leasing | Second Financial Sector Program Loan to support the development of alternative channels of market-based financial intermediation including insurance sector, leasing sector, money market and capital market, and financial market infrastructure such as secured transactions registration and accounting association | ADB | On-going | Jan. 2003 | Shigeko Hattori, ADB shattori@adb.org |
|  | Program Loan, co-financed with ADB and AFD to facilitate diversification of funding sources of financial leasing companies to improve credit access for SMEs | KfW | Ongoing | Dec. 2004 | Helmut Schoen, KfW helmut.schoen@kfw.de |
|  | Second Financial Sector Program Loan, cofinanced with ADB, to support the non banking financial sector. | AFD | On-going | 2003 | Marc Gilbert, AFD gilbertm@groupe-afd.org |
|  | Technical Assistance for Capacity Building for Nonbank Financial Institutions and the Capital Market | ADB | Ongoing | 2003 | Shigeko Hattori, ADB shattori@adb.org |
| Market-Based Financial Intermediation | Capital Market Development | GTZ | Ongoing | 2004/5 | Andreas Hauskrecht |
|  |  |  |  |  | Hauskrecht@sbcglobal.net |
|  | TA for the State Securities Commission (SSC) for capacity building, linking the equitization process with market development, and investor education. | World Bank / European Union ASEM Trust Fund | Approved | 2003 | James Seward, World Bank Jseward@worldbank.org |
|  | TA for the State Securities Commission (SSC) for the development of the securities market and the medium and long-term capital market | Seco (Swiss Embassy) / Private Sector | Ongoing | 2004 | Barbara Jäggin, Swiss Embassy Barbara.jaeggin@han.rep.admin.ch |
|  | Assistance to the MOF to develop the corporate bond market | NRI (Japan) | Approved | 2004 | Kengo Mizuno, NRI |
|  |  |  |  |  | k-mizuno@nri.co.jp |
|  | Assistance to the Government (MOF, SBV, MPI, OOG, MOJ) for external debt management | UNDP | Ongoing | 2000 | Trinh Tien Dung, UNDP |
|  |  |  |  |  | Trinh.tien.dung@undp.org |
|  | Capacity building assistance to the MOF for financial policy analysis | UNDP | Ongoing | 2003 | Trinh Tien Dung, UNDP |
|  |  |  |  |  | Trinh.tien.dung@undp.org |
|  | Comprehensive assessment of municipal bond market issuances and development | USTDA | Approved | 2004 | Paul Marin, USTDA PMarin@tda.gov |
|  | Support the SSC to develop the legal framework for securities market development and build capacity for SSC and other securities intermediaries; provide public and investor education and training | USAID | Ongoing | Sep-05 | David Brunell, USAID dbrunell@usaid.gov |
|  | Supporting the SSC to develop a (transitional) decree on unlisted shares and the (planned) law on securities in support of the US-Vietnam BTA and WTO accession. | USAID-STAR Project | Ongoing | Nov. 2003 | Dennis Zvinakis, USAID dzvinakis@usaid.gov Steve Parker, STAR Steve_Parker@DAI.com |
|  | Workshops, legal analysis and reference materials to support the development by the State Securities Commission of a new Law on Securities and a Decree on Over-the-Counter Trading | USAID-STAR Project | Ongoing | Aug. 2004 | Dennis Zvinakis, USAID dzvinakis@usaid.gov Steve Parker, STAR Steve_Parker@DAI.com |
|  | Capacity building for the National Registration Agency of Secured Transactions | ADB | On-going | Dec. 2002 | Armes Adhikari, ADB Radhikari@adb.org |
|  | Supporting the Ministry of Justice to develop the legal framework for secured transactions. | USAID-STAR Project | Ongoing | 2002 | Dennis Zvinakis, USAID dzvinakis@usaid.gov Steve Parker, STAR Steve_Parker@DAI.com |
| Sustainable Finance | Sustainable finance program for financial institutions – based on the business case: manage risks and opportunities that arise from social and environmental issues. Major components: - Awareness raising seminars (completed) - Training of trainers - Sustainable finance training (cost sharing) - Targeted technical assistance to committed banks (based on cost-sharing) US$ 230,000 Partner: Bank Training Center (BTC) as implementing agency, targets all financial institutions in Vietnam. | IFC-SFMF and IFC-MPDF Luxemburg trust fund | On-going | Aug-05 | Jacco Minnaar, IFC/MPDF jminnaar@ifc.org |

TRADE  WORKING GROUP

Vietnam’s WTO Accession: Summary of TA programs

# Updated as of November 11, 2005

| ##### Donor | Project | Project budget | Start - End | Related WTO Agreements | Focus area | Objectives | Project components | Executing Agency | Beneficiaries |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ADB | Tariff and Industrial Policy Analysis |  | 8//2003-March 2004 |  | Policy analysis and capacity building. | Analysis of trade policy regime and the structure of protection in the context of trade liberalization. |  |  |  |
| ADB | Capacity building for MOF to support Analysis (tariffs, industry and subsidy) for WTO Accession | $150,000 | January-December 2004 |  | Policy analysis and capacity building | Build capacity in MOF to conduct tariff policy analysis; review and assess in detail the current Government assistance programs, in particular, the financial supports, such as the subsidies in the context of WTO accession; propose modalities/approaches to the Government on how to deal with these issues; and assist MOF to strengthen the WTO accession and implementations issues. |  | MOF |  |
| ADB | The Implication of Vietnam’s WTO Accession on Existing Investment Incentives and Market Reform |  | December 2004-February 2005 |  | Policy, and institutional analysis. | Detailed diagnosis of the regulatory framework of investment in Vietnam. Examine the possible economic and social implications and adjustment costs that the elimination or adaptation of investment measures and incentives may have on the key domestic goods and services sectors. This work intends to build on the TA for Capacity building for MOF to support analysis of tariffs, industry and subsidy for the WTO accession, and covers services and manufacturing sectors. |  |  |  |
| Australia/ AUSAID | AusAid Regional Trade Analysis and Reform Project (TARP) – formerly WTO Capacity Building Project | 3,500,000 USD, design finalised | /2005 /2007 |  | Policy analysis and capacity building in 4 selected ASEAN countries | To support a program of WTO related capacity building | Training Researches Policy Analysis | MOT | MOT |
| Australia/ AUSAID | AusAid-MARD program on capacity building for WTO accession and training on WTO-related issues under CEG facility | 600,000 USD | /2003 /2005- | Agriculture Agreements | Policy analysis and research Capacity Building | Improving understanding of the implications of integration, Developing policies to optimize the domestic consequences of integration | Policy research Training seminar | MARD | MARD |
| Australia/ AUSAID | Vietnam integration in the World Economy Capacity Building for Anti Dumping under CEG facility | 393,032 USD | 2003-2004 | Anti-dumping Agreement | Policy development | Improving the capacity to develop policy | Policy development | MOT | MOT |
| Australia/ AUSAID | Technical Assistance for Formulating a Strategy of International Integration in the Banking Sector | 460,000 USD | 2003-2004 | Strategy of Integration in the banking sector | Policy analysis and research Capacity Building | To strengthen the capacity of the SBV to formulate and implement a Strategy on International Integration of the Banking Sector; | - Research on existing context and proposed strategies for the formulation and implementation of the Integration Strategy completed. - Increased skills of SBV staff and other selected stakeholders in policy analysis, formulation and implementation on banking integration issues | SBV | SBV |
| Australia/ AUSAID | Assistance for improving the Commercial Law in the integration process. | 100,000 USD | 2004 | Improving the domestic legal document regulating the commercial activities and the international integration requirements | Policy development Capacity Building | To improve the professional knowledge and legislative capacity of those who participate in the drafting and approving of Commercial Law and its major supporting guidelines. | Draft, finalize and incorporate articles/stipulations related to the issues of Commodity futures trading and Franchising in the draft Commercial Law. Organize workshops to gather feedback/raise awareness on the revise draft | MOT | MOT |
| Australia/ AUSAID | AusAid Regional SPS Capacity Building Project | 3,000,000 AUD | /2005 /2007 | SPS Agreements | Capacity Building on Trade related Plant and Animal quarantine for 8 ASEAN countries | Building capacity for MA | Study tour, surveys, booklet, Seminars workshops and courses on the SPS issues /2005 | N\a | Government agencies concerning SPS issues |
| Australia/ AUSAID | Technical Assistance to the development of draft(s) of the Ordinance on Standardization | 40,000 USD | 2005 | TBT and SPS Agreement | Policy development Capacity Building | To create a legal framework for standardisation activity in Vietnam to meet its socio-economic needs and the requirements of WTO Agreements, particularly the TBT and SPS Agreement; and facilitate Vietnam’s accession in WTO. | - Advice on the Draft Ordinance - Organize workshops to gather feedback/raise awareness about the Ordinance | STAMEQ (MOST) | STAMEQ (MOST) |
| Belgium | Trade liberalization and environment, socio-economic impact of WTO accession | 100,000 EUR Euro |  | Environment |  |  | Assess the socio-economic impact of VN’s accession to WTO Assess impact on the environment |  |  |
| Canada/ CIDA | APEC Economic Integration Program (APEC/EIP) | 9,000,000 CAD | /2004 /2008 |  | Capacity building | To assist in building the capacity of some developing economies in APEC in Southeast Asia to negotiate their accession to the WTO and/or implement their specific WTO commitments. | Training, WTO-related technical assistance, development of regional learning forum | Conference Board of Canada / Estey Centre for Law and Economics in International Trade | MOT and other ministries and five other APEC countries |
| Canada/ CIDA | Legal Reform Assistance Project (LERAP) | 4,995,000 CND CAD | /2001 /2006 |  | Capacity building | Assisting Vietnamese Government in promoting the rule of law by achieving greater efficiency, coherence and transparency in the legal system. | Strengthening the legal capacity for international economic integration, capabilities for the enforcement of civil judgments and Increasing comparative law research and analysis. | BearingPoin tand University of Victoria | Ministry of Justice |
| Denmark/ DANIDA | Agricultural Sector Program Support / WTO assessment and related training | 330,000 USD | 5/2002 – 5/2004 |  | WTO assessment and related training |  |  | MARD/ Program Officer Pham Thi Hong Hanh |  |
| Denmark | Framework conditions and services improved for business competitiveness | 2,000,000 USD | 2005-2009. NOTE: input awaits final GoV approval |  |  | -Changed role of, or improved service delivery by government (and quasi-government) organisations that directly benefits the private business sector. -Capacity of STAMEQ to deliver international standardisation and certification services significantly enhanced. -Improving access of businesses to information about technical barriers to trade for exporting by strengthening and widening the scope of services delivered by the STAMEQ WTO Office. | -National-level initiatives that directly increase private business competitiveness through improved access to capital, land, and export markets. [Specific initiatives to be specified] -Information campaign about standards and certificates led by the VPC. -Study of certification services market. -Develop long-term Business Plan for QUACERT. -Direct capacity building of the WTO/TBT Enquiry Point -Twinning relationship with Dansk Standard. | Project Facility in cooperation with ASMED and private business. The Project Facility (8 mill USD) constitutes the Component 3 of the 33 mill USD five Component Business Sector Programme Support (BSPS) to GoV. | STAMEQ QUACERT WTO/TBT Enquiry Point |
| Denmark | Research project on international economic integration | 250,000 USD | 2005-2009 |  | Strengthening development research and policy analysis capacity |  | Increased understanding of the issues surrounding Vietnam’s WTO accession and the potential impacts hereof: (i) Establishment of an inventory of what is already known; (ii) Assessment of potential impacts of WTO accession; and (iii) Elaboration of a set of policy recommendations for future action. Specific outputs will include: (i) An overview study on the institutional implications for Vietnam of WTO accession; (ii) A case (region or sector) study of the economic and social impact of WTO membership; and (iii) An economy wide analysis of the economic and social impact of WTO membership. | CIEM |  |
| European Commission | Multilateral Trade Policy Assistance Program (MUTRAP) | 3,250,000 Euro | 01/2001- 3/2004 |  | Capacity building, technical assistance and advisory | Supporting Vietnamese officials in policy-making departments of all relevants ministries involved in multilateral trade policy issues | Training on WTO issues, Research on the impact of service liberalization; Fostering knowledge of the Doha Development Agenda; Establishment of the Technical Barrier to Trade (TBT) and Sanitary/ Phyto sanitary (SPS) enquiry points; Training of judges on trade and related issues; Trade Law Chairs in Universities; and negotiation techniques; | Multilateral Trade Policy Department, Ministry of Trade | Relating ministries |
| European Commission | MUTRAP Bridging | 191,076 Euro | 8-11/2004 |  |  | Short term TA to assist the beneficiaries in strengthening the capacity of the government of Vietnam and Vietnamese stakeholders for managing WTO accession and meet their commitments and challenges from other international and regional trade related agreements | Several short term EU experts missions on SPS Action plan, SPS and TBT enquiring points and services. | Multilateral Trade Policy Department, Ministry of Trade | Relating ministries |
| European Commission | Trade needs assessment | 195,956 Euro | 2005 |  |  | Trade Needs Assessment exercise. Understanding of TRA priorities for next Country Strategy Paper. |  |  |  |
| European Commission | Asia TRTA trust Fund to Asian developing countries (19) and Asian regional organizations (ATF) | 4,500,000 Euro EC 500,000 Euro ITC | 1/7/2004-31/12/2009 |  |  | Short term TRTA and capacity building to Asian developing countries and Asian regional organisations | WTO rules & agreements issues, private international trade law, contract negotiation and commercial arbitration, regional trade integration. Trade information, packaging and trade finance | ITC ATF sub-site will be part of ITC sites Http://www.intracen.org |  |
| European Commission | Multilateral Trade Policy Assistance Program II (MUTRAP II) | 5,350,000 Euro | 2004-2007 |  |  | The project purpose is to strengthen the capacity of the government of Vietnam and Vietnamese stakeholders for managing WTO accession and meet their commitments and challenges from other regional and international trade related agreements. | - Sector specific: legal, policy, capacity building, training (Agriculture, Services (general and sectoral), SPS (Animal, plants, health, fisheries/TBT, enquiring points) - Horizontal issues (legal, capacity building network & curricular development, information & awareness raising, trade and environment, gender, social issues | Multilateral Trade Policy Department, Ministry of Trade | Relating ministries |
| European Commission | European Technical Assistance Programme | 11,034,800 Euro | 2003-2008 |  |  | Supporting Vietnam transition to market economy and international integration/ preparation for WTO accession and eventual implementation. It includes the drafting of taxation/custom/ accounting legislation and procedures in line with international standards, norms and recommendations, development and implementation of trade facilitation mechanisms and information systems to minimise the burden of customs procedures on trade. Harmonization of both the conformity assessment procedures and the quality assessment infrastructures with international standards. |  |  | MPI, MoF, MoSTE (Directorate for Standards & Quality) |
| European Commission | EU-ASEAN Intellectual Property Rights Co-operation Programme (ECAP II) | 1,500,000 Euro for Vietnam component (7,500,000 Euro for the whole programme) | 1999-2006 |  |  | Enhancing EU/ASEAN investment and trade to achieve further economic cooperation by upgrading the ASEAN intellectual property rights systems, in line with the highest international standards and practices. | Seminars, training, research | and Technology (National Office of Intellectual Property Right) | MoSTE (National Office of Intellectual Property Right) and MOCI (Copy right office) |
| European ### Commission | EU-ASEAN Regional Co-operation on Standards, Quality and Conformity Assessment (ISQAPII | Budget for Vietnam: n/a ( 9,000,000 Euro for the whole programme) | 1993-2005 |  |  | Enhance commercial exchanges between EU and ASEAN through standardisation, conformity assessment procedures and quality structure and practices. |  | ASEAN Secretariat |  |
| ### European Commission | ASEAN Programme for Regional Intergration Support (APRIS) | Budget for Vietnam: n/a ( 4,000,000 Euro for the whole programme) | 2003-2006 |  |  | To strengthen EU-ASEAN relations as a whole and complement the on-going EC-ASEAN dialogue process. |  | ASEAN Secretariat |  |
| ### Finland/ Ministry for Foreign Affairs of Finland | Project on assistance on Capacity building for the Ministry of Trade | 2,374,347 Euros | 12.2000-12.2004 |  | Human Resources Development | Assisting the Ministry of Trade to raise the capacity of its officials in formulating and managing policies. | Providing training programs and training consulting on formulating and implementing trade strategies and policies. Supporting to upgrade the information system of the Ministry of Trade. | MOT | MOT's staff, its subordinates, and provincial trade services. |
| France / Ministry of Foreign Affairs | Technical assistance to the NCIEC and line ministries for economic integration and WTO accession | 1,600,000 EUR | 1/2002-11/2005 | Laws | Regulatory Capacity building | Training and assisting reviewing of legal system Capacity Building and Support to media | Training, Study tour | NCIEC | NCIEC |
| Germany/ Ministry for Economic Coop. and Dev., Germany | Vietnam’s Accession to WTO: Preparation for Competing in a New Environment. |  | 10/2003 |  | Seminar on subsidy agreements, anti-dumping regulations, impacts on business, and trade disputes. |  | Seminar | NCIEC |  |
| Germany/ Ministry for Econ.Cooperation. and Dev, Germany (Implementatioen: GTZ) | Macro-Economic reform Programme | 3,0 Mio. EUR (first phase) | Start: 2005 |  | Economic advice | Economic advice to Government through support to CIEM. and other government agencies (state bank, state audit, MOF) | Advisory | CIEM | CIEM, SBV, State Audit, MOF |
| IMF | Legal Aspect of International Financial Institution |  | Annual Seminar |  | Covers legal, institutional and operational aspects of IFIs and WTO | Human capacity building for senior lawyers responsible for legal aspects of IFI and WTO membership. | Seminar | IMF-JVI Institute | SBV, MOF, and MOT |
| IMF | Balance of Payments statistics mission |  | 9/2003 |  | Statistics of trade, investment income, transfers, and FDI | Enhance the accuracy of the BOP statistics towards international practices. | TA report | IMF | SBV, GSO, MOT, and MPI |
| IMF | Seminar of the manual of the International trade statistics in services |  | One-day seminar on October 15, 2004 |  | Covers the key concepts of on international trade statistics in services | Enhance human capacity building to develop statistics concepts on trade in services | Basic training course |  | GSO, SBV, MPI, MOLISA, MOT, Ministry of training and education, and Tourism Department |
| IMF | Article VIII Review |  | 2/2005 |  | Removal of all exchange restrictions under Article VIII of the IMFs Articles of Agreement | To verify that Vietnam still applies some foreign exchange restrictions such as the evidence of tax obligation fulfillment before transferring foreign exchange abroad, absolute restrictions on a few current transfers, and absolute restrictions on re-exchanges; in order that Vietnam has a fair and open international trade and investment environment. | TA report | IMF | SBV, MOF, MOT, and MPI |
| IMF | Balance of Payments |  | Annual Seminars |  | Covers main concepts of the BOP and how to compile the BOP | Enhance human capacity building in compiling the IMF standards BOP | Seminars | IMF Institute, IMF-Vienna Joint-Institute, IMF-Singapore training Institute | SBV, GSO and MOT |
| IMF | Technical Assistant for drafting the foreign exchange ordinance |  | 6/2005 |  | Covers both legal and economic requirements of a standard foreign exchange ordinance | To have the first time foreign exchange ordinance which can cover the best practices and meet the WTO requirements | Advisory | IMF | SBV, MOF and other related government agencies |
| IMF | Two-week technical assistant for BOP compilation |  | Jan 2006 |  | Improve data collection framework and assist in reclassifying capital account items | To enhance the accuracy of BOP data according to international practices, in the context of Vietnam’s accession to the WTO. | TA report | IMF | SBV, GSO, MOT, and MPI |
| #### Italy | Providing technical assistance for institutional enhancement to facilitate the Socialist republic of Vietnam’s accession to the WTO | EUR 786,202 | 01/2003- 07/2003 (estimated) |  |  | Enhancing the skills and knowledge of Vietnamese policy and regulations makers in addition of researching and organizing current knowledge body in order to develop a long-term subsidy and countervailing measures policy and WTO-compatible detailed regulations which support domestic production while establishing fair competition for domestic producer | Basic training course Initial Follow-up and Evaluation Workshop; Tailor-made training course composed of four phases WTO trade policy course participation through scholarship; Intermediate follow-up and evaluation workshop; Final Seminar presentation of training component results. |  |  |
| Japan/ JICA | TA Project on WTO issues | --- | /2001 /2003 | GATS, Safeguard, IPR, Competition | Human resources development | To support capacity building related to the implementation of the WTO Agreements | Seminar by Japanese experts | Multilateral Trade Policy Department - MOT | NCIEC member agencies |
| Japan/ JICA | APEC Regional Training for WTO related |  | /2002 /2004 | TBT, AD, Safeguard, SPS | Human resources development | To train government officials to improve the basic knowledge of the individual WTO agreement | Training in Japan | MPI | Govt. officials |
| Japan/ JICA | (*5) Modernisation of IPA project | n/a | 04/2000 03/2004 | TRIPS | Institutional capacity building | To training maintenance staff of computer system, management staff of industrial property administration, application formality examination, substantial examination registration, publication licensing and legistration staff will be developed | Dispatch of Japanese experts training of Vietnamese officials, Vietnamese officials, providing equipment | NOIP | NOIP/MOST |
| Japan/ JICA | Capacity Building of Master Trainers for Modernization of Customs Administration |  | 08/2004~ 06/2007 | WTO Valuation Agreement, etc. | Human Resource Development | Master trainers are raised to provide practical training on Customs Valuation, Post Clearance Audit and HS Classification (including Chemical Analysis) based on the international standards, and act as instructors in the staff training courses. | Dispatch of Japanese experts, Send Vietnamese officials to Japan, Providing equipment of chemical analysis | MOF, General Department of Customs | General Department of Customs, Regional Customs Departments |
| Japan / JICA | Utilization of Intellectual Property Information | 530 million yen | 1/2005~3/2009 | TRIPS | Institutional capacity building | Through the utilization of the IP information system, efficient application processing, management and information service of the IP are available in NOIP | Dispatch of Japanese experts, training of Vietnamese officials, Send Vietnamese officials to Japan, providing equipment | NOIP | NOIP/MOST |
| ### Japan / JICA | Capacity Building on competition policy and enforcement of competition law |  | 2005~2006 |  | Capacity building | Enhance the capacity of Ministry of Trade in the implementation of Competition Law | Dispatch of Japanese experts, training of Vietnamese officials, Send Vietnamese officials to Japan | MOT | MOT |
| ### Japan /JICA | Tax administration Reform |  | 2005~2008 |  | Institutional capacity building | General Department of Tax capability for staff training and instructing the work of provincial and municipal tax bureaus is strengthened | Dispatch of Japanese experts, training of Vietnamese officials, Send Vietnamese officials to Japan, providing equipment | GDT | GDT/MOF |
| ### Japan / JICA | Training course” Intellectual property for APEC Economies” |  | 2005 | TRIPS | Human resoures development | To train govenrment officials to enhance the knowledge of IP | Training in Japan | MPI | Govt. officials |
| Japan / JICA | Stock exchange Seminar for Asian Countries |  | 2005 |  | Hunan resources development | To train government officials to improve the basic knowledge of the stock exchange | Training in Japan | MPI | Govt. officials |
| ### Japan /JICA | Training course “Operation of Understanding on Rules and procedures governing the DSU, WTO Agreement” |  | 2005 |  | Human resources development | To train government officials to improve the understanding on rules and procedures governing the DSU, WTO agreement | Training in Japan | MPI | Govt. officials |
| ### Japan / JICA | Training course “Seminar on Sovereign Debt Management” |  | 2005 |  | Human resources development | To train government officials to improve the knowledge of the sovereign debt management | Training in Japan | MPI | Govt. officials |
| ### Japan/ JICA | Training course” Foreign Trade Development” |  | 2005 |  | Human resource development | Provide information on measures and policies of public sectors(trade supporting institutions), on actual actives for trade promotion and development Japanese firms | Training in Japan | VCCI | Public official |
| ### Japan / JICA | Training course “Management on Trade and Investment Insurance” |  | 2005 |  | Human resource development | Enhance the knowledge and skills of management and administration of the trade and investment insurance system to promote and support trade and investment | Training in Japan | MOT | Govt. officials |
| ### Japan/ JICA | Training course “ Trade Investment Promotion Seminar” |  | 2005 |  | Human resources development | To improve knowledge on trade investment promotion | Training in Japan | VCCI | Govt. officials |
| ### Japan/ JICA | Study on Capacity Building for Enforcement of Competition Law and Implementation of Competition Policy |  | 2005~2006 |  | Capacity Building | To support the Competition Administration Department (CAD), Ministry of Trade to enhance the capability of CAD for enforcing competition law and implementing competition policy | Dispatch of JICA Study team (Japanese consultants), training of Vietnamese officials, Send Vietnamese officials to Japan for training | CAD, MOT | CAD,MOT |
| ### Korea Rep | Knowledge Partnership: Sharing Korean Economic Development and Crisis Management Experiences with Developing Countries | About 200.000 USD (Under preparation) | 2003-2004 |  | General WTO issues, economic adjustments | Sharing Korean experience of economic development: economic development planning, financial crises and the implemented adjustment and restructuring programs ... Assisting policy makers of developing countries gain both theoretical and practical knowledge to achieve their economic development goals and overcome the on-going financial crisis; | Selected consultants will be dispatched to Vietnam and disseminate knowledge and experiences related to a variety of issues regarding economic development processes. | MOT | MOT and other relevant Ministries |
| New Zealand | English language training for trade policy specialists Scholarships for Masters level study at Hanoi National Economic University on trade liberalization topics | 185,000 NZD | Ongoing Ongoing |  |  |  |  |  |  |
| Norway/ NORAD | Market Access and Trade Facilitation Support for Mekong Delta Countries, through Strengthening Institutional and National Capacities Related to Standards, metrology, Testing and Quality (SMTQ) | USD 908,520 | 1/2003 – 6/2005 | TBT | Integration into the global trade environment through alleviation of technical barriers to trade for Vietnam, Cambodia and Lao PDR | Facilitate industrial development and export capabilities (and consequently spurring economic growth and employment opportunities) of the assisted countries by reducing technical barriers to trade through the strengthening of standards, metrology, testing and quality institutional structures and national capacities. | - National capacity creation related to market access requirements and technical barriers to trade (TBT) and identifying manufacturing sub-sectors and export market focus for remedial action in each beneficiary country - Upgrade the required technical infrastructure for (a) standards development and harmonization, (b) metrology and testing laboratories required by the selected sectors; (c) standards for labeling and accreditation and/or certification of laboratories and quality systems | UNIDO | Apex institutions in each country dealing with Standards, Accreditation, Metrology and Testing Manufacturing facilities exporters |
| Oxfam GB | Analysis of impact of WTO accession on poor maize farmers in four provinces |  | 2004-2005 | Agriculture | Poverty and Social Impact on poor farmers | Analysis of impacts of accession on poor maize farmers in rural areas as input to MARD members of WTO negotiating team | Research in Nghe An, Lao Cai, Son La and Dak Lak | MARD/OGB |  |
| Oxfam GB | Analyses of impact of WTO accession on poor farmers practicing animal husbandary |  | 2005-06 | Agriculture | Poverty and Social Impact on poor farmers | Analysis of impacts of accession on poor maize farmers in rural areas | Research in rural provinces (details to be confirmed) | MARD/OGB |  |
| Singapore/ Singapore Trade | International Trade Institute of Singapore |  |  |  | Trade facilitation, TA | To provide premier training, research and consulting institution in customized training programmes, courses, seminars, conferences in international business and trade to help companies maintain their competitive edge (ASEAN Initiative for CLMV) | Training, research, consulting, seminar |  | Companies, officials from relevant agencies |
| Sida (Sweden) | Technical assistance on rules of origin (ROO) | About 200.000 EUR | 9/2003- 6/2004 | ROO | Capacity Building | Reviewing legal framework on ROO, case studies and study tour in Sweden | Seminar, training | NCIEC | NCIEC members |
| Sida (Sweden) | Strengthening of research capacity for Vietnam Institute of Trade | 100,000 USD | Ongoing - 2005 |  | Capacity Building |  | Training, research | VIT |  |
| Sida (Sweden) and seco (Switzerland) co-financing (see Switzeland seco below) | Support to Trade Promotion and Export Development in Vietnam | 3,165,000 USD | 6/2004 5/2007 |  | Trade promotion and Export development | To assist Vietnam in achieving the export growth rates set for the decade. To assist the government of Vietnam, Vietrade, trade supporting institutions and exporting enterprises to take advantage of the new export opportunities offered by trade liberalization and global economic integration. | Update National Export Development Strategy; Set up Operational Trade Support Network; Strengthen Training & Counselling Capacity of TPO/TSIs; and Develop Effective Trade Information Capacities | ITC, VIETRADE | VIETRADE, Trade supporting institutions and exporting enterprises |
| Switzerland/ Seco | Swiss Import promotion Program ( SIPPO) | 1,500,000 USD | 04/1999 - open |  | Export promotion capacity building | To assist SMEs in Vietnam in their efforts to gain access to the Swiss and European markets | Technical assistance; training information; contacts | SIPPO | SMEs |
| Switzerland/ seco | Vietnam WTO Accession – negotiation support | 320’000 USD | 10 / 2004 12 / 2005 |  | Negotiation analysis and advise | - To increase negotiating expertise among the Vietnamese negotiators - To assist in solving negotiating issues – To foster a favourable negotiating climate in Geneva through the services of a “honest broker” | - Negotiation Analysis and advise – specific TA | IDEAS Center Geneva | MOT |
| Switzerland | (5*) Special Program of Co-operation in the Field of Intellectual Property | 1,800,000 USD | 01/2002 - 12 / 2005 | TRIPS |  | To assist Vietnam to fulfill the obligations set forth in International treaties on I.P. incl. TRIPS Agreement under WTO | TA in enforcement of Intellectual Property Rights | Swiss Federal Institute of Intellectual Property, NOIP, Swiss Consulting Co.Ltd | NOIP |
| Switzerland (seco) and Sida co-financing (See above) | Support to Trade Promotion and Export Development | 3,165,000 USD | 6/2004 5/2007 |  | Trade promotion and Export development | To assist Vietnam in achieving the export growth rates set for the decade. To assist the government of Vietnam, Vietrade, trade supporting institutions and exporting enterprises to take advantage of the new export opportunities offered by trade liberalization and global economic integration.. | Update National Export Development Strategy; Set up Operational Trade Support Network; Strengthen Training & Counselling Capacity of TPO/TSIs; and Develop Effective Trade Information Capacities | ITC, VIETRADE | VIETRADE, Trade supporting institutions and exporting enterprises |
| Switzerland (seco) (UNIDO executed) | Market Access Support for Vietnam, through the Strengthening of Capacities Related to Metrology, testing and Conformity | USD 985,000 | 2/2003- | TBT and SPS | Integration into the global trade environment through alleviation of technical barriers to trade for Vietnam | Facilitate industrial development and export capabilities (and consequently spurring economic growth and employment opportunities) of the assisted countries by reducing technical barriers to trade through the strengthening of standards, metrology, testing and quality institutional structures and national capacities. | Upgrade the required technical infrastructure for metrology, textile/apparel, microbiology and chemical testing and calibration needs in industry, system certification capacity and strengthen SMTQ institutional service capability | UNIDO | STAMEQ, Manufacturing facilities and exporters |
| UK/ DFID and hopefully a number of other interested donors | Beyond WTO: Strengthening Vietnam’s capacity to sustain pro-poor growth and poverty reduction | 7-10 million USD | Being developed, proposed to start late 2005 and end 2010 | Various | Legal development, economic capacity strengthening and negative impact mitigation | To give the government a flexible financial facillity to take on various reform measures to address institutional and social and poverty issues arising from WTO membership | Three big components: legal development, economic capacity strengthening and dealing with social and poverty impacts | Office of the Government | Various government agencies |
| UK / DFID | Support to analytical and outreach activities to prepare for WTO accession | 300,000 USD | 1/2004-12/2004 |  | Sectoral tariff reduction options in industry and agriculture, WTO accession awareness raising | To support the preparation of WTO accession roadmap. | Research into the various tariff reduction options in industry and agriculture sectors, training and outreach activities for high level officials on the challenges and implication of WTO accession. | World Bank Institute and Vietnam Academy of Social Sciences | MoI and MARD |
| UK/ DFID | Training in subsidy and countervailing measures, and negotiation skills | 40,000 USD | First quarter 2004 |  |  | To support the formulation of subsidy and countervailing measures and WTO accession negotiation | Training in subsidies and countervailing duties, and negotiation skills for officials dealing with WTO negotiation | NCIEC |  |
| UNDP | Managing Vietnam’s Integration into Global Economy (Phase I: Integration Study) | 230,000 USD | 10/2001 9/2003 End: 06/2002 |  | Research and stock takings | Stocktaking of Vietnam integration process and signed trade and trade-related agreements including the US BTA, AFTA, APEC,World Bank’s PRSC, IMF’s PRGF, WTO accession. Road mapping the integration strategy. Capacity gap assessment on implementing international trade-related commitments. Study on the inter-ministerial coordination mechanism for WTO accession and experience of acceding countries. | Integration Study | NCIEC | NCIEC member agencies |
| UNDP | Integration Study Extension: Commercial Law Revision | 55,000 USD | 2003 |  | Legal reform and Capacity Building | Revision of the Commercial Law to support a level play field for commercial activities and for WTO compliance | In-depth research to examine the status of the Commercial Law in relation to other domestic legislation and its consistency with the WTO treaty and BTA obligations. Clear set of recommendations relating to the proposed changes of the Commercial Code. | NCIEC | MOT |
| UNDP | Competition Law | 200,000 USD | 2001-2003 | Competition policy | Legal reform and Capacity Building | Support drafting and finalisation of the first Competition Law | Technical support provided by UNDP/UNCTAD and international competition experts to review the successive drafts of the laws. Organise several advocacy events to raise awareness on the competition law and policy. Conduct a study on state monopoly applied to 5 sectors. | MOT | MOT Legal Department and Drafting Committee |
| UNDP | Capacity Strengthening to Manage and Promote Trade in Services in Vietnam in the Context of Integration (or “Trade in Services Project”) | 2,550,000 USD | 2003-2005 | Service sector development | Promoting the Regional and Global Integration Process | - To provide technical support to formulate a comprehensive and integrated development strategy for the services sector in the context of Vietnam’s international economic integration to ensure a long-term inter-agency and cross-sector coordination on policy formulation and implementation of integration commitments; - To provide substantive inputs to assist in the on-going negotiations for WTO/GATS accession; - To enhance human and institutional capacities in the area of trade in services; and - To increase public awareness of required reforms in the services sector. | - Formulation of a comprehensive strategy for the development of the services sector; - Improvement of information flows on services and of the current trade in services statistics system; - Assessments of the competitiveness and impacts of trade liberalization of selected services sectors; - Conduction of specialized and targeted training programs and study tours in Vietnam and overseas. | Ministry of Planning & Investment (MPI) | MPI and other related agencies |
| UNDP | Training and research capacity building for Vietnam on trade and development policy making and negotiations | 300,000 USD | 2003 | GATT, GATS, Agriculture, S&D, Trade remedies | Curriculum development and research capacity building | To enhance the capacity of Vietnamese trainers to adapt the "generic" UNCTAD/Commercial Diplomacy training tools on WTO issues to the local data, legislation, economic structure, development needs | Conduct a series of workshop on selected issues in the international economic agenda, WTO accession, training of trainers on trade policy. Research done by national university lecturers and researchers on WTO related issues in agriculture, trade in services, market access, and trade remedies for the post-curriculum development. | UNCTAD | Universities |
| UNDP | Asia Trade Initiative | 1,500,000 US D | mid-2002 2004 |  |  | To facilitate the cross fertilization of experiences and lessons learnt on trade, investment and economic governance. To strengthen the ability of countries in the region. To facilitate the coming together of governments (developed and developing) and non-governmental groups to learn from each other and strengthen their collective perspectives in trade fora and institutions. To advocate for human development policies. |  | Participating national governments, UNCTAD, Regional CSOs, UNDP COs and SURFs | Participating national gov, UNCTAD, Regional CSOs, UNDP COs and SURFs |
| USA | Support for Trade Acceleration Program (STAR) | 14,200,000 USD | 09/2001 12/2006 | Trade in goods and services (GATT, TBT and GATS), customs valuation (CVA), transparency, investment relations (TRIMS+), protection of IPR (TRIPS), right to appeal government decisions and commercial dispute settlement and arbitration, which includes substantial support for development of the court system. | STAR is demand driven, responding on an ongoing basis to requests by assigned counterparts. The focus for the remainder of 2005 and through 2006 is supporting the legal reforms and institutional capacities to fulfill fullyf the requirements for U.S.-Vietnam Bilateral Trade Agreement (BTA) implementation and accession to the WTO. | To support the Government of Vietnam’s efforts to implement reforms required for the successful implementation of the US-Vietnam Bilateral Trade Agreement and to support Vietnam’s efforts to accede to the World Trade Organization (WTO). | TA on legal and economic issues, including: support for policy and training workshops and seminars; legal analysis comments on on-going drafts of over 60 laws and regulations, of which around 25 have been approved; support for implementing effectively new laws and regulations; provision of reference materials and guidebooks; limited study tours; support of legal and economic research. Also serves as a gate way for peer to peer collaborations from U.S regulatory/ legal agencies such as the U.S. Federal Trade Commission, U.S. Securities Exchange Commission and so on | The GVN’s Steering Committee for a Program to Implement the BTA, chaired by the Office of the Government and including 9 other state agencies, and USAID. | Assigned to work with 46 state agencies, including many ministries, NA, the Supreme People’s Court, the party and 10 People’s Committees |
| USA | Trade and Law Exchange and Partnership Program | 1,192,000 USD | 9/2002 9/2005 | Trade in goods and services, customs valuation, transparency, right to appeal, investment relations, protection of IPRs, dispute settlement and arbitration. | Institutional capacity building; demand-driven technical assistance program | To assist the GVN in implementation of the BTA with additional focus on WTO disciplines and international best practices that are important for overall international economic integration, including WTO accession. | Design and facilitate study tours abroad for Government officials involved in BTA implementation. | Educational Forum of US-VN Trade Council (USVTC) with Various ministries (MOT, MOJ, etc.) | Key ministries such as MoTrade, Justice, Finance, SBV, OOG etc. |
| ### USA/ USAID | Vietnam Competitiveness Initiative | UD$ 5,642,068 | 10/ 2003- 10/ 2006 |  | Regulatory environment of business, capacity building for SMEs, access to credit for private sector businesses | Provide technical assistance to complements the GVN’s efforts to foster a strong, viable indigenous private sector that can harness the benefits of integration into the world economy. | This initiative focuses on: (1) improving the enabling environment for the private sector by promoting SME-supportive policies and regulations; (2) increasing capacity of the private sector using cluster-based approach to improve management skills, increased access to technology and other services for SMEs, and strengthened business associations; and (3) improving access to credit.. | Agency of SME Development (ASMEAD) of the Ministry of Planning and Investment | MPI, VCCI, CIEM and other agencies involved in business mgment; Business associations and ent. |
| ### World Bank/ WB (EASPR and trust funds from DFID and AuSaid) | Vietnam’s exports: Challenges and Opportunities; Assessment of policy recommendations for improving Vietnam’s competitiveness. | US$ 300,000 | Complete, 2003 | GATT | Export Growth Strategy; Regulatory Environment and Export Support System; Exports of such sectors as Agriculture and Seafood, Tourism, Footwear, Electronics and IT, Textiles and Clothing, and Infrastructure | Assess Vietnam’s policy reforms with respect to exports and to assess future prospects for achieving the exports targets that have been set in the Gov’s Socio-economic Development Strategy (2001-2010) in the context of the WTO accession. | (i) Lessons from East Asia’s Export Experience: Interpretation and Implications for Vietnam; (ii) Export Growth Strategy and Trade Integration; (iii) Export Incentive Structure and Foreign Direct Investment; (iv) Regulatory Environment and Export Support System; (v) Export Competitiveness and Trade and Macroeconomic Policy Link; (vi) Sub-sector studies ( Agriculture and Seafood; Tourism, Footwear, Electronics and IT, Textiles and Clothing, and Infrastructure). | WB (EASPR) | Gov’s officials from various related line- ministries, research institutions. |
| ### Would Bank/ WB (EASPR and WBI) | Diagnosis of Vietnam’s WTO readiness and awareness building among key Government stakeholders. | US$ 700,000 | Completed by 2003 - | GATT, GATS, TRIMs, TRIPs, AOA, SPS, TBT, ATC, ACV, SMC, AOS etc. | Political economy of the WTO accession, studies on impacts, readiness and prospects of some selected sectors / industries in the context of the WTO accession. | Provide Institutional and capacity building support to the Vietnamese Authorities that are preparing roadmaps for policy reform that will pave the way to Vietnam’s accession to the WTO. | (i) Organize Vietnam – Readiness for WTO accession Forum in Hanoi and HCMC (Jun 3-7,03); (ii) Conduct surveys of 220 manufacturing firms and 80 firms in service sectors to assess their readiness and strategy in response to Vietnam’s accession to the WTO accession (inputs for Vietnam – Readiness for WTO accession Forum). (iii) Organize a series of workshops on policy implications of Vietnam’s WTO accession with various ministries. | Vietnam Academy of Social Sciences (VASS) in close collaboration with line- ministries, Economic and Budget Committee of the National Assembly (NA), and Office of the Government (OOG). | Gov’s negotiations team; Gov.’s officials from various related line-ministries, MPs of the NA, researchers. |
| ### Would Bank / WBI | GDLN dialogues on trade and poverty in Vietnam. |  | Completed, Jan. 2003 |  |  | Conduct GDLN dialogue on trade and poverty in Vietnam. | Four- day dialogues on trade and poverty. | WBI / VASS | Gov’s official and researchers. |
| ### Would Bank/ WB (EASPR, WBI | Support Vietnam’s accession to the WTO. | US$ 310,000 | Completed, 2004 | GATT, GATS, TRIMs, TRIPs, AOA, SPS, TBT, ATC, ACV, SMC, AOS, etc. | Awareness raising and capacity enhancement with regards to political economy of the WTO accession, and assessment of impacts, readiness and prospects of some selected sectors industries through training, research and outreach activities. | Provide support to the WTO accession process, including enhancement of the analytical capacity in assessing impacts of Vietnam’s WTO accession; raising awareness through outreach activities for understanding of the WTO-related issues which are important both to the negotiations and implementation phases. | (i) Organize series of training workshops for officials from various ministries, MPs of the National Assembly (NA), officials from the Office of NA and the Gov’s Office. (Mar, Jun. and Sept., 2004). (ii) Analyze implications of Vietnam’s WTO accession for selected manufacturing sectors; export subsidy in agriculture; service industries and service export; transport sector (2004) (iii) Compare Vietnam’s legal framework of intellectual property rights with WTO requirements (2004); (iv) Study implications of WTO accession for the legal reform agenda; and propose a legislative action plan in the context of WTO accession. (April 2004) (v) Translate, publish and disseminate 41 chapters out of 55 chapters of the book “Handbook: Trade, Development and the WTO” (2004). | VASS, OOG, NA, related line-ministries, research institutions. | Gov’s negotiations team; Gov.’s officials from various related line-ministries, MPs of the NA, researchers. |
| ### World Bank/ WB (PHRD) | Preparation for Vietnam Customs Modernization Project . | US$ 996,500 | 2004-2005 | GATT Customs Valuation Agreement (CVA). | Customs modernization / trade facilitation / WTO accession. | Conduct a comprehensive diagnostic study of Vietnam’s customs system in comparison against international good practice; identify policies and mechanisms to address the gaps; and support their implementation through current and future projects. |  | WB (EASPR) / Ministry of Finance (MOF) / General Department of Vietnam Customs (GDVC) | MOF / GDVC / related Gov’s agencies / Project Preparation Team. |
| ### World Bank/ WB (IDA) | Vietnam Customs Modernization Project (Specific Investment Loan that covers significant technical assistant component.) | US$ 70,000,000 (including TA component with financing requirement of more than $10 mn) | 2005-2010 | GATT Customs Valuation Agreement (CVA). | Customs modernization / trade facilitation / WTO accession. | The VCMP aims to strengthen the capacity of the Customs administration of Vietnam to ensure that it is able to make an efficient and effective contribution to the achievement of the Government objectives in respect to trade facilitation, revenue collection, production of foreign trade statistics, commodity protection, and national security. The project would be a key factor in facilitating Vietnam’s accession to the WTO and securing the gains from greater integration into the world trading system. | (i) Customs Systems and Procedures; (ii) Organizational Restructuring and Management; (iii) Information and Communication Technology; (iv) Project Management Support. | EASPR / MOF / GDVC | MOF / GDVC / related Gov’s agencies/ manufacturers / exporters / importers / freight forwarders / shippers / port operators. |
| ### World Bank | Revenue Impacts of WTO Accession: Vietnam’s Customs Modernization. | US$ 32,860 | Completed, June 2004 | GATT Customs Valuation Agreement (CVA). | Revenue implications of the switch to required administrative and procedural changes toward implementation of CVA . | Conduct a revenue impacts analysis of various commitments that WTO accession will entail, will have on revenue. |  | EASPR | Gov. officials and researchers; and the Gov’s task team of the Customs Modernization Project Preparation. |
| ### World Bank WB (WBI) | Trade in Services and International Agreement (Regional Training Course). | US$ 60,000 | May 2005 | GATS | Trade in services | Capacity enhancement with regards to the economics of services trade reforms, the rules of international agreements, and the institutional challenges of trade negotiations in services. |  | VASS to coordinate. | Gov/s official and researchers. |
| ### World Bank WB (ARD and EASRD | Vietnam SPS Action Plan. | US$ 250,000 | 2004 - | SPS | Sanitary and phyto-sanitary issues, agricultural health, capacity building | (i) Assist Vietnam to develop its Medium-term National Action Plan for Food Safety and Agricultural Health in support of the implementation of its SPS commitments. (ii) Provide advice to MARD on the TOR of the National SPS Notification and Enquiry Point |  | Ministry of Agriculture and Rural Development (MARD). | Direct beneficiaries include the Gov’s officials providing SPS services. Ultimate ones include farmers, processors, traders, and customers. |
| ### World Bank | Preparation and publication of Q & A handbook on Industrial Property Rights for Vietnamese Businesses | US$ 48,000 | May-December 2005 | TRIPs | Compliance and enforcement in respect of the intellectual property rights legislation. | (i) Provide and support the businesses with adequate knowledge and skills on intellectual property rights, as well as the ways to proceed properly and quickly in compliance and enforcement with required procedures; (ii) encourage the businesses to actively participate in intellectual property activities worldwide, and contribute to the implementation of the Agreement on Trade-Related Aspects of Intellectual Property Rights (TRIPS Agreement) of the WTO. |  | VASS / VIPO | Vietnamese businesses, including SMEs. |
| ### World Bank WB (PPIAF trust fund) | Multi-modal transport regulatory review. | US$ 450,000 | May 2005 – Jan 2006 |  | Logistics, international and national trade. | The objective of the Consultancy is to present the Government of Vietnam with detailed regulatory options for encouraging a transport and logistics industry best able to meet Vietnam’s trade and economic growth objectives. This would enhance Vietnam’s regional trade within the context of AFTA and GMS; as well as its global trade once it accedes to WTO in 2005 as planned. | - Road freight haulage; Inland waterway freight - Railways; Coastal shipping; International shipping; Ports (int.and domestic); Air freight - Freight forwarding; Logistics centres (ICD’s) - Cross-border movements; Customs; Trade and transport insurance. | WB but MoT steering committee | Transport users, exporters/importers, transport service providers |
| ### World Bank | Implementation of the WTO obligations in the legal system. | US$ 200,000 | July 2005 – July 2006 | Implementation of GATT, GATS, TRIMs, TRIPs, AOA, SPS, TBT, ATC, ACV, SMC, AOS, etc. | Implementation of WTO obligations. | Provide a TA for Vietnam to prepare domestic legal conditions to implement WTO obligations and commitments in respects of the domestic legal system. | - (i) Drafting, adapting and implementing some WTO-related laws and regulations, including a check list of important issues may be developed to guide or use in drafting laws and regulations; - (ii) Reforming the legislative process; - (iii) Institutional capacity building to identify and train a group of international trade lawyers in the MOJ and ONA; and - (iv) Disseminations and information rules and obligations of WTO; | EASPR / VASS / MOJ / ONA | Gov.’s officials, MPs of NA, and the public at large |
| ### World Bank | Poverty impacts of Vietnam’s WTO accession. |  | Preparation |  | Possible impacts of the WTO accession on the poor, other distributional effects, and policy responses. | Provide support to enhance analytical capacity in assessing social impacts of the WTO accession. |  | ERSPR / VASS | Government officials and researchers. |

HEALTH PARTNERSHIP GROUP REPORT

Dec 2005

- Introduction

The first Aid Coordination Meeting for the Health Sector was held in March 1997 as per decision by the Prime Minister. It was followed by several years of International Support Group Meetings, ISG until 2002. The Health Partnership Group (HPG) was re-established in January 2005 to strengthen collaboration and coordination between the Ministry of Health (MOH) and the international community. Prior to this, the international community had met regularly for a number of years as the Health Sector Working Group (HSWG). In April 2004, MoH invited all interested donors to a Meeting of Interested Partners in Health (MIPH). Subsequently, MOH proposed regular meetings between MOH and the HPG with representatives of the international community.

The HPG is chaired by the MOH since April 2005, inviting bilateral and multilateral donors and other international organizations working in the health sector every 6 weeks. WHO serves as the present co-chair and secretariat.

During 2005, the HPG has met on a regular basis in order to:

- Identify ways to improve the management and effectiveness of ODA in the health sector, both in terms of financial and technical assistance;

- Exchange ideas on how to best support the development and implementation of health policies, programs and the Socio-Economic Development Plan;

- Enhance priority setting in the health sector;

- Share information on on-going and future projects and programs;

- Plan and conduct special HPG meetings to focus on particular themes.

In parallel with the HPG, there are smaller working groups that meet regularly to coordinate activities and discuss technical issues in specific areas of the health sector. The working groups include Health Management Information Systems, Health Financing, HIV/AIDS, Reproductive Health, Safe Motherhood and Newborn Health, Adolescent Health and Tobacco.

- HPG Progress over last 12 months

In 2005, the HPG focused on two main tasks: the work of preparation of health sector plans and strategies and progress towards introduction of Sector Programme Support (or SWAP). In addition, the HPG discussed a number of key current issues e.g. HIV/AIDS, health insurance, and the Health Care Fund for the Poor (HCFP).

The HPG gave a presentation to the National Assembly’s Social Affairs Committee on Drug Pricing and Traditional Medicine in advance of the adoption of the Drug Law.

### Health Strategies and Plans

- In April 2005 the MOH presented the Politburo Resolution on “People’s Health Care, Protection and Promotion in the New Situation,” to the HPG. The international community praised the resolution as a clear equity driven approach to improving the health of the population. The resolution sets out the strategic direction for all key aspects of the health system (health financing, health service provision, human resources, pharmaceuticals, etc).

- The MOH prepared a draft Action Plan to implement the Politburo Resolution on Health, covering the current key issues in 9 key sub-sectors. The MOH emphasized that a strong objective of the draft Action Plan is to decentralize activities to local government and to clarify the role of the MOH and other central agencies.

- In line with the draft Action Plan, the MOH prepared the overall Master Plan/ Health Investment Plan for the development of the Health Sector to 2010 with a vision to 2020 and the associated sub-sector master plans. The MOH requested comments and input from the international community to finalize the plan, which was submitted to Government for approval in September 2005.

- The donor community proposed that the 5-year Social Economic Development Plan (SEDP) represented a unique opportunity to collaborate and that the MOH should take a lead role to guide the international community on the development of the health sector up to 2010.

- MOH expressed the need to work on long term policy options for renewing and improving the health system. A proposal was developed and shared with the HPG and several donors agreed to provide financial and technical support to develop the long-term policy options. Key areas for consideration are 1) health financing; 2) health service provision; 3) human resources; and 4) governance and stewardship. The project is currently underway and the outcome of this project will serve as an important input to the 10th Party Congress to be held in 2006.

Sector Program Support (SPS) or (SWAP)

- The HPG agreed that a programme approach, rather than implementation of isolated projects, was needed to ensure the best possible use of donor resources for the development of the health sector. MOH proposed to work towards a Sector Programme Support in order to establish a strategic and financial framework, within which donors could provide support to the health sector in Viet Nam. This would enable full coordination and full alignment to government policy thus ensuring strong government ownership and optimizing the use of donor resources.

- The HPG heard a presentation from the Ministry of Agriculture and Rural Development (MARD) on their experience with implementing SWAP.

- It was suggested that Sector Programme Support (SPS) could be applied on thematic areas such as maternal and child health, the Health Care Fund for the Poor, HIV/AIDS, or by geographical areas.

- The HPG agreed to support a second Sector Programme Support study as a follow up to the study in 2000. The TORs are under preparation and the study is going to take place during 2005/2006. MOH established an ad hoc technical group to work on the SPS Study. HIV/AIDS was suggested as a pilot area for in-depth analysis and development for a SPS/ SWAP.

#### HIV/AIDS

- The MOH presented the current situation in investment in Viet Nam for HIV/AIDS Prevention and Control. It was noted that despite the recent major increases in donor support, the level of investment was only $0.25 per person compared with the target of $4 per person. MOH highlighted the limited coverage of projects working with high-risk groups such as Injecting Drug Users and Commercial Sex Workers; and that still only 1.7% of those with HIV/AIDS has access to Anti-retroviral Therapy. As noted above, HIV/AIDS is therefore considered as a possible sector for a SWAP/SPS. HPG also learnt about the establishment of the Viet Nam Administration for AIDS Control (VAAC) in the MOH.

#### Heath Financing

- Health financing and health insurance, particularly related to the poor and near poor, have constituted one of the key concerns for both the national and international community. Donors highly appreciate Government Decision 139, which established the Health Care Fund for the Poor (HCFP). A number of donor programs provide significant additional resources to the HCFP to support the effective implementation of the Decision.

- Because of many changes in health financing mechanisms and greater decentralization, the MOH plans to amend / revise Decision 139.  The international community was consulted by MOH on the new features of the revised decision and the major changes proposed are as follows:

- To cover 100% of poor through health insurance;

- The benefit package will be the same as the benefit package for compulsory members;

- There will be government financial support for the premium for the near poor to encourage the near poor to join the health insurance scheme;

- The premium will be increased from VND 50,000 to VND 60,000.

- In 2005, the government also issued the revised health insurance decree, which is now Decree 63. MOH presented to HPG some fundamental changes that have been made in terms of coverage, benefit package and provider payment methods, in order to improve the effectiveness and performance of the health insurance system. The revised decree also allows greater flexibility for implementation of health insurance at the provincial level. Some other issues of concern to the international community, e.g. family coverage instead of individual coverage or inclusion of dependents under compulsory health insurance, are still to be addressed.

Avian Influenza

- It is important in this report to acknowledge the continuing collaborative work between MOH, other key government players, FAO, WHO and the international community in avian influenza control.  The main threats are those to human health and to poultry. The work by the MOH with assistance of external partners includes strengthening surveillance, research on transmission routes and risk factors, improved laboratory capacity, infection control and patient care and treatment, IEC, vaccine development and pandemic preparedness planning. Information on Avian Influenza have been shared widely not only within MOH but among other important actors such as National Assembly and other government agencies.

- Next steps

- Implementation of Sector Programme Support (SPS), SPS would be a major objective for 2006 and the years to come.

- It has been agreed that the HPG would continue to meet regularly to enable the MOH and international community to work together to assist the Government in moving key issues forward on the development agenda;

- Improvements in Health Financing for the Poor.

## EDUCATION PARTNERSHIP GROUP

## Progress since last twelve months

## Government plan and coherence

- Provincial education plan: Pilot roll-out of the EFA action plan took place in 10 provinces to develop and test a modern decentralized planning approach and tool adapted from those utilized during the National EFA Action Plan process, also for building capacity for provincial education managers. The field-tested provincial educational planning methodological package has been published and widely disseminated to all provinces. This activity was coordinated by UNESCO with effective support from Provincial Education Planning Project/Building Capacity for Education Planning (PREP/BCEP) funded by CIDA through the World Bank.

- EFA – Fast Track Initiative (FTI) World Bank, DFID, Norway and the Netherlands are among the most significant contributors for this initiative.  A main consequence of FTI for Vietnam may be that it will attract additional international support. For example for the Targeted Budget Support (TBS) for EFA also New Zealand and possibly the Dutch are now contributing to help countries reach Universal Primary Completion.

- Education for Children with Disabilities: In 2005, the National Steering Committee on education for Children with Disabilities – MOET has made a great achievement on the Institutionalization of Inclusive Education for Children with Disabilities in Vietnam. The brand-new Regulation for Inclusive Education and the Ten Years 2005-2015 Strategy on Education for Children with Disabilities were drafted, providing a legal corridor for children with disabilities to be mainstreamed in the regular school system. The Regulation is expected to be adopted in December 2005 for nationwide implementation and the Ten Years 2005-2015 Strategy to be submitted to the Government at the beginning of 2006. This Strategy will be used to request an official Government resource allocation for Education for Children with Disabilities in Vietnam. These are also important tools for leveraging funds from international communities and private sector for Education for Children with Disabilities, and for guiding the inter-coordination for the disability sector in Vietnam. MOET and stakeholders have, through those efforts, aimed to achieve the Vietnam Government target for EFA by 2015 with financial and technical assistance of CRS/USAID. A UNESCO Inclusive Education learning package is being adapted for use in support to this work.

- UNICEF supported the organization of a regional workshop on Sector Wide Approaches in Education. Donors and development partners also continued to work closely with MOET, MOH, MOF, MPI, and Government Office to promote the sector-wide approach (SWAp) to ODA in education and health sectors.  The European Commission, DANIDA, NETHERLANDS, NORAD and SIDA have been supporting this initiative.

- United Nations Girls’ Education Initiatives (UNGEI): The British Government launched a new global strategy for girls education in developing countries, as part of its commitment to MDG #3 (Gender).   This was in line with United Nations Girls’ Education Initiative (UNGEI).  On behalf of the Education Sector Group, a small task force consisting of UNICEF, UNESCO, EC and Norway prepared International Partners a working note on operationalizing UNGEI in Vietnam. The principle of UNGEI is to form flexible partnership mechanisms to provide a vehicle for addressing gender issues in education. In Vietnam it is proposed to embed UNGEI within ESG. Funding for activities come from different sources. Four concrete activities were proposed, including review and harmonization of different school standards (FSQL/Child Friendly Schools/National Standard Schools) from a gender perspective; mapping of gender in education initiatives, action research on girls education; and disaggregating of data in various EMIS systems.  MOET has officially adopted the EMIS system developed by SMOET, which disaggregates data by gender.

- Under the umbrella of the UN Girls’ Education Initiative, UNICEF and  UNESCO, have been supporting the MOET to carry out the study on transition of ethnic minority girls from primary to lower secondary education in order to investigate the barriers for ethnic minority girls in transitioning to lower secondary school and to recommend interventions that would facilitate their completion of primary education and subsequent participation in lower secondary school. The capacity building workshops on gender and research were organized. The pilot phase to test the research tools and the research methodologies was successfully completed.  The next phase will be the mass data collection from approximately 24 villages of three provinces of Lao Cai, Gia Lai and Tra Vinh.  The study is scheduled for completion by June 2006 and specific recommendations will be made for policy consideration by the Ministry of Education and Training.

-	MOET with detailed comments of UNICEF has successfully amended the Education Law. The Viet Nam 2005 Education Law was ratified by the National Assembly on 14 June 2005 and was, with UNICEF support, introduced to international organizations, NGOs and Diplomatic Missions on 14 November 2005. Currently, with UNICEF technical and financial support, related Education Sub-laws (Decrees, Decisions, Rules and Regulations, Circulars…) are being developed for approval in early 2006.

- In follow-up to the Revised National Education Law as adopted by the National Assembly in 2005, and with initial support from UNESCO, the MOET has begun strengthening the network of Continuing Education Centres (CECs) and Community Learning Centres (CLCs) across the country, in implementation of Government decision to build a learning society and the priority to expand non-formal education for out-of-school adults and youth as targeted in the National EFA Action Plan.

- MOH and GSO have launched the first ever survey on Viet Nam Youth with technical and financial support of UNICEF and WHO. This has provided evidenced-based recommendations for policy development and program/project formulation for Vietnamese young people.

- EFA Targeted Budget Support (TBS): This is a  joint donor programme to support  the primary sub-sector with the aim to achieve the FSQL standards, using the National Targeted Program for Education as a funding vehicle. The  EFA Targeted Budget Support (TBS)  is  co-financed by   Belgium, CIDA, DFID, EC and New Zealand.  The grant providing donors pool funding together with the WB into the government budget, and a MOU regulating this. Different donors and international agencies were consulted  in the negotiations process.

- Poverty Reduction Support Credit (PRSC):  PRSC4 was signed and the preparation of PRSC5 is in progress. International donors worked closely together with the World Bank to prepare the new triggers and activities for PRSC 5. A PRSC stocktaking exercise took place to review the progress made under the first 3 PRSCs and to look at the future planned PRSCs.

- ECCD Interagency network was working very actively this year. The core members of the ECD working group are UNICEF, SC/UK, SCUS,  Plan International and an ADB consultant team. SCUK will take on the role of the secretariat until  December  2006, the group planned to invite the Government ECD agencies to be core members of ECD working group which support the group work effectively. .  UNESCO has been supporting ECCE policy and action plan implementation of the MOET, particularly in developing effective ECCE approaches for children and parents in disadvantaged areas.

- Quality of education being a primary concern in Viet Nam, and with the publication of the Vietnamese version of the EFA Global Monitoring Report 2005 on ‘The Quality Imperative’, support was provided by UNESCO to the MOET in organizing a major Symposium on Quality of Education with international expert contributions from Dfid and the International Institute of Educational Planning.

## 2.	Sector co-ordination

- SEAMEO: The South East Asian Ministers of Education Organization established in 1965 with the objective to get a better overview of all related education activities in South East Asia. Currently, SEAMEO has 10 South East Asian member country  and 7 associate members (Australia, Canada, France, Germany, New Zealand, Norwegian and the Netherlands).  The Secretariat (SEAMES) head office is based in Bangkok. Vietnam hosted the 40th SEAMEO Conference (3 days) in July 2005 to review the educational cooperation activities in the region.  During the SEAMEO Conference, a Policy Forum on Education took place.

- PTDP review: the MOET/WB/DFID joint review of the Primary Teacher Development Project.  The project was implemented in 10 provinces, but the reforms introduced could have nationwide impact. After three years of implementation there is a serious under spending and the review will look at a time extension for the project. On the positive side, the Project has been very good in communicating its objectives to all stakeholders and has actively used the media in its communication strategy. The project is developing teacher standards  and professional development opportunities to reach the profiles and is also working on quality insurance and conditions and terms of service for teachers.

- Global Campaign for Education - EFA Action Week this year was celebrated worldwide from 24 to 30 April 2005.  The theme for 2005 is "Education to end poverty".  In Viet Nam, UNESCO, Oxfam GB, World Vision, Plan International, Save the Children UK, and a number of EFA partner agencies are jointly organizing on this occasion a wide range of activities to mobilize public awareness and participation in promoting education for poor children as well as improving the impact of education on poverty reduction.

- ESG is functioning in a more regular and effective way. The international organizations meet every month while the bigger ESG group that includes bilateral donors, UN agencies, NGOs , and MOET meet on a quarterly basis.  The detailed plan of action for MOET Secretariat was developed and co-financed by different organizations.

### 3.	Education Forum

- One forum has taken place in January 2005 on “Towards Quality of teaching in Vietnam”. This forum brought together MOET officers, researchers, practitioners and teachers of all levels to share key issues/challenges of teaching and learning in the changing society in Vietnam.  Good practice from different NGOs such as Oxfam Great Britain, Save the Children UK was reflected.

4.	Social Economic Development plan and Education development plan

- International partners including DFID, EC, WB, CIDA, UNICEF and all member of the Education Sector Group have a joint comment to strengthen the 5 Year Strategic Education Development Plan 2006-2010. The suggestions covered both the content and the format of the Plan.   It was suggested that the plan should refer more explicitly to existing policies, programs and commitments, including agreed PRSC actions, EMIS, TBS for EFA and BCEP,  strengthening linkages between planning and budgeting.  The plan should also ensure that targets and plans for capacity development for teachers and educational managers, including those from ethnic minority groups, are consistent with the detailed targets and plans for construction and infrastructure development, the provision of separate sanitation facilities for boys and girls in all school sites.  There is a need in the plan to emphasize the necessity  for a stronger focus on the quality of education,  stronger promotion of modern teaching methods in teacher training institutes and throughout the education system. Annual achievement targets or objectives, with indicators and a robust monitoring and evaluation framework should be identified.  This would (i) make the plan more easily accessible in terms of goals and targets; (ii) identify criteria for progress and; (iii) indicate clearly selected priorities for resource allocation.  The Plan should identify responsibilities and time frames, with a clear sequencing of activities over time.

### Some recommendation for further improvement in the partnership work:

- Strengthening coordination is needed between bilateral & multilateral organizations, NGOs and MOET to ensure a comprehensive and effective support in education

- Education and WTO:  MOET has requested support from international donors regarding implications of WTO accession for education.

- The active role of Government body in coordination between organization will help to fill in technical and financial gaps to support government to achieve Vietnam education goals

- The national EFA coordination mechanism can be further reinforced to implement the National EFA Action Plan in the coming years, and to carry out the EFA mid-decade assessment in 2006.

#### Future plan of the group in terms of working formula

- Continue to work in different areas to support Government programme ESG will be strengthened with MOET leading roles to promote harmonization and coordination of all donors support to education to ensure international support in line with Government priorities and procedure, special focus will be on quality, equity and effective education at all levels.

# FOREST SECTOR SUPPORT PROGRAM AND PARTNERSHIP

# (FSSP & P)

in the final six months, 2005

The Forest Sector Support Program & Partnership is a broad framework for collaboration between the Government of Vietnam and now 24 (soon 25) international development partners working in the forestry sector. The FSSP & P Memorandum of Agreement (MOA) was signed in November 2001, and runs through 2010.    Prior to the FSSP & P establishment, it was preceded by the 5 Million Hectare Reforestation Partnership, which operated from 1998 through 2001. The FSSP MOA includes 15 basic principles of collaboration agreed amongst the partners, and a Program Framework, which specifies indicative performance standards for the broad goal, focused objective, or purpose, and specific activities under 9 Result Areas.

This report provides an update on major Forest Sector Support Program and Partnership implemented activities during the past 6 months, 2006 planned actions, and revised success criteria of FSSP & P.

Main activities implemented in the last 6 months

- Legal framework for Forest Protection and Development

As the (revised) Law on Forest Protection and Development was adopted by the National Assembly in 2004, and went into effect on 1 April 2005, work has been ongoing to prepare, or update, a number of supporting legal documents (decrees, decisions, circulars and regulations).   The Partnership is providing support to this work, with funding from the Trust Fund for Forests.   The Decree on Implementation of the Law has gone through several drafts and consultation workshops, and the final version of the decree was submitted to the Prime Minister in August 2005 for approval.

The FSSP and TFF are providing support to a number of other important legal decrees and regulations that are to being prepared in 2005-06 by the Forest Department, Forest Protection Department, and MARD’s Legal Department.  This legal work is part of the overall efforts to develop an updated and more coherent legal framework, which is important for Vietnam’s development and also for WTO accession.

- Formulation of National Forestry Strategy (2005-2020)

The Forest Department is leading efforts to prepare a new National Forest Strategy (2006-2020). Work has been ongoing since 2004, with the involvement of a 30-person inter-ministerial Strategy Team and a team of international and national consultants. Support for the strategy development is being provided by MARD, related Ministries, the FSSP CO Trust Fund, the Trust Fund for Forests (TFF), ADB and the World Bank, the FAO-Netherlands Partnership Programme (FNPP) and a wide range of key stakeholders.

Work on the NFS is also being linked and harmonized with a number of other ongoing strategies and studies, such as the preparation of the forest sector 5-year plan, more detailed plans for forest seedlings, forest material supply plantations, the non-timber forest products action plan, the forest research strategy, revisions of the 5 Million Hectare Programme (see below), studies on gender and poverty issues, etc.

The strategy will articulate a vision for the sector, which will seek to balance social objectives, such as poverty reduction and improvement of rural livelihoods, with improving the forest sector’s contribution to the national economy and ensuring environmental and biodiversity conservation for selected forests. The strategy will also look at future challenges, as Vietnam’s forest sector becomes more integrated into the global economy.  This analysis considers the likely future impacts of WTO accession and reduction in AFTA tariffs, as well as Vietnam’s obligations to international conventions and multilateral environmental agreements (MEAs).

The 15-year strategy contains an action plan for the first 5 years of implementation, as well as more general ideas for the future implementation.  Efforts have been taken to harmonise the NFS 5-year action plan with the forest sector 5-year plan, developed as a contribution to the MARD 5-year plan and thus to the National Socio-economic Development Plan (NSEDP, 2006-2010).

Although it was originally planned that the new National Forest Strategy would be approved by the Prime Minister in June 2005, it is now agreed that the strategy formulation will be finalized in early 2006.

- Five-year Planning

Earlier in 2005, the forest sector was actively engaged in preparation of its 5-year plan (2006-2010), to serve as a contribution to the MARD 5-year plan (5YP) and National Socio-economic Development Plan (NSEDP).  The final draft plan was submitted to MARD’s Planning Department in July 2005, and elements incorporated into MARD’s final draft, submitted to the Ministry of Planning and Investment.

- 5 Million Hectare Reforestation / 661 Programme

The Five Million Hectare Reforestation Programme (5MHRP), implemented by Decision 661, is government’s major forestry programme for the period 1998-2010.  It is a major government programme intended contributed towards the achievement of the CPRGS.  The 5MHRP aims not only to reforest Vietnam, but also to address issues of rural poverty and national socio-economic development.  Its objectives are to:

- To speed up forest plantation, regreen bare land, protect existing forests as well as new forests, increase the protective function of forests and protect the environment and biodiversity; create favourable conditions for sustainable national development, and increase the forest cover to more than 40% of the national territory;

- To create employment, increase incomes for local people [residents in forest areas], thus contributing to hunger elimination and poverty reduction; develop production and create conditions for secure livelihoods, and ensure national defense and security; and

- To create raw material areas in association with development of industries processing forest products.

Thus, the 5MHRP aims to contribute to improved environmental protection, poverty reduction, and enhanced contributions of forestry to the national economy.

As of 2004, the 5MHRP has achieved approximately 2 out of 5 million hectares of planned reforestation.  A major national workshop was conducted on 11-12 October 2005, to review implementation to date, and propose actions for implementation during the final five years (2006-2010).  Deputy Prime Minister Nguyen Tan Dzung instructed MARD to undertake certain actions.  A revision of Decision 661 will be issued in the near future. Proposed actions to complete implementation of the 5MHRP by 2010 are included within the forthcoming National Forest Strategy, as part of the NFS initial 5-year action plan (2006-2010).

4. Forest Sector Monitoring and Information System (FOMIS)

Work is ongoing to further develop the initial forest sector database.  Earlier in 2005, efforts were undertaken to establish an updated database on ODA support to the forest sector, to complement the data already collected by the International Support Group of MARD.  This data is being used in the preparation of the National Forest Strategy.  Work has also been undertaken to establish a network of national focal points for forestry-related Multilateral Environmental Agreements (MEAs).

5. Trust Fund for Forests (TFF)

Vietnam’s Trust Fund for Forests (TFF) is a grant facility to support pro-poor and sustainable approaches to forest management, and a transition towards a comprehensive sector-wide approach for development and cooperation in the forest sector.  By pooling resources from several donors into one fund, the TFF will provide a more effective means for supporting key sectoral priorities, which are agreed and updated annually by the FSSP partnership.   The TFF was established in June 2004.  Two technical advisors have been working with the FSSP Coordination Office and relevant ministries since November 2004, to develop the TFF Regulation, operational procedures for the TFF, launch operations, and build capacity to manage the fund.  In 2004, the FSSP Technical Executive Committee approved 5 small TFF grants, totalling € 200,000.  Early in 2006, the FSSP Partnership Steering Committee agreed to provide € 500,000 in support to formulation of the new National Forest Strategy and preparation of a number of legal documents.  During 2005, the TFF has issued calls for concept notes for both small and large grants.  It is anticipated that 2 small grants and 3 large grants will be approved before the end of the year.  Work to begin to develop benchmarks for sectoral budget support has been delayed until 2006.

6. Harmonization of Implementation Frameworks (HIF) Study

The Phase II HIF report was finalized in late 2004. This study looked at ways in which the procedures for large-scale forestry projects, whether funded by 661 or ODA, could be harmonized.  A proposal for Phase III HIF activities, to include provincial piloting, has been prepared and submitted to the TFF for possible funding.

7.  Other Ongoing FSSP&P Activities

The FSSP&P has been engaged in other ongoing activities, such as development of the Forest Sector Manual and improvement of communication systems, including the launching of a new FSSP&P website (www.vietnamforestry.org.vn) and quarterly newsletters Information exchange among FSSP, International Support Group (ISG), 5MHRP, and the Science and Technology Journal of Agriculture and Rural Development is being improved through regular newsletters, magazines and publications.

The FSSP Partnership Steering Committee (PSC) will be meeting in December 2005 to discuss the 2005 Annual Review and approve the 2006 work plan and budget.  An international consultation workshop on the draft National Forest Strategy is also scheduled for mid-December 2005.

The FSSP&P Provincial Reference Group (PRG) has been reformulated.  In September 2005, six regional FSSP networks (organized by agro-ecological zone) were established, with participation from more than 40 “forestry provinces.”  Henceforth, each network will choose its own network leader, who will then serve as the network representative in the PRG.  It is hoped that this change will enable the PRG and the networks to become effective means for decentralization of FSSP&P activities to the provinces.  In late 2005, the PRG will assist the Strategy Team with upcoming regional stakeholder consultations, and discuss regional priorities for the National Forest Strategy.

All these activities aim to improve the communications, transparency and governance among FSSP&P partners, and to support forestry’s contributions towards improving rural livelihoods and poverty reduction. The FSSP Partnership continues to work towards a gradual adoption of various elements of sector-wide approach (SWAP), and improved aid coordination and harmonisation.

Partnership Activities for 2006

In 2006, the FSSP Partnership will undergo a major review, i.e., its second mid-term evaluation.  This review is intended to be an opportunity to review and revise the overall structure of the Partnership, and see how it can be revised to support implementation of the new National Forest Strategy.  It is also anticipated that an external review of the Trust Fund for Forests will be undertaken earlier in the year, right after Tet.

Currently four core donors provide support to the activities of the Partnership and FSSP Coordination Office (FSSP CO), through the CO Trust Fund (CO TF).  The same four donors also fund the Trust Fund for Forests (TFF).  This support is committed through the end of 2007.  During the next year, agreement will be reached on a roadmap for moving towards a fuller sector-wide approach (SWAP), possible sector budget support, and building up capacity to gradually hand over some coordination functions from the FSSP CO to other units within the Ministry of Agriculture and Rural Development.

The intention then is that the Partnership and the Trust Fund for Forests will both provide support to the forthcoming National Forest Strategy and its initial 5-year action plan, and thus also to the implementation of the National Socio-economic Development Plan (NSEDP, 2006-2010).  As the Partnership moves towards a fuller programme, or sector-wide, approach, its partners will then be working to improve harmonization and aid effectiveness, in line with the agreements between Government and international partners as expressed in the Hanoi Core Statement of June 2005.

Some Possible Success Indicators for 2006

- New National Forest Strategy (2006-2020) adopted by Prime Minister, disseminated, and implementation commences

- FSSP&P work plan more closely aligned with work plans of national partners, and in support of the new NFS

- Partnership Memorandum of Agreement revised to more effectively support implementation of NFS

- Five “sub-partnerships” will be created, i.e., one for each of the five programmes for the National Forest Strategy

- Greater support to decentralization of activities

- Sector financing study will be undertaken, and sectoral benchmarks for sector budget support will be negotiated and agreed

- Information dissemination on key sector and partnership activities will be enhanced, i.e., ODA database for forest sector will be put on website

- Trust Fund for Forests will be supporting key strategic priorities

- Forest Sector Monitoring and Information Systems (FOMIS) will be further developed at national level, i.e., for monitoring implementation of NFS and 5-year plan, reporting on international environmental agreements, etc., and also piloted at provincial level

NATURAL DISASTERS MITIGATION PARTNERSHIP

(NDM - PARTNERSHIP)

Introduction

The NDM-Partnership completed its initial phase of implementation in late 2003, which has resulted in setting up the Partnership institutions and coordination mechanism and finalization of several provincial pilot projects. A more comprehensive Action Plan of the Partnership for the next three years has also been developed setting more challenging targets for the Partnership in strengthening coordination while contributing more actively to sectoral priorities and the implementation of the CPRGS.  This note provides a brief update on progress of the NDM-Partnership in 2004 (from December 2004 to November 2005), which was devoted mainly to continuing of mobilizing partners in discussing and finalizing the new Action Plan, obtaining official endorsement of NDM-P 2nd phase by the Government in addition to accomplishing a majority of workload of the two pilot projects in Binh Dinh and Da Nang provinces.

1) Progress of the NDM-Partnership over the year 2004 to support CPRGS and sector strategies and programs

- The year 2004 has recorded the actual starting of the construction and completion of majority of the workload of the two provincial priority projects in Binh Dinh province and Da Nang city.  The capacity building component of the two projects is in its stage of implementation. These projects are a combination of upgrading small-scale flood control infrastructure and grassroots capacity building to reduce vulnerability of people, particularly the poor to annual flooding. As such, they will contribute to reducing the human and property loss due to floods while empowering the communities and people in planning for their own actions in disaster reduction.

- With wide consultations and inputs from different partners in the formulation process of the NDM-P’s new Action Plan, the Plan has incorporated CPRGS implementation targets and sectoral priorities including mobilization of support for finalizing the Strategy for disaster reduction, integration of disaster risk concerns in the new Water Resources Management Strategy and preparing a new Law on dyke management and disaster reduction, etc.

- A number of NDM-P partners have achieved good progress in their on-going and planned programmes/projects in disaster reduction aiming sector-wide approach issues and poverty reduction. Examples of these are the AUSAID project in Quang Ngai, formulation of the World Bank NDM project and other water-supply and sanitation and vulnerability reduction projects of INGOs.

- In cooperation with ISG, NDM-P has supported the Dyke Department in developing the Ministry’s five-year work plan (2006-2010).

2) In follow-up to the discussion at the mid-term CG meeting, what progress has your partnership group made in developing views/proposals for integrating the CPRGS approach into socio-economic planning?

- As part of its workplan for 2005, the NDM-P, in close collaboration with the International Support Group (ISG) of the Ministry of Agriculture and Rural Development (MARD), facilitate discussions and provide inputs to ensure that a holistic approach for disaster reduction is clearly reflected in Ministry and subsequently the National 2006-2010 Socio-economic development plans.

- The Action Plan has outlined a number of studies on inter-linkage between natural disasters and poverty, environmental degradation

3) Over the next twelve months, what concrete actions will your group take?

Proposal for the NDM-Partnership phase 2 has been endorsed by the Government in September 2005. The key milestones of the NDM-P will be actual operation of the NDM-Partnership phase 2. The Netherlands Embassy, AUSAID, Luxembourg Embassy, SIDA and UNDP have expressed their continued support to NDM-P and together signed in the Letter of Intent. Actual implementation of its Action Plan is expected to start soon.

4) What are your revised success criteria - or milestones- for 2005 to ensure your partnership group reaches its development outcomes?

The approval and implementation of the new Action Plan of the NDM-P will lead to many concrete outputs, the principle three of which are:

- A final Strategy for Natural Disaster Reduction that emphasizes vulnerability reduction, particularly for the poor in hazard-prone areas (by June 2005)

- Recorded inputs to the MARD and National 2006-2010 Socio-economic Development Plans for 2006-2010

- An Implementation Framework that shows priorities and clear assigned responsibilities across sectors and at all levels to implement the Strategy for natural disaster reduction (draft for discussion by end 2005)

5) The future of this Partnership

Natural hazards are forecasted to be on the rise with high risks to turn into disasters without exceptions for a disaster prone country like Viet Nam. There has been an increasing recognition on causes of natural disasters for poverty in Viet Nam and the CPRGS has set a clear target to halve by 2015 the number of people relapsing into poverty due to disasters. Further, awareness on climate variability and the risks of natural disasters is increasing. Much remains for the NDM-P to further promote its coordination and mobilization of other sectors, institutions to support a broader disaster reduction agenda. The Government and MARD renewed commitments to this Partnership as well as participation of new partners from other sectors, research institutions and local levels are keys to success.

INTERNATIONAL SUPPORT GROUP (ISG-MARD)

# ISG process: An update of 2005 progress and recommendations

## ISG activities follow the 7 Key Areas
(Work Plan 2004-2006)

## Facilitation of policy dialogue within and between MARD and donors

## Coordination in formulation of foreign-funded programs/projects

## Development and coordination of thematic studies

## Support to the International Cooperation Department (ICD of MARD)

## Information collation and dissemination

## Capacity building and management processes (appropriate training and other capacity building activities)

## Monitoring and evaluation (in ISG process)

# I. Activities planned for the year 2005

## Main activities planned:

## Two meetings of ISG Steering Board (the 10th in July and 11th in November)

- ISG annual Plenary Meeting in September 2005

## Support to the development of the sector FYP (from Mar to Dec 2005), and support its implementation

- Support to MARD and donors in formulation of the RWSS Sector Support partnership.

- Activities of the three Thematic Ad-hoc Groups (TAG).

- Policy Advisory Briefings (PABs) process

- Continue support for 5 provincial dialogue platforms (Thanh Hoa, Thai Nguyen, Tra Vinh, Soc Trang, An Giang)

## Support MARD institutional development activities, strengthening capacity in formulation and development ODA M&E system; strengthen capacity in management of ODA, INGO and FDI for the ARD sector

## Improve activities of ISG MIS (website ISG, ISG newsletter, Monthly Briefing, integrated database…) in service of sector policy dialogues and management of foreign resources.

# II. Main activities done in the past eleven months of 2005

10th Meeting of the ISG Steering Board 6 July 2005:

- ISG SB members approved the proposed adjustments for the ISG work plan and budget for 2005.

- ISG SB members approved the ToR of consultants to review ISG process for 2003-2005 and develop an ISG Work Plan for 2006-2010.

- ISG SB agreed that there should be a review and on that basis to agree to the continuation of the ISG process. A request for an extension of the ISG Trust Fund will then be submitted to GoV for approval.

- ISG SB members agreed to the contents of the three presented PABs.

- ISG SB approved timeframe for ISG Annual Plenary Meeting to be in September 2005, and the theme is “Investment for the agriculture and rural areas”.

11th Meeting of the ISG Steering Board 2 Nov 2005:

## The Steering Board discussed and approved the draft review report of ISG performance for 2003-2005 and draft proposed work plan for ISG process in the new period of 2006-2010.

- The Board also agreed that the ISG Trust Fund should be extended until 2010.

- Follow-up steps after the meeting were agreed.

Organization of the ISG Annual Plenary Meeting 2005:

- From 22-23 September 2005, ISG hosted the Plenary Meeting with the topic of “Investment for the Agriculture and Rural Development Sector.” This important forum attracted participants including from MARD, relevant GoV agencies, donors, and the domestic and foreign private sectors. This forum helped lay the groundwork for ICD taking on the important function of coordinating FDI in the ARD sector.

- During the meeting, ISG was identified as a potentially key player in this function.

- The Royal Netherlands Ambassador is quoted as saying that “the ISG process is important for communication channels between the Government and donors. The Royal Netherlands Embassy congratulated MARD with the ISG process, which could serve as an example for other ministries.”

- Outputs of the forum, including the minutes, documents and presentations of the two-day forum are now available on the ISG website for larger audience’s reference. http://www.isgmard.org.vn/

## Development of Policy Advisory Briefings (PAB) within the ISG process

## Some PABs completed and approved (circulated to all stakeholders – also shared at the mid term CG meeting 2005- and now available on the ISG website), including:

- PAB No. 1: Experiences from the first PAB on “Streamlining CPRGS into MARD Rural Development Strategy” (completed March 2005

)

- PAB No. 2: Joint donor statement on MARD planning process for 2006-2010 (completed March 2005)

- PAB No. 3: Policy recommendation drawn out from the joint Gov-donor Rural water supply and sanitation (RWSS) sector review (completed May 2005)

Some PABs still pending:

- Recommendation and issues drawn out from the planning for 2006-2010 of the forestry sector, including viewpoints of international partners (proposed to be completed June 2005, but still pending due to the fact that no concensus reached among the forestry sector stakeholders)

- Recommendation and issues drawn out from the planning for 2006-2010 of the ARD sector and recommendations for an improved mechanism for coordination among key players in the sector (proposed to be completed July 2005, but still pending due to lack of resource person.)

A new PAB (PAB4) on recommendations and issues for consolidation of the ISG process (see the attached document):

- Just been completed by the ISG review team 2005 and approved by the ISG Steering Board at the 11th meeting of the Board on 2 November 2005.

## Follow-up actions for PABs process:

##### Any PABs should be articulated directly by and have direction and steering from the MARD Minister.

##### Completion of PABs as proposed:

##### Publishing series of PABs as reference policy documents; uploaded on the ISG website for larger audience’s reference.

##### Submit to MARD Minister.

##### Shared with the donor community at the mid term and annual CG meetings 2005.

PAB considered as an effective policy advise tool for the ARD sector; Stakeholders are encouraged to actively participate in PAB process to ensure common interests/benefits.

PAB’s success depends on the willingness and active contribution from the development community.

## Operation of Provincial Policy Dialogue Platforms (PDP) of the ISG process

- Within the framework of TAG3 “Support the implementation of the comprehensive poverty reduction and growth strategy (CPRGS) in agriculture and rural areas”:

### Coordinate with Planning Department in preparation for introduction of guidelines for formulation of new FYPs and plan 2006 for dialogue platforms provinces,

### In collaboration with IFAD and CECI, organized a workshop between 12 provinces to share information and experiences on community empowerment and community-based planning.

## Activities of Thematic Ad-hoc Groups (TAGs) and thematic activities:

- TAG1 “International Agro-economic integration and policy”:

## Monitoring implementation of 3 study proposals approved by ISG SB Chairman. One of the studies is the review of the FDI performance in the sector, still being carried out, which contributed a lot of good resources/inputs for the ISG annual Plenary Meeting on “Investment for the agriculture and rural development sector” held 22-23 September 2005 in Hanoi. (See further in the Appendix: progress reports of the three study teams)

- TAG2 “Support Development of hydraulic works, disaster control and rural water supply”:

### Support the joint GoV-donor RWSS sector review (organization of meetings, workshops, sharing of info, results and progress of the review team). This review was completed with a full set of documents/reports/recommendations circulated to all the stakeholders and now also available on the ISG website.

### Support to the joint GoV-donor task force on formulation of the RWSS Support Partnership. Four meetings of the Task Forces held in the year until now. Information and documents of the design consultant group are shared among relevant stakeholders.

### Contribution to the ISG MIS (relevant legal documents, news regarding water sector activities) for sharing with ISG stakeholders. All of these documents can be obtained from the ISG website or ISG Secretariat.

- TAG3 “Support the implementation of the comprehensive poverty reduction and growth strategy (CPRGS) in agriculture and rural areas”:

### Continue to support efforts in implementation of CPRGS in the sector.

Main activities of the ISG information system:

- The ISG website is regularly updated: news, reports, legal documents, activities of partnerships and TAGs. ISG website is considered as the most effective tool for information dissemination (e.g. in service of the annual ISG plenary meetings)

- The ODA Database regularly updated and ready to provide information at request of MARD and donors.

- Integrated database are under construction: national consultants have been recruited and carrying out the planned work for the database. Bidding procedures to be completed soon for best solution/software.

- ISG Newsletter quarterly produced (two issues published for 2005; two issues to be published in early November and end of December 2005).

- ISG Monthly Briefings regularly issued from 5 to 7 of each month; circulated to all the ISG stakeholders. More and more contributions from the stakeholders have been made to the ISG Secretariat.

- The ISG annual survey 2005 has been undertaken. Details will be presented in the final annual ISG report 2005.

Review of the ISG process performance for 2003-2005 and development of a new work plan for ISG in the period of 2006-2010:

- A team of national and international consultants was engaged to carry out the proposed tasks.

- Draft review report and work plan completed, approved by the ISG Steering Board.

- Conditions should be ensured for seeking extension permission from the Government to the ISG Trust Fund (in November 2005).

## Support to formulation of the FYP 2006-2010 of the agriculture and rural development Sector:

- Since March 05: preparation and support to donor consultation process of MARD.

- 18/3/05: Consultation workshop held with following outputs (available on ISG website):

## Synthesis report of international partners comments to development of the FYP

## Joint donors Statement on the FYP development process.

- The final draft of the ARD Plan for 2006-2010 was submitted by MARD to the Government for synthesized and incorporated into the Socio-economic development Plan (SEDP) of Vietnam. This can be obtained from ISG Secretariat.

- Supporting activities provided to specific units under MARD (development of log frames for the FYP, Plan 2006 for some sub-sectors, trainings; the planning tasks is to be completed by end of November 2005). However, these tasks are now pending due to some reasons, including lack of the pro-active involvement and willingness of the relevant departments.

- Support ICDMARD in formulation of its 5-year plan 2006-2010. Meetings have been held among ICD leaders and staff, and some international experts.

This activity is highly appreciated by MARD and donors, through which the role of ISG process in coordination is strengthened.

## Activities within ISG framework to support efforts to strengthen capacity and institution of the management task in general (ODA, FDI, NGO), and sector ODA monitoring and evaluation.

## Support MARD (CPOs, ODA projects) in introduction of application of the harmonized progress reporting tool approved by the 5 banks: WB, ADB, KfW, AFD, JBIC to selected projects which were approved by MARD Minister

## Support MARD ICD in organization of the Training workshop on M&E and Application of the harmonized progress-monitoring tool agreed among the 5 banks on 10 August 2005.

## Support MARD in formulation of pilot system for monitoring and evaluation of ODA projects in the water sector (piloted on two big loan projects)

## Basic completion of the ICD website which is now online within MARD system to get further comments before it can be made public.

## Developing the integrated database regarding international cooperation of the sector:

### A workshop held April 2005 for collation of comments from ICD officers and related partners for completion of the ICD website and the database

### Consultants (editing and information collation and analysis) have been engaged from July 2005 to carry out the activities mentioned in the ToR of the integrated database.

### Bidding procedures are now being completed for engaging a legitimate company to design the software/application.

## Provision of training for ICD officers on networking (April 05)

## Support ICD MARD in formulation and implementation of some bilateral cooperation programmes (for example: MARD Sida Cooperation Programme)

III. Concrete actions over the next twelve months

## Seek an extension for the ISG Trust Fund as agreed by the ISG Steering Board.

## Consult with donors and MARD officials conditions ISG should meet to justify an extended Framework Arrangement (FA).

## Base on the MARD’s FYP 2006-2010, develop a road map to guide cooperation in policy and coordination of donor assistance/FDI investment.

## Hold a number of meetings and workshops on key policy issues per schedule and at request of Minister. Meeting Results Briefings should be produced to summarize key decisions, recommendations and future work.

- Identify key issues for developing study proposals.

## Prepare Policy Advisory Briefings (PAB) regularly on priority demand basis. Encourage MARD Minister and other ISG members to propose topics for PABs at any time.

## Utilize and strengthen the established expert networks established within MARD to strengthen ISG’s position as a communication focal point with in MARD on foreign funded projects.

## Have TAGs officially established through a Ministerial decision.

## Encourage ISG stakeholder to get familiar with the FYP and ensure that its principles and targets are incorporated into ISG policy discussions.

## Identify appropriate areas for ISG support in implementing Hanoi  Core Statement.

## Support the development of MARD institutional framework related to management and coordination of external resources for the sector (ODA, NGO, FDI).

Appendix:

Progress report on implementation of thematic studies in the framework of the Thematic Adhoc Group 1 (TAG1)

# I. Study 1: Promoting the development of forms of joint ventures and cooperation in agriculture trading and production

Progress: The study on agricultural product transactions, which was evaluated and financed by ISG Secretariat, Ministry of Agriculture and Rural Development, has been carried out from April 2005. Up to now, the research agency (Institute of Agricultural Economics) has been implementing following activities:

- Design survey forms and questionnaires to interview households, traders, marketing agents, managerial staff and focal markets.

- Collecting information and signing contracts for implementation of 2 following thematic sub-studies:

  - Current status of domestic agricultural product transactions;

  - Experiences on agricultural product transactions of other countries.

- Carrying out survey in provinces of Tien Giang, Can Tho, Dac Lac and Bac Giang

- Carrying out survey at focal agricultural product markets in Hanoi and HCM City

- Designing FORM and selecting data analysis software.

Implementation arrangements of other activities in the framework of the study:

- From 01-15/11/2005 put in and analyze the collected data, carrying out more surveys if necessary. Developing the report frame, summarizing survey findings and writing the first part of the study. Organizing a seminar in Ho Chi Minh City.

- From 15-30/11/2005 writing the report and hand it in the ISG Secretariat.

- From 1-15/12/2005: Organizing a seminar in Hanoi and complete the final report.

- From 15-25/12/2005 submitting the report and taking over.

- From 25-30/12/2005: Complete administrative procedures and payment.

II. Study 2: Training Need Assessment with respect to international economic integration at sector-wide scope

Progress: After the study was approved, the research agency, International Cooperation Department, has cooperated with concerned units to carry out the training needs assessment (TNA). Activities and progress are as follow:

|  | Procuring TNA consultants (mostly from Agricultural Economics Institute and University of Agriculture No. I) | 7/2005 |
| --- | --- | --- |
|  | Developing TNA outline | 8/2005 |
|  | Training on survey skills and method | 12/9/2005 |
|  | Collecting secondary information | 9/2005 |
|  | Carrying out survey in some provinces in the North, the Central and the South | 15/9 - 30/10/2005 |

Finance: To carry out above-mentioned activities, ISG Secretariat financed the study team an amount of US$ 6,172 (accounting for 36.7% of the total budget for the study).

Expected implementation arrangements to the end of 12/2005:

|  | Processing data | 15/10 - 15/11 |
| --- | --- | --- |
|  | Writing report | 15 - 30/11 |
|  | Organizing seminar to collect comments on the report draft | 1 - 15/12 |
|  | Completing the report | 16 - 30/12/2005 |

III. Study 3: Performance analysis of FDI in agriculture and rural development

After the study was approved, the research agency, International Cooperation Department, has cooperated with concerned units to carry out the study. Up to now, following activities have been implemented:

|  | Procuring consultants |
| --- | --- |
|  | Developing the outline |
|  | Collecting secondary data |
|  | Designing the questionnaire and undertaking information collection |
|  | Writing report |

Expected implementation arrangement to 12/2005

|  | Collecting more data |
| --- | --- |
|  | Completing report |
|  | Organizing seminar to collect comments on the report draft |
|  | Final touch to the report |

Policy Advisory Briefing (PAB) No. 4

Some Key Issues for Improving the ISG Process in 2006-2010

Author: 	Eric Biltonen

Date: 		31st  October 2005

Introduction

The ISG recently facilitated a performance review of the ISG process for 2003-2005. The findings of this review served two purposes. The first purpose was to provide justification for the extension of the ISG Trust Fund through which activities for the ISG process are funded. The second purpose was for the findings of the performance review to serve as input into the design of a new ISG Work Plan for 2006-2010. It is hoped that the recent review and new work plan will help the ISG process become more effective in fulfilling its mandate.

The ISG process provides a link between MARD and the donor community. Regardless of the achievements made by the ISG Secretariat, the full potential of the ISG process relies on the active ownership and participation of its stakeholders. This Policy Advisory Briefing outlines several issues and recommendations identified during the recent performance analysis that relate directly to the Minister of MARD.

The Issues

The ISG was established in 1997 with the purpose of advising the Minister on the utilization and effective mobilization of ODA in the Agricultural and Rural Development Sector (Decision 541/NN-TCCB/QD dated April 9th, 1997). Two key roles that have been identified for the ISG are facilitating Policy Dialogue Forums and facilitating the gathering and sharing information. Additionally, the ISG was to support MARD in the coordination of ODA to improve the effectiveness of its utilization. Thus, a broadly defined framework was established for two-way interaction so that MARD and the donor community could influence each other’s policies in the Agricultural and Rural Development sector. This requires a process that is both fully owned by the stakeholders and responsive to the policy needs of MARD.

During the development of the 2004-2006 ISG Work Plan, several issues were identified that needed to be improved for ISG process to work more effectively. These included the need to develop a mechanism to communicate the findings and recommendations resulting for ISG activities to the top-levels of MARD. It was recommended that Policy Advisory Briefings be issued at regular six month intervals and be approved by the Steering Board. It was not decided; however, how topics for the PABs should be decided upon and prioritized. Moreover, the process of approving PABs to be submitted to the Minister was based on the meeting schedule of the ISG Steering Board and not based on the policy needs of MARD.

A key component of the ISG process has been the Thematic Ad-hoc Groups (TAGs). These groups meet regularly and on an ad-hoc basis to discuss matters on specific sub-sectors and topics effecting MARD policy and planning. The recent review highlighted that the success of these groups relied on the active participation of relevant departmental staff within MARD. The review further identified a constraint in mobilizing MARD resources to effectively facilitate in carrying out ISG activities (developing PABs, attending TAG meetings, etc.) The TAGs were established “outside” the official MARD work schedule so participation in TAGs is an additional, not a regular, burden on the work loads of MARD staff. ISG effectiveness would be enhanced by providing a mechanism so that MARD resources could be mobilized more effectively.

Another key function identified for ISG has been the identification and facilitation of Thematic Studies to address key issues related to the effective utilization of ODA. The recent review highlighted the existing lack of a mechanism for identifying and prioritizing topics for Thematic Studies. While a few thematic studies have been identified and facilitated, this remains an under-performing role of the ISG. Moreover, if the role of supporting coordination of FDI is adopted by the ISG, thematic studies can provide very important support to the effective utilization of both ODA and FDI. Thematic Studies can provide the scientific knowledge necessary for holding informed policy dialogues.

Key Policy and Institutional Issues

The review highlighted several key areas to improve the effectiveness of the ISG process. Two important issues are increasing the ownership of the ISG process by MARD and making the process for demand-responsive to policy development needs in the ARD sector.

As stated in the Decision establishing ISG, the overarching function of the ISG is to provide consultancy to the Minister of MARD. Fully addressing these two issues will thus require the active participation of the Minister of MARD. The following issues are given as recommendations to mainstream the ISG process into MARD policy and planning processes and to ensure that the outputs of the ISG process are meeting the real needs of MARD.

It is recommended that:

- The topics of PABs should be prioritized based on the party identifying the topics. The order of prioritization should be: topics identified by the Minister are given highest priority, topics identified by active ISG members as second, and topics identified by others is last priority.

- In response to recommendation 1, the Minister is encouraged to make full use of the ISG process by requesting policy advice on specific topics within their mandate. ISG Stakeholders are further requested to make arrangement in order to respond in a timely manner to requests of the Minister.

- It is recommended that the existing TAGs and any new TAGs be (re-)established by Ministerial Decision, so that departmental participation is made a part of MARD staff official annual work plans. This will help the ISG process in mobilizing existing resources within MARD required for its effective operation.

- It is recommended that proposed Thematic Studies be prioritized based upon the party recommending the study. Top priority will be granted to topics requested by the Minister, second priority will be given to active ISG members, and third priority will be granted to all others.

- In response to recommendation 4, the Minister of MARD is encouraged to make regular requests for the facilitation of Thematic Studies through the ISG process.

By allowing the ISG process to be increasingly guided by priorities articulated by the Minister, MARD will demonstrably increase its ownership of the process, while also making ISG more relevant to the real needs of MARD. Finally, requests made to the ISG through the Minister will also serve as a useful indicator for evaluating the impact the ISG has on policy making within MARD.

# For further information, please contact us at:

# Secretariat of the International Support Group (ISG)
Ministry of Agriculture and Rural Development (MARD)

# Room # 209, A9, No 2 Ngoc Ha, Hanoi
Tel:  + 84 - 4 – 7336610; Fax: + 84 - 4 - 7336624
E-mail: isgmard@fpt.vn
Website: www.isgmard.org.vn

TRANSPORT PARTNERSHIP GROUP

- Partnership Assessment

  - The status of the partnership group

Since its establishment in July 2000, the group has consolidated information and experience on projects and programs in the transport sector in order to encourage the alignment of supports and the improvement of aid effectiveness.  The group is currently moving toward a forum of active discussion on sector issues and in joint policy formulation. 　Besides the discussion on the next five year plan, focus of the partnership group to date has been on three specific issues: “Road Maintenance,” “Traffic safety” and “Hanoi Urban Transport”.

  - The structure of the partnership group

Presently MoT and JBIC jointly chair the partnership group meetings with participants from MoT-affiliated organizations and donors involved in the sector. The partnership group values flexibility in its membership and actively involves new participants relevant to discussed topics.  Hanoi People’s Committee (Hanoi PC) participated in the past few meetings which focused on traffic safety and urban transport in Hanoi.

- Achievement of the partnership group

  - The 10th and 11th Transport Partnership Working Group Meeting

The 10th transport partnership group meeting was held on July 7th, 2005, and the 11th meeting is planned to be held on November 14th, 2005.  Both meetings focus on Road Maintenance, Traffic safety, Hanoi Urban Transport, and Socio-Economic Development Plan for 2006-2010.

  - The progress of the partnership group

- Road Maintenance

Several donors have supported the Vietnam Road Administration (VRA) in building maintenance capacity for national highways.  The previous partnership group meeting held last year found out that there was room for improvement of coordination among stakeholders, especially ADB, DFID, JBIC and WB.  Since then, the partnership members hold regular meetings for coordination based on the demarcation of donor support agreed at the meeting last July (see attachment).  Currently, more attention is paid to such questions as: how to ensure the sustainability of the road maintenance system supported by donors; how to secure necessary organizational arrangement and enough budgets for road maintenance.  In order to address these issues, it is proposed to draw a comprehensive picture for road network maintenance including both at national and sub-national level.

As for the rural transport, all major donors have reached a consensus for necessity of a consistent and comprehensive capacity building approach for sub-national transport development.  The study for updating the rural transport development strategy has commenced with the assistance of DFID.  The output of this study will be shared in the 11th meeting.

- Traffic Safety

Development of road networks and associated rapid motorization has brought about an increase in the number of traffic accidents, which is a very critical problem not only from humanitarian but also from socio-economic perspectives.  Seeing this as a potential risk for the country’s economic growth, the 10th meeting dealt with the traffic safety for the first time, and the partnership members confirmed the necessity for further efforts and support to improve the traffic safety.  At the same time, the coordinative role of TSPMU was remarked to ensure the consistent approach among donors’ support.  The 11th meeting will discuss more details of the current overall demarcation of donors’ support, which will enable the partnership members to understand what kinds of support are required specifically.

- Hanoi Urban Transport

Coordination among donors has been made through the partnership group meetings as well as regular meetings arranged by donors.

JICA has assisted Hanoi People’s Committee in preparing “Comprehensive Urban Development Programme in Hanoi Capital City” (HAIDEP), while “Hanoi Metropolitan Master Plan” is being undertaken by MOC and the National Institute of Urban and Rural Planning under the technical assistance of WB and Ile-de-France Region (IMV) with the support of the cooperation service of the French Embassy.  These plans have been utilized to align donors’ supports and ensure priority of individual transport projects in Hanoi.

The WB has been preparing Hanoi Urban Transport and Development Project (HUTDP), which includes Bus Rapid Transit (BRT) component and road component.   Several meetings were held between WB and JBIC to discuss coordination (i) between the Ring Road No.2 (Buoi to Nhat Tan) to be formulated by WB and the proposed Nhat Tan Bridge Construction Project to be formulated by JBIC and (ii) between BRT component and the JBIC-funded Transport Infrastructure Development Project in Hanoi & the JICA-funded Hanoi Transport Safety Project.

The F/S for the Hanoi rail public transport project has been completed with the supports from the French government and submitted to the Vietnamese government in October 2005. The approval from the Prime Minister is expected before the end of this year.

The F/S for the elevated railway project between Hanoi and Ha Dong was completed with the support of China and submitted to the prime minister.  The prime minister is now considering the comments from related ministries.

- Socio- Economic Development Plan

MOT has already submitted the transport sector development plan for next five year (2006-2010) to Prime Minister’s Office in accordance with Prime Minister’s guidance (Ref. No.33/2004/CT-TTg) on drafting the 2006-2010 Socio-Economic Development Plan (SEDP). In the process of finalization of transport sector development plan, the partnership group plays a vital role in channeling inputs from donors to MOT.

At the 9th meeting, the partnership members reached a consensus on the outline of donors’ input to support MoT in drafting the new SEDP.  Based on the agreed outline, the performance during 2001-2005 was reviewed and the orientation for the 2006-2010 development plan were studied and shared with other stakeholders at the 10th meeting.  The findings of the study on the 2006-2010 development plan include that 1) the linkage between inputs and outcomes is weak, 2) the fund source is absolutely lacking, 3) the planning process in the relevant organizations, especially sub-sector agencies, needs to be improved, and 4) the absorptive capacity of MoT needs improvement.

These findings led to recommendations of i) proper demarcation with regard to investment and O&M between central and local governments, ii) acceleration of equalization of transport SOEs, iii) prioritization of investments, iv) strengthening of planning capacity, and v) harmonization between transport sector development plan and regional development plan.  MOT will present at the 11th meeting as to how it has incorporated these recommendations in the process of finalization.

It is also noted that the 11th meeting will invite MPI to make a speech on what the partnership group should do in order to assist the Government of Vietnam in implementation of Hanoi Core Statement (HCS) on aid effectiveness.

- Actions for the next 12 months

- To continuously support MOT to plan and implement the transport sector development plan for 2006-2010

- To assist VRA to draw a comprehensive picture for road management systems and a road map toward completion of data collection for the entire road network, in order to ensure organizational arrangement, and identity necessary budget for road maintenance,

- To help MOT develop a Medium Term Expenditure Framework (MTEF) in transport which would bring together the need to plan under budget constraint, to balance investment and recurrent expenditure, and to set out clear priorities and performance measures for PRSC-5.

- To continue efforts to align donors’ support in Hanoi urban transport and traffic safety.

＜Road Maintenance demarcation>

PMS (Pavement management system): its scope is national roads

|  | Item | Contents | Donor |
| --- | --- | --- | --- |
| 1 | Database | Data are collected by RRMCsand PRMCs | ADB |
| 2 | Maintenance Planning | RRMUs and PDOTs make plans to submit VRA |  |
| 3 | Plan Analysis | VRA analyzes plans | WB |

BMS (Bridge management system): its scope is national bridges

|  | Item | Contents | Donor |
| --- | --- | --- | --- |
| 1 | Database | Data are collected by RRMCs and PRMCs | ADB |
| 2 | Inspection | Checking if repair should be needed or not | JBIC |
| 3 | Maintenance Planning | RRMUs and PDOTs make plans to submit to VRA |  |
| 4 | Plan Analysis | VRA analyzes plans |  |

DIỄN ĐÀN ĐÔ THỊ VIỆT NAM - VIET NAM URBAN FORUM

37 LÊ ĐẠI HÀNH, HÀ NộI

# Tel: 84-4-9746011; Fax: 84-4-9745991; E-mail: urbanforum@fpt.vn

PARTNERSHIP REPORT

FOR THE CONSULTATIVE GROUP MEETING

On the Operation in 2003-2005, Action Plan in General and for 2005-2006

of Viet Nam Urban Forum

- Introduction

The Viet Nam Urban Forum (VUF) is officially founded on 22nd October 2003, with the signatures in the “Memorandum of Understanding” of 7 Vietnamese partners (Ministry of Construction, Ministry of Planning and Investment, Ministry of Natural Resources and Environment, Ministry of Home Affaires, Ministry of Finance, Viet Nam Association of Cities, Ha Noi People’s Committee) and 8 international partners (UNDP, WB, ADB, SDC, EC, French Embassy, SCF-UK and BTC), and MOC is the coordinating agency.

On 3rd February 2005, AFD (France) and on 14th June 2005, SGS company (Australia) have signed respectively in the MOU to become members of Viet Nam Urban Forum.

The forum is a place of policy dialog, exchanges of experiences, lessons to contribute to the formulation and implementation of policies in urban management and development in Viet Nam between ministries, sectors, localities of the country and the donor community, where the Government of Viet Nam plays a key role.

It is expected that in November 2005, VUF will admit 3 new members, i.e. UN-Habitat, JICA and the Center for Urban Projection and Study (PADDI supported by France).

The Executive Board of VUF consists of representatives of all members, chaired by the Vice Minister of Construction Nguyen Tan Van. The Executive Board convenes every 6 months..

The Forum Secretariat consists of officials of MOC involved on the part-time basis, headed by the Director General of ICD, Mr. Nguyen Sinh Hy. The Secretariat meets every month. The Forum Coordinator is the Deputy Director of ICD, Mr. Pham Khanh Toan.

The VUF office is located in the compound of MOC, 37 Le Dai Hanh, Ha Noi.

- Executed Works at VUF

- Organization

This is a new kind of partnership, where interests of local and international partners are harmoniously combined in the management and development of Viet Nam’s urban system. Therefore, experiences in organizational works of MOC are limited. The recruitment of the former coordinator was also not done well. All this has led to passive and ad hoc actions of the Forum.

It is until August 2005, after MOC reorganized the Secretariat and appointed the new coordinator, the VUF started to reactivate its role. The Executive Board meeting on 7th October 2005 has set out the general action plan as well as some major activities in 2005-2006 of VUF.

- Study

Main studies done by members of VUF are

- Study on "Migration, Urbanization and Transformation in Rural Areas of Viet Nam", by Mr. Jean-Marie Cour, done in 2003, sponsored by French Embassy.

- Study on "Urbanization Policy" by Mr. Jipgar Joshi, done in 2003, sponsored by UN-Habitat.

- Consultation by IMV on the Regional Planning of Ha Noi Capital, done in 2004, 2005, sponsored by French Embassy.

- Study on "Technical Assistance for Regional Planning in Viet Nam" by Mr. Lawrie Wilson, done in 2005, sponsored by WB.

c. Organization of Workshops and Conferences

VUF has organized presentations, workshops and participated in the organization of large conference, such as:

- Presentation of study results by Mr. Jean-Marie Cour, on 14.11.2003, sponsored by French Embassy.

- Workshop on "Housing for Low Income Households in HCM City" by VeT, on 28.11.2003, sponsored by French Embassy.

- Workshop on "Urban Finance at Sub-regional Level and Infrastructure Bonds of HCM City", on 18.3.2004, sponsored by WB.

- International Conference on "City Development Strategies", on 24-26.11.2004, sponsored by the Cities Alliance (CA), organized by MOC.

- Workshop on "Wastewater Treatment Technology", on 28.3.2005, sponsored by WB.

- Workshop on "Regional Planning of Ha Noi Metropolitan Area", on 10.5.2005, sponsored by WB, JICA and IMV.

- Workshop on "The Practice of Urban Management and Planning in the Market Economy", on 15.6.2005, done and sponsored by SGS Company.

d. Training

VUF was the focal point for the following training activities:

- Direct and Video-conferencing training on urgent issues of urban management and planning, from January to April 2005, organized and sponsored by WB.

- Study tour on urban management and governance in Kumning (China). There 04 representatives from MOC, MPI, MOF and MOHA taking part in this delegation, from 15-20.5.2005, organized and sponsored by SDC.

- The Action Plan of VUF

a. General Action Plan

Based on the 4 objectives: (i) Policy dialog; (ii) Sharing of experiences and lessons learnt; (iii) Recommendation of policy frameworks; (iv) Information database, the Forum has identified the outputs to be achieved, then the following concrete activities towards these outputs..

There about 20 activities envisaged focusing on 4 main topics of interest of the Forum: (i) Urban planning and development; (ii) Urban infrastructure development and environment; (iii) Urban land and housing development; (iv) Urban administration reform.

b. Action Plan for 2005-2006

Based on the activities that the members of VUF have done and are doing, the Forum has set out some concrete activities which are practically effective for the urban development such as regional planning, methodology in plan making, strategy formulation, finance reform, review of experiences and study for implementation..

Some activities until the first half of 2006 are:

- Ha Noi Capital Regional Planning

- Methodology in the 5-year plan making of the sectors and localities

- Urban administration reform through the water sector reform

- Revision of the Urban Development Strategy of Viet Nam

- Review of experiences and lessons from the practice of CDS and urban upgrading implementation in some cities of Viet Nam

- Regional planning of HCM City

- Training on the management and development of urban technical  infrastructure

- Building up of the initial information database

- Policy dialog

c. Principles and Operational Mechanism of VUF

VUF is operating based on the commitments of its members to support the course of urban development in Viet Nam. The members benefit from activities of the Forum, thus define their roles and contributions to the Forum..

MOC is the coordinating agency of the VUF, providing initial material basis for the Forum, including an office room at the Ministry's compound and staff working part-time for the Forum.

The Swiss Development Cooperation Agency (SDC) has provided working equipment for the Forum's office, including tables, chairs, cabinets, computer, printer, telephone, fax . . . for the immediate operation of the Forum.

At the Executive Board meeting of the VUF, there will be general direction of action identified for the Forum, as well as main activities in the next 6 months. These activities will be committed on by the members to be supported and realized. At first, the activities of the Forum still have ad hoc characteristic and satisfy immediate goals such as presentations, workshops, policy dialogs, exchanges of experience and lessons . . .

Later, if the financial condition allows, the Forum will have more long term and strategic activities, such as, studies in topics, policy formulation, information database, dissemination, awareness campaign, capacity building etc.

Legal PARTNERSHIP

Partnership Update, December 2005

Approval of Strategy for the Development and Improvement of Vietnam's Legal System to the Year 2010 and Direction for the Period up to 2020(LSDS)

The LSDS, flowed from the Legal Needs Assessment process conducted from 2000, was approved by the Polit Bureau on 24 May 2005 after more than one year of preparation. The Government is assigned to prepare an Action Plan to implement the LSDS and this Action Plan will be finalised soon. Following are key issues of the LSDS:

The objectives, baseline standpoints for development and improvement of the legal system emphasize to develop and improve a consistent, comprehensive, feasible, transparent legal system with focus on the perfection of the legal institutions of the socialist oriented market economy, on building the Vietnam rule-of-law socialist state which is of the people, by the people and for the people; on basic renovation of law making and implementing mechanism; on acceleration of role and effectiveness of the law to contribute to the good social management, maintaining political stability, developing national economy, international integration, building of a clean and strong state, implementing human rights and democratic rights, freedoms of the citizen and make Vietnam a modern, industrialized country in 2020.

The LSDS will contribute, inter alia, to ensure the human rights, democratic rights and freedoms of the citizen; build the socialist oriented market economy, develop culture and society, maintain the national defense and public order; combine the actual circumstance of Vietnam with selectively adopted international experience on law making and implementation; harmoniously combine national fine culture values and traditions with modern characteristics of the legal system; bring into play democracy, accelerate legality during the development, improvement and implementation of law. The LSDS will be carried out in line with the administrative reform, judicial reform by firm steps and with the focus; pay special attention on quantity and quality; fully diagnose pre-conditions to ensure effectiveness and enforceability of the law.

Approval of Judicial Reform Strategy (JRS)

On the 2nd of June, the Polit-bureau issued a Resolution on Judicial Reform Strategy to 2020. The key issues of this Strategy are reform of judicial system.

The following are the key directions set out by the Strategy:

1.1. Improving criminal and civil policy and legislation in line with the socialist-oriented market economy; building Vietnam’s socialist rule-of-law State of the people, by the people, and for the people; improving judicial procedures to ensure that they will be consistent, democratic, and transparent, as well as respect and protect human rights.

1.2. Organising judicial organs and judicial support institutions in a proper and scientific manner, with modern organisational structures and working conditions/facilities, of which the court sector is placed at the centre and adjudication plays the key role; realising strong socialisation of judicial support activities.

1.3. Building a strong contingent of judicial and support staff, especially officials holding judicial posts, by enhancing their legal responsibility and authority, as well as by introducing higher specialised standards for each category of staff: for example, political and ethical qualities, professional and technical capacity, as well as social knowledge and experience; and adopting a mechanism for recruiting and appointing officials for some judicial posts through examinations.

1.4. Renovating and enhancing the oversight role of elected bodies, the public, and the people’s ownership of judicial activities.

Legal System Development Facility

The Rules on LSDF was signed by Prime Minister Phan Van Khai on 21 June 2005 (Decision number 153/2005/QĐ-TTg).

Key objectives of the LSDF are as follow:

- Mobilise financial resources from donors to support the implementation of the LSDS

- Provide financial support to priority activities and emerging needs identified during the implementation of the LSDS

The Facility is unique in the sense that it is open to all donor agencies and can be continuously replenished up to a ceiling amount of US$ 3 million. In addition,the Prime Minister has delegated the authority to the Minister of Justice to take decisions on particular initiatives to be funded by the Facility. Apart from activities related to the overall management and implementation of the LSDS, priority will be given to:

- Pilot projects to strengthen the law enforcement capacity of law enforcement agencies at both central and local levels

Legal information and dissemination to enhance legal awareness and knowledge of grassroots officials and local people, especially people living in rural, mountainous, remote or isolated areas or islands

- Education and training of a body of leading legal specialists capable of development of the legal system and enforcing the laws and regulations defined in the LSDS

The Facility will form an integral part of project VIE/02/015 “Assistance to Implementation of Vietnam’s Legal System Development Strategy to 2010”, funded by UNDP, Sweden and Denmark

Legal Partnership Forum (LSF), Da Nang 11-12 October, 2005.

The LPF involved the participation from both government and donor counterparts is to promote discussion, co-ordination, and strategizing between Vietnamese agencies, as well as foreign partners, in order to further development and improvement of Vietnam’s legal and judicial systems.

The main issues discussed at the LPF were as follows:

- Priorities/trends in the recently adopted Legal System Development Strategy;

- Priorities/trends in the recently adopted Judicial Reform Strategy;

- Recent legal reform for the rule of law and access to justice.

Monthly Donor Group Forums on the Legal System Development Strategy and Judicial Reform Strategy

On 6 September 2005 Minister of Justice participated in a Donor Forum organized by UNDP to present key issues of the LSDS. On 7 October, a Vice Chairman of the Central Committee for Internal Affairs also joined the similar event to share the key contents of the Judicial Reform Strategy with the donor community. These two important strategies have been translated into English and shared with the donor community by UNDP and/oh behalf of the government counterparts.

Informal Monthly Coordination Lunch

During the reporting year, JOPSO has coordinated the gatherings at the Press Club every months where technical advisors and experts working for the legal related projects and representatives from donors could share information on their on-going activities and supports in the legal related areas.

THE MATRIX ON ON-GOING DONOR-GOVERNMENT COORPERATION IN THE LEGAL SECTOR

(Update in November 2005)

Based on inputs from various donors and Vietnamese agencies, this matrix is an update of international assistance in the legal and judicial sectors. The matrix is divided into five parts:

- Support for implementation of the Strategy for Development and Improvement of Vietnam’s Legal System to 2010, and Direction up to the year 2020 (LSDS) and co-ordination of international co-operation in the legal and judicial sectors;

- Legislative support;

- Institution-building and law implementation/enforcement;

- Capacity-strengthening; and

- Access to Justice.

Your comments or information to improve and complete this matrix are highly appreciated. Information or queries should be sent to: vie02015.vn@undp.org

| Area of support | Key Objectives, Activities | Vietnamese Implementing Agencies and Donors | Name, address, tel/fax and email of contact persons |
| --- | --- | --- | --- |
| Support for LSDS Implementation and Coordination of International Co-operation in the Legal and Judicial Sectors |  |  |  |
|  | Strengthen the Management Capacity for the LSDS implementation: - Assist for establishment of a Steering Committee and Secretariat to implement the LSDS - Assist for establishment of a coordination mechanism between Vietnamese agencies and relevant donors, as well as databases on donor funded projects in the legal and judicial sectors - Assist for establishment of a multi-donor facility | MOJ, MPS, CPIAC, SPC, GI, VLA, some local Departments of Justice - UNDP/ Sida/ DANIDA/ WB/ ADB (VIE/02/015 project (Ongoing project): 2003-2007) | 1. Mr. Le Thanh Long, Project Manager tel: 7336722. Fax: 7340104 lethanhlong250@yahoo.ca, vie02015.vn@undp.org 2. Mr. Luu Tien Dung, Program Officer, UNDP tel: 9421495/ext.103 email: luu.tien.dung@undp.org 3. Mr. Vu Tuan Minh, Program Officer, Sida tel: 7260402 email: mr.minh@sida.se 4. Ms. Charlotte Laursen, Counselor Development, Embassy of Denmark (DANIDA) tel: 8231888 chalau@um.dk |
| Legislative Support |  |  |  |
| Strengthening legislative drafting process | Strengthen capacity of reviewing constitutionality, legality and consistency of normative legal documents through: Assist to draft Law on Promulgation of Legal Normative Documents (at Central and local levels) and drafting LNDs to implement the two laws | - MOJ - UNDP/ Sida/ DANIDA (VIE/02/015 project) - MOJ - USAID (STAR project (Ongoing project): 2002-2005) | 1. Mr. Le Thanh Long, Project Manager tel: 7336722. Fax: 7340104 email: lethanhlong250@yahoo.ca, vie02015.vn@undp.org 2. Mr. Luu Tien Dung, Program Officer, UNDP tel: 9421495/ext.103 email: luu.tien.dung@undp.org 3. Mr. Vu Tuan Minh, Program Officer, Sida tel: 7260402 email: mr.minh@sida.se 4. Ms. Charlotte Laursen, Counsellor Development, Embassy of Denmark (DANIDA) tel: 8231888 email: chalau@um.dk 5. Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
|  | Assist to carry out the tasks of reviewing and examining LNDs in accordance with PM’s Directive No. 10/2002/CT-TTg of 19 March 2002 | MOJ - UNDP/ Sida/ DANIDA (VIE/02/015 project ) | 1. Mr. Le Thanh Long, Project Manager tel: 7336722. Fax: 7340104 email: lethanhlong250@yahoo.ca, vie02015.vn@undp.org 2. Mr. Luu Tien Dung, Program Officer, UNDP tel: 9421495/ext.103 luu.tien.dung@undp.org 3. Mr. Vu Tuan Minh, Program Officer, Sida tel: 7260402 email: mr.minh@sida.se 4. Ms. Charlotte Laursen, Counsellor Development, Embassy of Denmark tel: 8231888 email: chalau@um.dk |
|  | Strengthen the NA and ONA participation in the legislative process (study tours on specific laws, comparative studies, workshops, internships etc.) | ONA – DANIDA - UNDP Ongoing project: - 2005 | 1. Ms. Charlotte Laursen, Counsellor Development, Embassy of Denmark tel: 8231888 email: chalau@um.dk |
|  | Support legislative drafting and review process | NA (Law Committee and Committee for Social Affairs) – CIDA (PIAP) Ongoing project: | Ms. Vu Thi Yen Programme Officer, CIDA Tel: 7345000 Vu.YenThi@international.gc.ca Mr. Michael McCabe Tel: 9331800 email: mmccabe@piap.org.vn |
|  | Support for legal drafting skills under a Public Administrative Reform | MARD – UNDP (Project VIE/02/016: Project Support to Public Administration Reform Programme in MARD) Ongoing project | 1. Mr. Nguyen Tien Dung, Program Officer, UNDP 9421495/248 nguyen.tien.dung@undp.org 2. Mr. Dao Viet Dung, Program Officer, ADB email: 9346600/ 327 email: dvdung@adb.org 3. Mr. Nguyen Van Diem, MoHA Tel: 0913212893 email: htqt@fpt.org |
|  | Strengthen law drafting and reviewing by: - Building case scenarios of future impact of WTO rules in national legislation using a comparative law approach and regional experiences of recent accessions; - Developing a WTO check-list for review of current and future legislative initiative; - Building of a framework to prepare gradually to proceed to the implementation of WTO rules in national legislation; Drafting, amendments and supplementation of current and future legislations and/or legal normative instruments. | MOJ - CIDA (LERAP) | 1. Ms. Vu Thi Yen, Programme Officer, CIDA Tel: 7345000 Vu.YenThi@international.gc.ca 2. Mr. Isabeau Vilandré, Lawyer Tel: 84-4 9436695/6. MB: 0904 172 387 Fax: 84-4 943 6694 e-mail:lerap@fastmail.fm 3. Mr. Nguyen Khanh Ngoc Deputy Director, International Law Dept. Ministry of Justice Tel: 7334302 email: khanhngocn@yahoo.com |
|  | Increase capacity to undertake comparative law analysis in order to improve law drafting and research | MOJ - CIDA (LERAP) | 1. Ms. Vu Thi Yen, Programme Officer, CIDA Tel: 7345000 Vu.YenThi@international.gc.ca 2. Mr. Isabeau Vilandré, Lawyer Tel: 84-4 9436695/6. MB: 0904 172 387 Fax: 84-4 943 6694 e-mail:lerap@fastmail.fm 3. Mr. Cao Xuan Phong Deputy Director, Legal Comperative Law Center, Institute of Law Science, MOJ Tel: 8430934 email: phongcx@fpt.vn |
| Legislative support for implementation of BTA and WTO accession | Support for developing a follow-on Roadmap for changes to laws, regulations, and procedures needed to implement the BTA and to accede to WTO | MOJ/NA (CEBA and Committee on Foreign Relations) USAID (STAR PROJECT) | 1. Mr. Hoang Phuoc Hiep – Director , Department of International Law, MOJ Tel. 8431386/7340982 Fax 8431431 hiephp@moj.gov.vn 2. Mr. John Bentley, Chief Legal Advisor, STAR Project Tel: 9349814 email: johnbentley@fpt.vn |
|  | Create a legal environment for implementation of the BTA and accession to WTO This involves supporting legal reforms in almost all key economic and commercial sectors, as well as advancing the procedures and capacity of the courts to resolve commercial, IPR and investment disputes. | 36 government and state agencies at the national level, and 10 provincial/ city governments USAID (STAR PROJECT) | Mr. Steve Parker, Director, STAR Project Tel: 9349814 |
|  | Strengthen the capacity of the government of Vietnam and Vietnamese stakeholders for managing WTO accession and meet their commitments and challenges from other international and regional trade related agreements. | Ministry of Trade, Ministry of Justice, Office of the National Assembly Multilateral Trade Assistance Project Vietnam II (MUTRAP II) ASIE/2003/005711 On-going: (10/1/2005 – 30/6/2008) MOT-EU | MUTRAP II Project Task Force Suite A201 Ham Long Building,14-16 Ham Long Str. ,Hanoi Tel. 9454314/15 Fax 9454311 mutrap@mutrap.org.vn Mrs. Tran Thi Thu Hang- Project Director Mr. Peter Naray –European Technical Assistance Team Leader Tel: 9454316 peter_naray@mutrap.netnam.vn Mrs Vu Thi Tuan Anh- Programme Officer, EC Delegation Hanoi Tel. 9341300-Ext. 8217 E-mail: Anh.VU@cec.eu.int |
|  | Review available instruments of trade defence in light of Vietnam’s WTO rights and obligations | MOT-EU (MUTRAP II) | MUTRAP II Project Task Force Suite A201 Ham Long Building,14-16 Ham Long Str. ,Hanoi Tel. 9454314/15 Fax 9454311 E-mail: mutrap@mutrap.org.vn Mrs. Tran Thi Thu Hang- Project Director |
|  | - Support for the National Assembly and Ministry of Justice in developing a Legislative Action Plan for WTO Accession (Technical Assistance) - Continue to implement the previous results of Legislative Action Plan for WTO Accession (in preparation) | NA / MOJ - WB MOJ/WB | 1. Mr. Pham Minh Duc, Senior Economist, WB 2. Mr. Ngo Duc Manh - Director of Information Center, ONA Tel: 08043590 Email: ngoducmanh@yahoo.com 3. Mr. Nguyen Khanh Ngoc – Deputy Director Tel/ Fax: 7334302 khanhngoc_n@yahoo.com 4. Mr. Cao Xuan Phong, Deputy Director, Legal Comperative Law Center, Institute of Law Science, MOJ Tel: 8430934 |
|  | Develop legal and institutional framework to deal with anti-dumping measures taken against Vietnam and against foreign products in Vietnam | MOT - CEG Facility (AusAID) | Mr. Graham Alliband, CEG Facility Manager tel: 936 0290 fax 936 0289 Galliband@ceg.edu.vn |
|  | Assist to study on laws necessary for economic integration (study of various laws to be reformed in line with WTO accession) | MOJ - JICA/LCP | Mr. Sasaki, Naoshi JICA Project email: naoshi0@aol.com |
|  | Assist for Amendments of Law on Credit Institutions (completed) | SBV -– CIDA | 1. Ms. Vu Thi Yen, Programme Officer, CIDA Tel: 7345000 Vu.YenThi@international.gc.ca |
|  | Assist for Amendments of the Law on Credit Institutions | SBV/ NA (CEBA) - USAID (STAR PROJECT) | Mr. John Bentley, Chief Legal Advisor, STAR Project Tel: 9349814 email: johnbentley@fpt.vn |
|  | Post-WTO accession: Facilitate the implementation of Vietnam’s commitments for its WTO accession: - Monitoring legislative review of initiatives undertaken and adoption of legislations and/or legal normative instrument to comply with WTO requirements; - Building reviewing instruments to help harmonize legislations and normative instruments to further integrate WTO and economic integration mechanism in national legal instruments (national/provincial levels, sartorial levels). New approach: The assistance will be linked to day to day working plan and focus on local level | MOJ - CIDA (LERAP) Ongoing project: 2001-2007 | 1. Ms. Vu Thi Yen, Programme Officer, CIDA Tel: 7345000 Vu.YenThi@international.gc.ca 2. Mr. Isabeau Vilandré, Lawyer Tel: 84-4 9436695/6. MB: 0904 172 387 Fax: 84-4 943 6694 e-mail:lerap@fastmail.fm 3. Mr. Nguyen Khanh Ngoc Deputy Director, International Law Dept. Ministry of Justice Tel: 7334302 email: khanhngocn@yahoo.com |
| Support for drafting of specific laws and regulations | Assist for Revision of the Commercial Law and drafting regulations to implement the Commercial law | MOT – CEBA (NA) USAID (STAR PROJECT), UNDP, CEG Facility (AusAID), France | Mr. Graham Alliband CEG Facility Manager Tel: 936 0290 fax 936 0289 Galliband@ceg.edu.vn |
|  | Assist for Drafting LNDs to implement Competition Law | MOT – CIDA (PIAP) | 1. Ms. Vu Thi Yen, Programme Officer, CIDA Tel: 7345000 Vu.YenThi@international.gc.ca 2. Mr. Micheal McGabe Tel: 9331800 email: mmccabe@piap.org.vn |
|  | Assist for Revision of Civil Code | MOJ - JICA/LCP Law Committee of the National Assembly – USAID (STAR PROJECT) | 1. Mr. Morinaga Taro, Chief Advisor JICA Project Tel: 04-9-426-558 (Office) 095-335-7315 (Mobile) Fax: 04-9-426-561 email: tkmorinaga@fpt.vn 2. Mr. John Bentley, Chief Legal Advisor, STAR Project Tel: 9349814 email: johnbentley@fpt.vn |
|  | Assist for Drafting the new Civil Procedure Code | SPC/NA (Law Committee) - JICA/LCP USAID (STAR PROJECT) | 1. Mr. Ngo Cuong, SPC Tel: 9343168 2. Mr. Morinaga Taro tkmorinaga@fpt.vn 3. Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
|  | Assist for drafting LNDs to implement the Civil Procedure Code | SPC - USAID (STAR PROJECT) | 1. Mr. Ngo Cuong, SPC Tel: 9343168 2. Mr. John Bentley, Chief Legal Advisor, STAR Project Tel: 9349814 johnbentley@fpt.vn |
|  | Assist for drafting Ordinance on Legal Aid | MOJ – VIE.02.015 (UNDP/Sida/DANIDA) | 1. Mr. Le Thanh Long, Project Manager tel: 7336722. Fax: 7340104 email: lethanhlong250@yahoo.ca, vie02015.vn@undp.org 2. Mr. Luu Tien Dung, Program Officer, UNDP tel: 9421495/ext.103 luu.tien.dung@undp.org 3. Mrs. Ta Thi Minh Ly, Director of the National Legal Aid Agency tel: 8431389, fax: 7333153 tathiminhly@fpt.vn |
|  | Assist for drafting the Enterprise Bankruptcy Code | SPC - JICA/LCP | 1. Mr. Morinaga Taro, JICA Project email: tkmorinaga@fpt.vn 2. Mr. Ngo Cuong, SPC Tel: 9343168 |
|  | Assist for drafting the Ordinance on Secured Transactions | MOJ – JICA/LCP / ADB | 1. Mrs. Nguyen Thuy Hien, Director, National Agency for Registration of Secured Transactions Tel: 7334160 2. Mr. Sasaki, Naoshi JICA Project email: naoshi0@aol.com 3. Mr. Shinsuke Kawazu, ADB skawazu@adb.org |
|  | Assist for drafting the Immovable Property Registration Law | MOJ – JICA/LCP | 1. Mr. Sasaki, Naoshi JICA Project email: naoshi0@aol.com |
|  | Assist for drafting the Judgment Execution Code | MOJ/NA (Law Committee) - JICA/ USAID (STAR PROJECT)/ VIE.02.015 (UNDP-Sida-DANIDA) | 1. Mr. Nguyen Binh, Deputy Director of Civil and Economic Legislation Dept., MOJ tel: 8438836 2. Mr. Morinaga Taro, JICA Project Tel: 04-9-426-558 (Office) 095-335-7315 (Mobile) Fax: 04-9-426-561 email: tkmorinaga@fpt.vn 3. Mr. Le Thanh Long, Project Manager VIE/02/015 tel: 7336722. Fax: 7340104 email: lethanhlong250@yahoo.ca, vie02015.vn@undp.org |
|  | Assist for drafting the State Compensation Law | MOJ – JICA/LCP | Mr Morinaga Taro, Legal Expert, JICA Project Tel: 04-9-426-558 (Office) 095-335-7315 (Mobile) Fax: 04-9-426-561 email: tkmorinaga@fpt.vn |
|  | Assist for drafting new comprehensive IP Law, Technology Transfer and Standardizations | MOST/ MCI/NA (S&T Committee) - USAID (STAR PROJECT) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
|  | Assist for drafting Law on Negotiable Instruments | NA (CEBA)SBV - USAID (STAR PROJECT) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
|  | -Assist for drafting, reviewing and approving the Audit Law -Assist in reviewing two-year implementation of the state budget law and related legal implementation documents (such as Decree 73 on local budgeting) involving state management agencies and spending units at local level. -Assist in reviewing two-year implementation of the National Assembly’s Ordinance on formulation, examination and decision of state budget | CEBA-UNDP-DFID-CIDA project (VIE/02/008) | 1. Mr. Trinh Tien Dung, ARR/Programme Officer, trinh.tien.dung@undp.org 2. Mr. Nguyen Hoang Anh, National Project Manager, CEBA vie02008.vn@undp.org |
|  | Assist in drafting a revised decree (to replace the old decree no. 90) managing external debt management | MOF-UNDP – AusAID-Seco project (VIE/01/010) | 1. Mrs. Truong Thai Phuong, Deputy NPD, MOF truong.thai.Phuong@mof.gov.vn 2. Mr. Trinh Tien Dung, ARR/Programme Officer, trinh.tien.dung@undp.org |
|  | Assist for study on public finance reform: import-export taxation, income tax, value added tax | MOF- France |  |
|  | Assist for drafting Personal Income Tax Law | MOFI – UNDP (Project VIE.03.010) | Ms. Nguyen Thi Thanh Nga, Program Officer UNDP email: nguyen.thi.thanh.nga@undp.org |
|  | Assist for research for amendment of Custom laws and regulations to meet with requirement of Kyoto Convention | MOF – DHRD (Japan) |  |
|  | Assist for drafting of government regulations on business registration and licenses to effectively implement the Enterprise Law | CIEM- UNDP | Ms. Do Thi Nguyet Nga,Programm Officer, UNDP Email: do.thi.nguyet.nga@undp.org |
|  | Assist for drafting of Common Investment Law and Unified Enterprise Law | MPI /CIEM/UNDP PMRC – USAID (STAR Project) | Ms. Do Thi Nguyet Nga, Programme Officer, UNDP Email: do.thi.nguyet.nga@undp.org |
|  | Assist for drafting of regulations on customs valuation, classification, post-entry audit and border measures for IPR enforcement; amendment to the Customs Law | MOF (Customs Department) - USAID (STAR Project) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
|  | Assist for drafting of Ordinance on Procedures for Administrative Cases | SPC - USAID (STAR Project) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
|  | Assist for amending Law on Complaints and Denunciations | GI/IAC - VIE.02.015 (UNDP/Sida/DANIDA) / USAID (STAR Project) | 1. Mr. Le Thanh Long, Project Manager tel: 7336722. Fax: 7340104 email: lethanhlong250@yahoo.ca, vie02015.vn@undp.org 2. Mr. Luu Tien Dung, Program Officer, UNDP tel: 9421495/ext.103 email: luu.tien.dung@undp.org |
|  | Assist for drafting of Law on Referendum – research international experience and assessment of relevant existing Vietnamese LNDs | VLA – VIE.02.015 (UNDP/Sida/DANIDA) | 1. Mr. Pham Quoc Anh, President, VLA 2. Mr. Le Thanh Long, Project VIE/02/015 Manager 3. Mr. Luu Tien Dung, UNDP Program Officer |
|  | Assist for drafting of Law on Electronic Transactions | NA (Science & Technology Committee) - USAID (STAR Project)/ ADB | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 email: johnbentley@fpt.vn |
|  | Assist for drafting of Law on Concluding and Implementing International Treaties | MOFA/NA (Committee on Foreign Relations) - VIE/02/015 - USAID (STAR Project) | 1. Mr. Le Thanh Long, Project Manager tel: 7336722. Fax: 7340104 lethanhlong250@yahoo.ca,vie02015.vn@undp.org 2. Mr. Luu Tien Dung, Program Officer, UNDP tel: 9421495/ext.103 luu.tien.dung@undp.org |
|  | Assist for drafting of Tourism Law and LNDs to implement Tourism Law | General Administration of Tourism – SNV (Netherlands) |  |
|  | Assist for drafting of Amendment of the Law on Local Election and the Law on Organization of People’s Councils and Committees | ONA – UNDP |  |
|  | Support for drafting and finalizing a government decree on delegation of responsibilities in state management to local governments in order to assist the Decentralization of state financial management | MOF - UNDP |  |
|  | Support for review and improvement of a government regulation of local investment and development funds | MOF - UNDP |  |
|  | Assist for drafting of Law on compulsory purchase and requisition by providing comparative experiences | MOF - UNDP |  |
|  | Support for the implementation of the revised decree 10 aiming at mitigating negative impact of the socialization on the poor | MOF- UNDP |  |
|  | Assist for drafting of laws and regulations on human trafficking, smuggling of migrants and transnational organized crime in order to enable VN to ratify the UN Convention on Transnational Organized Crime and its protocols | MOJ - UNODC | Mr. Nguyen Cong Hong, Deputy Director, Criminal and Administrative Legislation Department, MOJ Tel: 7335117 |
|  | Support revision and implementation of law related to court procedure to support a speedy introduction of the adversarial system in Vietnam | SPC – DANIDA/ UNDP/Sida/DANIDA (Project VIE.02.015) | 1. Mr. Le Thanh Long, Project Manager tel: 7336722. Fax: 7340104 lethanhlong250@yahoo.ca, vie02015.vn@undp.org 2. Mr. Luu Tien Dung, Program Officer, UNDP tel: 9421495/ext.103 luu.tien.dung@undp.org |
|  | Support revision and implementation of law on administrative procedure - to increase capacity to deal with administrative cases | SPC – DANIDA MOJ – UNDP/Sida/DANIDA (Project VIE.02.015) | 1. Mr. Le Thanh Long, Project Manager tel: 7336722. Fax: 7340104 lethanhlong250@yahoo.ca, vie02015.vn@undp.org 2. Mr. Luu Tien Dung, Program Officer, UNDP tel: 9421495/ext.103 email: luu.tien.dung@undp.org |
|  | Assist for drafting of LNDs to implement Land Law 2003 | MONRE – Sida (SEMLA program) |  |
|  | Assist for drafting of Law on Environment Protection (Amended) and implementing LNDs | MONRE – Sida (SEMLA program)/ UNDP–Poverty and Environment Project and UNDP-Agenda 21- VIE/01/021 | Mr. Dao Xuan Lai, Programme Officer, UNDP. Email: dao.xuan.lai@undp.org |
|  | Assist for drafting of Law on Biological Diversity | UNDP – Poverty and Environment Project | Mr. Dao Xuan Lai Programme Officer, UNDP. Email: dao.xuan.lai@undp.org |
|  | Assist for drafting of Law on Nuclear | MOST - JICA, KOICA, France, IAEA |  |
|  | Assist for drafting of Law on Information Technology | Ministry of Telecommunication - KOICA |  |
|  | Assist for drafting of Law on protection of public healh | MOH – WHO |  |
|  | Assist for drafting of Ordinance and decrees on grant and transplant tissue and organ | MOH – WHO |  |
|  | Assist for drafting of Law on Anti-corruption and ratification of UN Convention on anti-corruption | GI – UNDP, Sida | 1. Mr. Nguyen Van Thanh, Director of the Institute for Inspection Research, GI Tel: 0904295999 2. Mr.Luu Tien Dung, Programme Officer UNDP luu.tien.dung@undp.org; 3. Mr. Ngoc, Sida |
|  | Assist for Consolidation of Decrees on Securities and Development of a new Securities Law | SSC/NA (CEBA) - USAID (STAR Project) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
|  | Support for drafting and implementing National Strategy on Forestry | MARD – Netherlands, Finland, Swizerland, Sweden and other 24 donors |  |
|  | Support for amending Law and LNDs to implement Law on on Forest Protection and Development | MARD - Trust Funds for Forestry (TFF) and FSDP |  |
|  | Assist to draft some legal normative documents under the framework of Public Administrative Reform Project | MARD – GTZ (REFAS) |  |
|  | Support for drafting of Law on Gender Equality | Vietnam Woman’s Union (VWU)- ADB (financed by the Poverty Reduction Cooperation Fund) TA No. 4453 VIE: Supporting the Preparation of the Law on Gender Equality (implementation period from 2005 to 2007) | 1. Mme. Nguyen Thanh Hoa, TA Director tel: 971 8324 fax: 971 3143 2. Ms. Le Thi Ngan Giang, Deputy Director, Law and Policy Department, VWU giangltng@yahoo.com banlpcs@yahoo.com 3. Ms. Nguyen Nhat Tuyen, Social Development and Gender Officer, ADB VRM tel: 933 1374 email: nguyentuyen@adb.org |
|  | Assist for drafting of new Education Law | MoET-EC | 1. Mr.Pham Do Nhat Tien-Former Project Director, Assistant to Minister of Education, MoET 49-Dai Co Viet Str., Hanoi Tel: 8.694794, 8.694911 2. Ms. Nguyen Lam Giang, Programme Officer, European Commission Tel: 9341300/Ext.8269 giang.nguyen@cec.eu.int |
|  | Support for drafting process of the Viet Nam Youth Law and its Guidance Decree | UN Youth Task Force - National Committee on Youth of Vietnam – ILO - UNICEF |  |
| Support for research on child protection issues including assessment of legal gaps | Legal Assessment on Child Abuse | CPFC - UNICEF | 1. Mr. Vu Ngoc Binh, Project Officer for Rights Promotion UNICEF Viet Nam Tel: (+844) 942-5706 (Ext. 256) (+844) 942-5705 Mobile: 0913579640 Email: vnbinh@unicef.org |
|  | Legal Review on Children Affected by HIV/AIDS | MOLISA - UNICEF |  |
|  | Legal Review on Trafficking | MoJ with UNODC and UNICEF |  |
|  | Situation Analysis on Juvenile Justice | MoJ (Law Research Institute) and UNICEF |  |
|  | Assessments of the Juvenile Justice Situation in Hai Phong | CPFC; CPFC Hai Phong and UNICEF |  |
|  | Situation Analysis on Children Affected by HIV/AIDS | MOLISA - UNICEF |  |
|  | Situation Analysis on Children with Disabilities | MOLISA - UNICEF |  |
|  | Surveys in 3 Regions on Trafficking in Children and Women | MPS - UNICEF |  |
|  | Situation Analysis on social work to make recommendations for social work in VietNam including legal review | MOET - CPFC; MOET - UNICEF |  |
|  | Assessment on the Court System for Children | SPC - UNICEF |  |
| Support for drafting of specific laws, decrees; National Program of Action and glossary applicable to children and youth | Support for revision of the Law on Protection, Care and Education and development of its decrees and circulars | CPFC - UNICEF |  |
|  | Provision of comments for the Draft Law on HIV/AIDS | UNDP: UNAIDS; UNICEF; UNIFEM; Policy Project (USAIDS) |  |
|  | Support for the Draft Law on Youth and its decree | Youth Union - UNICEF |  |
|  | Support for the Draft Law on Education and its decrees, ministerial decisions and circulars | MOET - UNICEF |  |
|  | Support for the revision of the governmental decree on breast feeding | MOH - UNICEF |  |
|  | Support for drafting the National Strategy on Children Protection 2006-2010 with a vision to 2020 | CPFC - UNICEF |  |
|  | Support for drafting the National Program of Action (NPA) on Trafficking 2004-2010 | MPS -UNICEF and other agencies |  |
|  | Support for drafting the National Program on Community Based for Children in Especially Difficult Circumstances (CEDC) 2005-2010 | MOLISA - UNICEF |  |
|  | Support for drafting specific guidelines on community based care for CEDC, including social houses | MOLISA - UNICEF |  |
|  | Support for drafting the Glossary on Juvenile Justice | MoJ and UNICEF |  |
|  | Support for drafting the Lexicon on child abuse | CPFC - UNICEF |  |
|  | Support for drafting the National Strategy on Family | CPFC - UNICEF |  |
|  | Support for issuance of the code on social work | MOET - UNICEF |  |
|  | Provision of comments for the Draft Law on Prostitution | MOLISA - UNICEF and other agencies |  |
|  | Support for the Draft on Socio Economic Development Plan | CPFC - MPI - UNICEF |  |
|  | Program no. 135 |  |  |
|  | Plan to review the laws and policies on street children in order to develop a national strategy on street children | CPFC - MOLISA - UNICEF |  |
| Institutional Building |  |  |  |
| Strengthening parliamentary supervision | Enhance the oversight function of the National Assembly strengthening parliamentary supervision knowledge and skills of Parliamentarians and staff; Enhancing the parliamentary public information to ensure transparent, participative and democratic processes; Enhancing the internal information services of the Office of Vietnam National Assembly (ONA) to support Parliamentarians. | ONA - Sida | Mr. Vu Tuan Minh, Program Officer, Sida Tel: 7260402 email: mr.minh@sida.se |
| Institutional Support Programme (ISP) for Vietnam | Institutional support to the legislative and legal/judicial sectors in Vietnam pertaining to integration issues including a) policy advice and institutional support and b) capacity building and training. | MOJ, ONA, SPC, SPP - EC (in preparation) | 1. Mr. Phung Van Hung, Deputy Director, Information Center, ONA tel: 08046763/ 0903422725 email: hungpv@qh.gov.vn 2. Mrs. Nguyen Bich Ngoc, Senior Legal Official, International Cooperation Dept., MOJ Tel: 7333150 ng_bich_ngoc@yahoo.com 3. Mr. Nguyen Van Luat, Director Judicial Research Institute, SPC 4. Mrs. Vu Thi Tuan Anh, Program Officer, EC mission Tel. 9341300-Ext. 8217 Anh.VU@cec.eu.int |
| Supporting to the establishment of a Vietnam National Bar organisation | - Assess the organization, activities and autonomous capacity of the local bar associations; - Create a forum for lawyers, legal researchers, bar associations, judicial bodies and other state agencies to discuss on the role of the local bar associations in society, to suggest the requirements and necessary conditions for the establishment of the National Bar Association in Vietnam; - Complete a detail outline of project on the establishment of the Bar Associations of Vietnam. | MOJ - Sida (Preparatory project) | 1. Ms. Ha Phuong Lan, Deputy Director, International Cooperation Dept., MOJ Tel: 7340109 email: lanhp@moj.gov.vn, halan_btp@yahoo.com 2. Mr. Vu Tuan Minh, Program Officer, Sida Tel: 7260402 email: mr.minh@sida.se |
| Institutional Building for Vietnam Lawyer's Association | Fact-finding and Project Formulation | VLA - UNDP | Mr. Luu Tien Dung, Program Officer, UNDP Tel: 9421495 email: luu.tien.dung@undp.org |
| Institutional Building for Inspection at grassroots level | Strengthen Bar Associations of Vietnam: - Strengthen the professional capacity of practicing lawyers - Strengthen the normative basis for practicing lawyers - Establish an autonomous National Bar Association of Vietnam based on self-regulation and the highest degree of professional standards. - Elaborate long-term development strategy for the lawyer’s profession in Vietnam up to 2020 | MOJ - Sida | Mr. Vu Tuan Minh, Program Officer, Sida Tel: 7260402 email: mr.minh@sida.se |
|  | Conduct workshops and training courses for inspectors at grassroots level | GI – Asia Foundation |  |
|  | Support for strengthen monitoring system of CPFC inspectors | CPFC (Inspection Unit) and UNICEF |  |
|  | Plan to develop guidelines to strengthen functions of inspectors who deal with monitoring and investigation of children’s rights (especially the most vulnerable groups) at the national and sub-national levels | CPFC and UNICEF |  |
| Institutional Building for Bank for Social Policy | Develop training package; conduct training on and monitoring of the joint credit scheme with the Bank for Social Policy | VWU at central level and in project sites and UNICEF |  |
| Support for the establishment of an Agency for Criminology and Statistics | Collect, process and disseminate accurate data on crime | SPP– DANIDA | Ms. Charlotte Laursen, Counselor Development, Embassy of Denmark (DANIDA) tel: 8231888 email: chalau@um.dk |
| Support for Legal aid system | Strengthen NLAA and PLAC’s capacity to carry out legal aid, strengthen the capacity of mediation groups, lawyers, law students to carry out legal aid. | MOJ - Sida | 1. Mrs. Ta Thi Minh Ly, Director, National Legal Aid Agency Tel: 8431389, MB: 0903444108 2. Mr. Vu Tuan Minh, Program Officer, Sida Tel: 7260402 email: mr.minh@sida.se |
| Support for local justice agencies | Strengthening administrative and judicial procedures at local levels | MOJ - Sida | Mr. Vu Tuan Minh, Program Officer, Sida Tel: 7260402 email: mr.minh@sida.se |
| Support for follow up the Regional Commitments on Trafficking | Support to MPS to follow up the Regional Commitments and Plan of action on combating trafficking | MPS; other key agencies; UNICEF; UNIAP |  |
| Capacity building and law implementation/ enforcement |  |  |  |
| Strengthening the skills of the MPs as representatives of the people | - Improve general skill sets of MPs; - Improve communication with voters; - Handle of claims and petition, policy analysis, debating and presentation skills and assessment of bills. | ONA - DANIDA | Ms. Charlotte Laursen, Counselor Development, Embassy of Denmark (DANIDA) tel: 8231888 email: chalau@um.dk |
| Strengthening law making and law implementation capacity | - Support the improvement of services for the Members of the National Assembly through international and national seminars with ONA | ONA (Centre for Information, Library and Research Services) - FES | Dr Felix Schmidt, Friedrich Ebert Stiftung International P.O.Box 44, 7, Ba Huyen Thanh Quan, Hanoi, Vietnam Tel.: 8455108/8452632 Fax: 8452631 Web: www.fes-vietnam.org fesvn@netnam.vn |
|  | - Strengthen the capacity of MoJ in law making and law implementation - Strengthen law implementation ability of judges and civil executors, - Strengthen MoJ’s admin. management capacity | MOJ – Sida |  |
|  | Strengthen legal capacity and international practical experience for government officials on laws on national boundary identification | MOFA – Francophone Community of Belgium |  |
|  | Strengthen capacity to implement policy on land and environment including implement Land Law 2003 | MONRE – Sida (SEMLA program) |  |
|  | Strengthen law making and implementation on Gender Equality | Vietnam Woman’s Association – Spangenberg (USA) |  |
| Comparative law research and analysis | Developing comparative law study and analysis skills through delivering short term training courses in Canada and locally organized work shops | MOJ-CIDA (LERAP) | 1. Ms. Vu Thi Yen, Programme Officer Tel: 8235500 email: Vu.YenThi@international.gc.ca 2. Mr. Isabeau Vilandré, Lawyer Tel: 84-4 9436695/6. MB: 0904 172 387 Fax: 84-4 943 6694 e-mail:lerap@fastmail.fm 3. Mr. Cao Xuan Phong Deputy Director, Legal Comperative Law Center, Institute of Law Science, MOJ Tel: 8430934 |
| International trade dispute settlement | Improving international trade dispute settlement skills through short-term training held locally | MOJ-CIDA (LERAP) | 1. Ms. Vu Thi Yen, Programme Officer Tel: 8235500 Vu.YenThi@international.gc.ca 2. Mr. Isabeau Vilandré, Lawyer Tel: 84-4 9436695/6. MB: 0904 172 387 Fax: 84-4 943 6694 e-mail:lerap@fastmail.fm 3. Mr. Nguyen Khanh Ngoc Deputy Director, International Law Dept. Ministry of Justice Tel: 7334302 khanhngocn@yahoo.com |
| Improvement of the professional and practical skills of the judiciary in court proceedings | - Draft a Bench book for Judges (including a CD-rom) - Provide 20 two day seminars and some five day Training of Trainers Training Courses for judges at local level | SPC - CEG Facility (AusAID) | Mr. Graham Alliband, CEG Facility Manager tel: 936 0290 fax 936 0289 email Galliband@ceg.edu.vn |
| Strengthening capacity of the police force and investment agencies | Assist to enforce the Drug Law : strengthen the law enforcement efforts over trafficking in drugs | MPS - UNODC |  |
|  | Strengthen capacity of the police force in implementing the Ordinance on Dealing with Administrative Violations through support for law enforcement in dealing with administrative violations | MPS – VIE.02.015 (UNDP/Sida/DANIDA) | 1. Ms. Katrine Pedersen, Program Officer UNDP tel: 9421495 email: katrine.pedersen@undp.org 2. Mr. Luu Tien Dung, Program Officer UNDP 3. Mr. Tran Dinh Nha, Director, Legal Department, MPS tel: 0913202491 |
|  | - Enhance capacity for officials at investigation agencies in implementation of Criminal Procedure Code | MPS - DFID | Mr. Tran Dinh Nha, Director, Legal Department, MPS tel: 0913202491 |
| Registration of secured transactions | Support the capacity building and training for officials of registration agencies for secured transactions | MOJ (National Registration Agency of Secured Transactions) - ADB | 1. Mrs. Nguyen Thi Thuy Hien, Director, Director, National Agency for Registration of Secured Transactions, MOF Tel: 7334160 2. Mr. Dao Viet Dung, Governance and Public Sector Reform Officer, ADB Tel: 933 1374/ ext. 125 email: dvdung@adb.org |
| Improving capacity to enforce civil judgments | Strengthen capacity of enforcement of civil judgement enforcement law and regulation | MOJ (Civil Judgment Enforcement Agency) - CIDA (LERAP Project) | 1. Mr. Hoàng Thọ Khiêm, Director, Civil Judgement Enforcement, MOJ Tel: 8430929 2. Mr. Isabeau Vilandré, Lawyer Tel: 84-4 9436695/6. MB: 0904 172 387 Fax: 84-4 943 6694 e-mail:lerap@fastmail.fm 3. Mrs. Vu Thi Yen, Programme Officer, CIDA Tel: 7345000 Vu.YenThi@international.gc.ca |
| Strengthening the rights of Vietnamese children in conflict with the law | Support for: - Reduce crime rate of children offending or being victimized - Decrease the number of children dealt by the formal justice system (to avoid further stigmatization and victimization) - Establish child sensitive system/procedures for children (in case the child is dealt by the normal court system) - Improve prevention and reintegration/rehabilitation programmes as well as laws/policies to strengthen the rights and situation of the CICLW. | CPFC and other legal agencies - UNICEF/Sida |  |
| Improving skills of welfare and justice agencies and para-professionals on juvenile justice issues | Develop training package and conduct multi-sectoral training for law enforcers; court and procuracy officers; welfare personnel and para-professional to become master trainers on juvenile justice in particular diversion and reintegration of children in conflict with the law | CPFC; other key government agencies; UNICEF |  |
| Strengthen skills of law enforcers on child investigation | Develop training package and conduct training for MPS to become master trainers on friendly investigation for children as victims; offenders and witnesses | MPS and UNICEF |  |
| Implementation of CRC | Train children on CRC | Youth Union and UNICEF |  |
| Implementation of of Intellectual Property Rights (IPR) | Support for enhanced enforcement of Intellectual Property Rights (IPR) by the Government enforcement officials | MPS – USAID (STAR Project) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
|  | Strengthen the capacity of the Supreme People’s Court and local courts in enforcing IPR. Strengthen the awareness of and coordination within People’s Committees in Hanoi and Ho Chi Minh City on the importance and means of IPR enforcement through awareness-raising, coordination, and training workshops | SPC - USAID (STAR Project) Hanoi and HCMC PCs - USAID (STAR Project) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
|  | Strengthen the awareness of and coordination within People’s Committees in Hanoi and Ho Chi Minh City on the importance and means of IPR enforcement through awareness-raising, coordination, and training workshops. Strengthen the capacity for officials at the grass root level (the Vietnam Copyright Center) in enforcing IPR of Vietnamese artists and authors through awareness-raising workshops | Hanoi and HCMC PCs - USAID (STAR PROJECT) Vietnam Copyright Center - USAID (STAR Project) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
|  | Strengthen the capacity for officials at the grass root level (the Vietnam Copyright Center) in enforcing IPR of Vietnamese artists and authors through awareness-raising workshops | Vietnam Copyright Center - USAID (STAR Project) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
| Legal education at law universities | - Upgrade law teachers’ knowledge on teaching methods; - Train law teachers at LLM and PhD levels; - Develop Teaching curriculum; - Improve project management and international relations. | Hanoi and HCMC Law University and MOET - Sida |  |
|  | Assist to formulate and implementing a two-year bachelor course on Japanese and Vietnamese law providing a basis for research and studies on Japanese law | VNU - JICA/LCP | Mr Morinaga Taro, Legal Expert, JICA Project Tel: 04-9-426-558 (Office) 095-335-7315 (Mobile) Fax: 04-9-426-561 (Fax) email: tkmorinaga@fpt.vn |
|  | Developing long-term capacity of governmental legal staffs by funding abroad Master courses | MOJ-CIDA (LERAP) | 1. Ms. Vu Thi Yen, Programme Officer, CIDA Tel: 8235500 Vu.YenThi@international.gc.ca 2. Mr. Isabeau Vilandré, Lawyer Tel: 84-4 9436695/6. MB: 0904 172 387 Fax: 84-4 943 6694 e-mail:lerap@fastmail.fm 3. Mr. Nguyen Khanh Ngoc Deputy Director, International Law Dept. Ministry of Justice Tel: 7334302 khanhngocn@yahoo.com |
| Judicial training | - Provide written comments, seminars and study tours to Japan to assist judicial training institutions in becoming capable of developing high-caliber human resources; - Provide consultation, written comments and workshop to develop a comprehensive manual for procurators in the field of criminal investigation and criminal first instance trial. | MOJ (Judicial Academy – former LPTS) – JICA/LCP SPP – JICA/LCP | Mr Morinaga Taro, Legal Expert, JICA Project Tel: 04-9-426-558 (Office) 095-335-7315 (Mobile) Fax: 04-9-426-561 (Fax) tkmorinaga@fpt.vn |
|  | - Provide judicial professional training (judges and court staff) - support court administration and procedural reform | SPC – CIDA (in preparation) | Ms. Vu Thi Yen Programme Officer, CIDA Tel: 7345000 Vu.YenThi@international.gc.ca |
|  | - Construct mock court and develop training material; - Procure Vietnamese and international books for library; - Strengthen the capacity of the court system to move towards greater independence for the courts. | SPC - DANIDA | Ms. Charlotte Laursen, Counselor Development, Embassy of Denmark (DANIDA) tel: 8231888 email: chalau@um.dk |
|  | Increase independence of judiciary and their capacity in selected areas. | SPC - DANIDA | Ms. Charlotte Laursen, Counselor Development, Embassy of Denmark (DANIDA) tel: 8231888 email: chalau@um.dk |
|  | - Build Capacity for SPC in administrative law, court management and case management. - Procure Vietnamese and international books for library and translation of selected books | SPC - DANIDA | Ms. Charlotte Laursen, Counselor Development, Embassy of Denmark (DANIDA) tel: 8231888 email: chalau@um.dk |
|  | Train prosecutors in international and comparative law | SPP - DANIDA | Ms. Charlotte Laursen, Counselor Development, Embassy of Denmark (DANIDA) tel: 8231888 email: chalau@um.dk |
| Strengthening capacity for officials at the grass root level in law implementation | Support for strengthening legal capacity for officials in the political system at grassroots level of Lang Son province | CPIAC – UNDP/Sida/DANIDA (Project VIE/02/015) | 1. Mr. Le Thanh Long, Project Manager tel: 7336722. Fax: 7340104 lethanhlong250@yahoo.ca, vie02015.vn@undp.org 2. Mr. Luu Tien Dung, Program Officer, UNDP tel: 9421495/ext.103 email: luu.tien.dung@undp.org 3. Mr. Nguyen Dinh Luc, Director, Legal Department, CPIAC Tel: 08045143 |
|  | Strengthen capacity for legal officials at local levels through legal needs assessment and prepare legal training materials | MOJ - UNDP/Sida/DANIDA (Project VIE/02/015) | 1. Mr. Le Thanh Long, Project Manager tel: 7336722. Fax: 7340104 lethanhlong250@yahoo.ca, vie02015.vn@undp.org 2. Mr. Luu Tien Dung, Program Officer, UNDP tel: 9421495/ext.103 email: luu.tien.dung@undp.org 3. Mr. Nguyen Tat Vien, Director, Legal Dissemination Department, MOJ Tel: 8231130 |
| International economic integration | Strengthen legal capacity for international economic integration, access to WTO | MOJ - CIDA | Ms. Vu Thi Yen Programme Officer, CIDA Tel: 7345000 Vu.YenThi@international.gc.ca |
|  | Strengthen capacity to implement quarantine regulations between four countries Vietnam, Laos, Cambodia and Myanmar | MARD - Newzealand |  |
|  | Strengthen capacity for enterprises and officials on investigation and application of anti-dumping measures | MOT - CEG Facility (AusAID) | Mr. Graham Alliband, CEG Facility Manager tel: 936 0290 fax 936 0289 Galliband@ceg.edu.vn |
|  | Provide training courses for enterprises on basic knowledge on WTO requirements and integration policy of Vietnam | MOT - Italy |  |
| Strengthening the Party’s leadership and multisectoral collaboration for successful implementation of National HIV/AIDS strategy | Support for strengthening the capacity of Party Commissions at all levels to compile, issue, direct, monitor, organise and supervise the implementation of new directives, resolutions and policies relating to the control and prevention of HIV/AIDS, with a view to creating a favourable environment for the effective implementation of solutions suggested in the National HIV/AIDS strategy. | CCSE-UNDP/Sida | 1. Ms. Thanh Van, PO UNDP,25-29 Phan Boi Chau, Hanoi Tel: 942 1495 ext 150 2. Katja S Gray-HIV/AIDS Specialist UNDP,25-29 Phan Boi Chau, Hanoi Tel: 942 1495 ext.162 E-mail:katja.gray@undp.org |
| Strengthening the Leadership Role and Multisectoral Collaboration of People-elected Bodies and Government Agencies at Different Levels for the Successful Implementation of the National HIV/AIDS Strategy | ## Support people-elected bodies engaging in awareness raising activities and possess updated knowledge on HIV/AIDS prevention as well as on relevant policies and legislation Support the capacities of the National Assembly and people elected bodies at different levels for development and dissemination of resolutions, policies, laws related to HIV/AIDS prevention and control. (Please note that these are just some of the outputs for the project) | National Assembly’s Committee for Social Affairs/CCIC-UNDP/ Sida | Thanh Van, PO UNDP,25-29 Phan Boi Chau, Hanoi Tel: 942 1495 ext 150 Katja S Gray-HIV/AIDS Specialist UNDP,25-29 Phan Boi Chau, Hanoi Tel:942 1495 ext.162 E-mail:katja.gray@undp.org |
| Support for Access to Justice |  |  |  |
| Development of national legal database and legal information dissemination | Strengthen legal capacity for international economic integration, access to WTO | MOJ - CIDA | Ms. Vu Thi Yen Programme Officer, CIDA Tel: 7345000 Vu.YenThi@international.gc.ca |
|  | Strengthen capacity to implement quarantine regulations between four countries Vietnam, Laos, Cambodia and Myanmar | MOH |  |
|  | Strengthen capacity for enterprises and officials on investigation and application of anti-dumping measures | MOT - CEG Facility (AusAID) | Mr. Graham Alliband, CEG Facility Manager tel: 936 0290 fax 936 0289 Galliband@ceg.edu.vn |
|  | Provide training courses for enterprises on basic knowledge on WTO requirements and integration policy of Vietnam | MOT - Italy |  |
|  | - Support publication of court decisions (publication of two volumes of judicial decisions for the Supreme Judicial Council) - Support for establishment of a website to publish judicial decisions of the Supreme People's Court | SPC - USAID (STAR Project) SPC - EC | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
|  | Develop a Roadmap for Creating an Electronic Official Gazette to publish laws and regulations on the internet | OOG - DANIDA/ SCOG and USAID (STAR Project) | Ms. Charlotte Laursen, Counselor Development, Embassy of Denmark (DANIDA) tel: 8231888 email: chalau@um.dk |
|  | Support enhanced transparency in legislative operations of the National Assembly | ONA - USAID (STAR Project) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
|  | Support online business forum for publishing draft regulations for comments by businesses by development of a website operated by VCCI for publishing draft legal documents for public comment. | VCCI - USAID (STAR Project) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 email: johnbentley@fpt.vn |
|  | Support publication of reference materials on BTA/WTO and related legal reforms and research on economic impact of the BTA | ONA |  |
|  | Raise awareness and build support for legal changes in BTA implementation and WTO accession and the economic impact of the BTA. | NA/SPC/ MOT/IAC/ MOJ and others -USAID (STAR Project) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 email: johnbentley@fpt.vn |
|  | Better coordinate existing legal databases and make them available for public use. | MOJ - UNDP | 1. Mr. Cao Xuan Phong, Institute for Law Science, MOJ Tel: 8430934 2. Mr. Luu Tien Dung, Program Officer, UNDP 9421495/ext.103 luu.tien.dung@undp.org |
|  | - Enhance capacity of MoJ’s staff in accessing legal information in the National Legal Database - Strengthen legal dissemination - Develop a legal library | MOJ (Legal Research Institute)– Sida | 1. Mrs. Duong Thi Thanh Mai, Director of the Institute for Law Science, MOJ Tel: 8231131 2. Mr. Vu Tuan Minh, Program Officer, Sida Tel: 7260402 |
|  | Support for dissemination of Law on Conclusion and Implementation of International Treaties | MOFA – USAID (STAR Project) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 johnbentley@fpt.vn |
|  | Support for implementation of Action Plan for dissemination of state management on foreign debts (based on Decree 90) | MOF – UNDP (Project VIE/01/010) | Mr. John Bentley, Chief Legal Advisor STAR Project tel: 9349814 email: johnbentley@fpt.vn |
|  | Provide training courses on Legal dissemination skills | MARD – UNDP (project VIE/02/016) |  |
|  | Support for dissemination of Law on Tourism | General Administration of Tourism – AECI (Spain) | Mr. Nguyen Bich Van, Director, Legal Department, General Administration of Tourism |
|  | Strengthen capacity of conciliation groups and conciliators at the grassroots level | MOJ – UNDP/Sida/DANIDA (Project VIE.02.015) | 1. Mr. Le Thanh Long, Project Manager tel: 7336722. Fax: 7340104 lethanhlong250@yahoo.ca, vie02015.vn@undp.org 2. Mr. Luu Tien Dung, Program Officer, UNDP 9421495/ext.103 luu.tien.dung@undp.org 3. Mr. Vu Tuan Minh, Program Officer, Sida tel: 7260402 email: mr.minh@sida.se 4. Ms. Charlotte Laursen, Counselor Development, Embassy of Denmark (DANIDA) tel: 8231888 email: chalau@um.dk |
| Support for strengthening indicators and data system on juvenile justice | Strengthen the indicators and data system on juvenile justice through development of set of indicators; piloting; and collection of data | CPFC, other key agencies such as MPS and GSO and UNICEF |  |
|  | Support to Disseminate legal information and support local mediation | MOJ - CIDA (in preparation) | Ms. Vu Thi Yen Programme Officer, CIDA Tel: 7345000 Vu.YenThi@international.gc.ca |
| Conciliation at grassroots level | Support for dissemination of laws and regulations on national boundaries | MOFA – AusAID (Project LASRAI) |  |
| Legal Aid | Strengthen NLAA capacity to carry out legal aid, strengthen the PLAC’s capacity to carry out legal aid, strengthen the capacity of mediation groups, lawyers, law students to carry out legal aid. | MOJ - UNDP/Sida/DANIDA (Project VIE.02.015) | 1. Mr. Le Thanh Long, Project Manager tel: 7336722. Fax: 7340104 lethanhlong250@yahoo.ca, vie02015.vn@undp.org 2. Mr. Luu Tien Dung, Program Officer, UNDP 9421495/ext.103 luu.tien.dung@undp.org 3. Mr. Vu Tuan Minh, Program Officer, Sida tel: 7260402 email: mr.minh@sida.se 4. Ms. Charlotte Laursen, Counselor Development, Embassy of Denmark (DANIDA) tel: 8231888 email: chalau@um.dk |
|  | Support to National Legal Aid System and 10 PLACs in Vietnam (Phase 1) | MOJ- SDC (NLAA project) | Mrs. Ta Thi Minh Ly, Director, NLAA, MOJ Tel: 8431389 fax: 7333153 tathiminhly@fpt.vn Ms. Nguyen Thanh Giang, Program Officer SDC Tel:9346627 giang@sdc.net |
| Piloting on Juvenile Justice at sub-national level | Plan to strengthen models and services on diversion and reintegration in project sites | MPS; CPFC and UNICEF |  |
| Piloting on Child Victims and Offenders | - Support to recovery centres for child victims to trafficking - Provision assistance to trafficking victims - Strengthen community prevention on trafficking victims - Plan to support models on police investigation for child victims and child offenders | WVU and UNICEF MPS and UNICEF |  |

Abbreviations used in the Matrix

ADB: 	Asian Development Bank

AECI: 	Agencia Española de Cooperacion Internaciónal (Spanish International Cooperation Agency)

AusAID: 	Agency for International Development of Australia

CEG Facility: 	Vietnam - Australia Capacity Building for Effective Governance Facility

CEBA:  	Committee on Economy and Budget (of the National Assembly)

CIEM: 	Central Institute for Economic Management (Ministry of Planning and Investment)

CIDA: 	Canadian International Development Agency

CPFC: 	Committee for Population, Family and Children

CPIAC: 	International Affairs Committee of the Central Communist Party

DANIDA: 	Danish International Development Agency

DFID: 	United Kingdom Department for International Development

EC: 	European Commission

FES:	Friedrich Ebert Stiftung (Germany)

FTU	Hanoi Foreign Trade University

GTZ: 	Deutsche Gesellschaft für Technische Zusammenarbeit (German Tecnical Co-operation)

GI: 	Government Inspectorate

JICA/LCP: 	Japan International Cooperation Agency / Legal Cooperation Project

IAEA: 	International Atomic Energy Agency

KOICA: 	Korean International cooperation Agency

LERAP:	CIDA funded Legal Reform Assistance Project

MARD: 	Ministry of Agriculture and Rural Development

MOET: 	Ministry of Education and Training

MOJ: 	Ministry of Justice

MOT: 	Ministry of Trade

MOF: 	Ministry of Finance

MOFA: 	Ministry of Foreign Affairs

MOH: 	Ministry of Health

MONRE: 	Ministry of Natural Resource and Environment

MPS: 	Ministry of Public Security

MUTRAP II: 	Multilateral Trade Assistance Project Vietnam II

NA:  	National Assembly

NLAA:	National Legal Aid Agency

NORAD: 	Norway Agency for Development

OOG: 	Office of the Government

ONA: 	Office of National Assembly

PCs: 	People's Committee(s)

PLAC:	Provincial Legal Aid Centre

PMRC: 	Prime Minister's Research Commission

REFAS: 	Support to the Reform of the Forest Administration System

SBV: 	State Bank of Vietnam

SCOG: 	Strenghening the capacity of the Office of the Government Project

SDC: 	Swiss Agency for Development and Cooperation

SECO: 	State Secretariat for Economic Affairs of Switzerland

SEMLA program: Vietnam – Sweden Cooperation Program on Strengthening Capacity of land and environment management

Sida: 	Swedish International Development Agency

SNV: 	Netherlands-based International Development Organisation

SPC: 	Supreme People’s Court

SPP: 	Supreme People’s Procuracy

STAR: 	Support for Trade Acceleration Project, funded by USAID

SSC: 	State Securities Comission

UNDP: 	United Nations Development Programme

UNICEF: 	United Nations Children's Fund

UNODC: 	United Nations Office on Drugs and Crime

USAID: 	Agency for International Development of the United States

VCCI: 	Vietnam Chamber of Commerce and Industry

VLA: 	VIetnam Lawyers' Association

VNU: 	Vietnam National University

WB: 	World Bank

WHO: 	World Health Organisation

WTO: 	The World Trade Organisation

PARTNERSHIP DEVELOPMENT

IN PUBLIC FINANCE MANAGEMENT

PROGRESS REPORT

(Documents for the Consultative Group Meeting, December 2005)

- Background:

2005 is the first year of new support from donors in public finance management. New proposals for technical assistance to support the Public Financial Modernisation Master Programme have been continuously developed and promoted to obtain more financial resources for the country’s comprehensive financial reforms.

- Process of implementation of cooperation relationship in 2005:

The working group has increased information exchange to improve the quality of the cooperation between different stakeholders in the public financial management field. Since the end of 2004, a number of problems have been tackled and all top six components of the Public Financial Modernisation Master Programme (PFMMP) have received equal attention. Most areas have been supported by donors through the multi-donor trust fund (MDTF).

MDTF has provided a flexible tool to regulate donor support to the PFMMP and has attracted stronger interest from donors. The additional ODA amount of US$600,000 from SIDA (Sweden) and a new aid amount of 1,500,000 Euro from the European Union for the MDTF has provided it with more resources to meet the increasing demand of the ongoing reforms. At the same time, all the donors have committed themselves to provide additional financial support to the PFMMP through the MDTF.

Expenditure management: the Public Finance Management Reform Project (WB loans) has proceeded according to schedule: a service provider has been selected through the TABMIS bidding package and is pending official approval by the Government. Consultants to work on the establishment of a medium-term expenditure and medium-term fiscal framework have been recruited. Commune budget management training has been conducted throughout the country thanks to the support of the VN-German State Budget Management project and the MDTF.

Revenue management: support provided by the IMF and other donors through the MDTF to the taxation field, especially the pilottax self-assessment declaration and self-payment systemhas been widely and thoroughly conducted and resulted in a number of achievements. Detailed implementation plans for tax system reform programmes up to 2010 have been approved by the Government and implementation begun. Recently, USAID has expressed interest in Vietnam’s tax administrative reforms and the two parties have actively exchanged information on the possibility of building long-term cooperation in this field. The pre-feasibility study of the Customs Modernisation Project (with expected loans from WB) has been completed and approved by the Prime Minister and will start in early 2006;

Donors have provided support to business management through projects under the ASEM II Trust Fund (Second phase support to redundant workers; support for the resolution of non-performing debt and assets of state-owned enterprises) and the MDTF. The establishment of the State Financial Investment Corporation has also attracted attention from many donors. The project on capacity building for development of financial policy mechanisms for the private sector funded by the National Effectiveness Capacity Building Fund (CEG) of the Australian Government has been put into operation and is expected to play a very active role in supporting private sector development, improving transparency and utility of financial management policies as well as providing recommendations to improve business and financial management for the private enterprise sector.

Other areas in the PFMMP such as public asset management and price controls etc, are receiving greater funds through MDTF in comparison with those in previous years.

Following numerous discussions and exchange of views between VN and the EU, the bidding phase to select key experts for the EURO-TAPVIET II project has been completed. At present, the project is recruiting staff and initial work has been started. It is proposed that the project will be put into full operation at the end of 2005. The support to the Ministry of Finance consists of four components: (1) Financial policies and legal services (2) Taxation (3) Customs and (4) Accounting - auditing and insurance.

Within the framework of AFD and ADB loans, the Insurance Training Centre project with a total fund, according to the agreement, of US$2.7 million came into operation in January 2005. The project is proceeding on schedule.

The Vietnam Agricultural Insurance Development Project funded by the Asian Development Bank (ADB) aims to support the Ministry of Finance in studying and designing an appropriate agricultural insurance model. The project has been in operation since September 2005.

Other new projects under active preparation are: technical assistance proposals such as the feasibility study for a plan to establish a national financial statistics system; a project to support an SME guarantee fund; a project on a Master Plan for the State Treasury and a project to establish a customs statistics system. All of these are under continuing discussion with the USTDA (United States). Other projects on cooperation with UK partners on capital market and securities market development are also under discussion with the UK Embassy in Hanoi based on the outcomes of a working meeting between MoF leaders and the Mayor of London. The cooperation between the Vietnam MoF and Korea’s Ministry of Budget and Planning on state budget management  has been actively advanced. The Vietnam-German project on state budget management phase 4 will be completed in December 2005 and the two sides have exchanged ideas on the possibility of extending cooperation in this field within the framework of the Macroeconomic Support Programme for Vietnam of the German Government.

- Outcomes of the partnership in public finance management:

1. The process to speed up state budget and financial management reforms has played an important role in the economic development of the country:

1.1. To implement the reform of incentive policies with the following important objectives:

- To develop equal and non-discriminatory tax policies for all economic sectors and economic industries and ensuring tax equality among investors in each economic sector.

- To further extend tax policies to cover all activities of the economy. The tax policies should ensure the restructuring of the current revenue collection system, which means creating a shift from  indirect taxes to direct taxes.

- To reform the tax policy system and amend and provide supplements to the Law on VAT; Law on Special Sales Tax; Law on Corporate Income Tax; Ordinance on Income Tax applicable to High Income Earners etc. The new system will be gradually applied to all enterprises in all economic sectors and will contribute to the improvement of the investment environment, create favourable conditions for enterprises to increase their capital accumulation and direct investment to production and business development.

- To reform the policies on tax collection as well as budget allocation and decentralise budget management in order to motivate local government at all levels to improve budget management. To ensure that administrative procedures for tax collection and payment have been clarified and simplified and that tax management has gradually been reformed and modernised.

- To pilot tax self–assessment in one province and one city and then to apply this across the country from the beginning of 2007 in order to enhance the autonomy of citizens, increase state budget revenue and improve transparency in revenue collection.

1.2. To reform the policy on budget allocation and utilisation to strictly enforce policies on budget expenditure and abolish subsidy system, the public expenditure allocation must be kept within revenue and other financial resource availability in order to ensure its practicality and efficiency. In particular, budget expenditure should concentrate on the following priorities:

- Budget expenditure should concentrate on investments in infrastructure projects which are not for profit or repayment, especially infrastructure for remote or rural areas (such as transportation or irrigation etc.)

- Education, training and vocational training and scientific and technological development should receive priority in budget allocation whilst they continue to reform their management mechanisms. Public services such as health care, education and culture should mobilise other public resources besides their allocations from the state budget.

- The budget should be focused on hunger elimination and poverty reduction. Great importance should be attached to the construction of essential infrastructure in poor regions and to support to poor people. Budget resources should be used to buy medical insurance for all poor people throughout the country; implement hunger elimination and poverty reduction programmes (Programme 135) and provide loans for hunger elimination and poverty reduction (through the Social Policy Bank) utilising the interest rate compensation scheme.

- The budget should support economic restructuring especially in agricultural production for exports; improvement in livestock breeds and seeds and in restructuring livestock and plantation organisation.

1.3. The budget deficit is under control whilst any state budget overspending is only used for development investment; the budget balance is more stable; the budget deficit is under tight control and government debt and national debt are at secure levels.

1.4. Government and Party policy on economic integration has been implemented:  investment has been encouraged; business and production have been developed; capital accumulation capacity has been increased; competitiveness has been improved; all previous tax and tariff policies have been unified; additional income tax and remittance tax have been abolished and international commitments on reduction of import duties have been implemented -  (tariff on thousands of items have been reduced in accordance with the CEPT/AFTA tariff reduction roadmap; the Vietnam-US Bilateral Trade Agreement, EU-Vietnam Treaty and GATT have been further implemented and hundreds of fees and charges have been reviewed, eliminated or reduced).

Many financial and budget policies, policies on ODA, FDI mobilization and management, policies on financial market development have been amended, supplemented and developed in accordance with the international economic integration policy of the Party and the State. These policies have been changed to match international practices. The State subsidy has been reduced step-by-step and domestic enterprises have been promoted in order to increase their competitiveness, orient their development towards competitive products etc.

1.5. To revise mechanisms of assignment of responsibility and autonomy to administrative and public service units who have reorganised themselves and achieved good results in some sector and localities. Introduce financial policies to encourage further socialisation of public activities which initially mobilises some parts of society to make contributions to the promotion of education, health, culture and sport development.

1.6. To formulate and implement financial mechanisms and policies to speed up the process of reform, renewal and improvement of efficiency of state enterprises (Decree No. 64/2002/ND-CP dated 19 June 2002; Decree No. 187/2004/ND-CP dated 16 November 2004 of the Government etc. Conduct equitisation according to accepted methods of publicity and transparency through auction. Combine the equitisation process with the development of the capital and securities markets. Combine the equitisation process with the process of increasing capital mobilisation for investment, business and product development. Promote the reform of financial management mechanisms towards state enterprises and state capital in enterprises and at the same time establish funds for equitisation, redundant labour, dispose of debts, satisfactorily settle policy issues for employees etc.

1.7. To implement the State Budget Law with the following fundamental objectives:

- Consistently managing the state budget and ensuring the right to decide of the National Assembly. Consistent operation of the Government towards the state budget ensuring the leading role of the central budget in the implementation of national strategic and important tasks and policies of macroeconomic regulation. Supporting difficult areas to carry out the socio-economic development, hunger elimination and poverty reduction. At the same time, strengthening  the decentralisation of management and thereby creating initiative as well as improving the responsibility of local government to deal effectrively and in a timely manner with the tasks of socio-economic development in their areas and speeding up the mobilisation of financial resources for economic development and socio-cultural development.

- Decentralising revenue sourcing and expenditure tasks from the Central budget to the local budget to increase the number of income sources for local budgets and promote local government to take the leading role in balancing its budget. Increasing the number of local authorities who can balance their budgets and make contributions to the central budget. Reduce the number of local authorities receiving budget support from the central budget. Clarifying and improving initiative together with the responsibility of ministries, sectors, localities and units in state asset and budget management. Combining the responsibility for budget management and its use with responsibility for organisation and implementation of professional and political duties, of ministries, sectors, localities and units.

- Reforming the method of budget management and use and combining budget investment with socio-economic efficiency. Carrying out administrative reforms in budget preparation, implementation and accounting. Implementing publicity and practising economy to prevent wastage in the management of the state budget. Closely controlling state revenue collection and payment activities through regulations intended to improve responsibility, inspection, examination and auditing together with the settlement of breaches.

- 1.8. Implementation of recommendations of the 2004 Consolidated Report on Public Expenditure Assessment:

- In the Official Correspondence No. 2276/VPCP-QHQT dated 28 April 2005 of the Government Office, the Prime Minister assigned the Ministry of Finance to coordinate with the World Bank to publish the General Report on Public Expenditure Assessment and take the initiative in coordinating with the Ministry of Planning and Investment and relevant agencies, together with the assistance from the World Bank and donors, to organise the implementation of recommendations provided in the Report and periodically report the results of implementation to the Prime Minister. In implementing the directions of the Prime Minister, the Ministry of Finance and other Ministries cooperated with the WB to publish the Report in Da Nang City on 13 and 14 May 2005 and at the same time carried out the following activities:

+ Establishment of a coordination team including representatives from relevant Ministries and Government agencies to implement the recommendations provided in the report on public expenditure assessment.

+ Based on the recommendations provided in the Report, under the management of the Ministry, to develop and organise a programme to implement the recommendations of the 2004 report on public expenditure assessment.

+ During 2005, the Ministry of Finance has coordinated with the World Bank and groups of donors having the same objectives to study the following 04 important subjects. 1. Evaluation of risks and adverse impacts on the sustainable balance of the current and future budget and solutions for their prevention. 2. Adjustment of budget allocation norms to ensure equality towards the poor. 3. Changes in ODA methodologies, from project-based support to target-based state budget support. 4. Alignment of the government financial statistics in accordance with International practice. These subjects are being urgently studied and proposals are expected to be completed in the first 6 months of 2006.

2. Results achieved from the state budget - financial policy reform in the past:

- Firstly, the system of policy mechanisms and method of continuously renewing and perfected the financial organisation of the State are important tools of the Party and the State to stabilize macroeconomic climate, encourage development investment of the whole society and effectively increase the potential of national revenue.

Over the past five years, the tax system has been continually reformed; the policy of state budget allocation and management decentralisation has been reformed; the establishment of mechanisms and policies of development of the financial market, insurance, financial services, enterprise financial mechanisms, price management policies, financial management policies over land and public assets etc according to the socialist-oriented market mechanism, has made a contribution to stabilising the macroeconomic climate and encouraged resources for socio-economic development.

Secondly, to effectively carry out state budget tasks and improve the state financial potentials; actively change the state budget structure; increase the resources for development investment in socio-economic infrastructure; develop education, culture, health and society; ensure national defence and security; conduct hunger elimination and poverty reduction; carry out salary and wage reforms; increase budget provisions, financial reserves and national foreign currency reserves; balance revenue and budgets in a more stable manner; closely control state budget overspending, government debt and national debt at a level that can ensure the national finance security.

During the 2001-2005 period, state budget revenue increased by 24.1% over its target; the average revenue increase reached 18.4% per year; the mobilisation rate reached 22.5% of GDP(). Domestic revenue (not including crude oil) increased in a stable way by 20.2% per year, the ratio raised from 50.7% in 2001 to 55% in 2005. Regarding revenues from state enterprises, despite the fact that the ratio reduced, the annual revenue increase reached 13.9%. Revenues from private enterprises and foreign invested enterprises increased rapidly and in a stable manner (28.8% per year, amounted to VND37,300 billion in 2005, tripling the revenue of 2001 of VND12,425 billion). The mobilisation of revenue from land resources has seen important changes (increasing  on average 70.2% per year by 2005; a sevenfold increase over 2001). Revenues from petrol and gas significantly increased (on average 18.7% per year) whilst the ratio of imports over experts gradually declined (from 22.1% in 2001 to 17.8% in 2005).

The above results are very important to improving the conditions for reforming collection policies, implementing policies of encouraging saving and business and production development as well as requirements for international integration.

During the 2001-2005 period, stage budget expenditure increased 21.7%. representing 28.7% GDP. The average expenditure increase reached 17.6% per year and the size of the state budget doubled in the 1996-2000 period. The rate of investment expenditure reached 30.6%, together with the mobilisation of treasury bonds for education and government bonds. Expenditure in education increased from 15% to 18% of total state budget expenditure between 2000 and 2005. Expenditure on health, information and culture, hunger elimination and poverty reduction and the implementation of social policies increased 2.2 to 2.5 times. Expenditure on national defence and security has been ensured etc. Budgets have been allocated to all levels of Government for overcoming natural disasters and epidemics. With the implementation of mechanisms to encourage the development of poor areas, the state budget’s implementation of Central resolutions increased its investment to more than VND 40,000 billion for the Central Highlands, Northern mountainous areas, South western areas and difficult mountainous areas. A significant resource has also been used for salary and wage reform. The leading role of the Central budget is ensured whilst at the same time decentralisation is strengthened to create initiative for local budgets. The number of Provinces and centrally governed cities which can balance their budget and make contributions to the state budgets has increased from 5 to 15.

Budget policies have been implemented within an overspending of less than 5% of GDP (less than 3% of GDP as calculated according to international practices). At the end of 2005, the Government outstanding debt represented 36% GDP and national outstanding debt represented 32% GDP which ensures national financial security in the current and medium-term period.

Thirdly, to prepare and implement financial policies to promote the reorganisation, reform and improvement of efficiency of state enterprises. Carry out equitisation in a public and transparent manner through auction. Combine equitisation with developing capital for enterprises, develop the capital and securities markets; promote the reform of the financial management mechanisms of state enterprises and for state capital in enterprises. Formulate equitisation funds for the disposal of debts and systems applicable to employees.

To design and implement the Ordinance on national disaster prevention and improve the tasks of prevention, fighting and overcoming the consequences of natural disasters. Participate in regulating the supply-demand relationship of a number of essential goods and support in a timely maneer, national defence and security in important areas; etc.

Fourthly, the financial market is established which gradually becomes an important channel to mobilise capital for development investment for the whole society.

An institutional system governing the financial and financial services market and accounting and auditing has been established to create a legal framework and encourage and orient the development of the financial and financial service markets in a healthy and efficient manner.

The securities market has been designed and carefully developed to ensure it’s safety. Over the past 5 years the total volume of listed and transacted shares and bonds was more than VND 30,000 billion (around US$2 billion); the financial service market also developed well, increasing 18% per year. Revenues from insurance premiums increased more than 30% per year (4 times the increase of the service sector as a whole) to VND17,000 billion in 2005, representing 2.1% GDP and an increase of more than 2.5 times compared to the year 2001. It annually re-invests in the economy more than tens of thousands of billion Vietnam Dong.

Fifthly, financial reform in the financial - budget field has been strengthened; important results have been achieved in assigning financial autonomy and the application of the financial-budget regime in a public and transparent manner to administrative and public service units in some sestors and localities. The financial policies which encourage socialisation have mobilised part of society’s resources to make contributions to the development of education, health, culture and sports and gymnastics.

Sixthly, external financial systems and international integration have achieved a number of important results. The system of tax policies, financial distribution policies, ODA and FDI mobilisation and management policies and financial market development policies has been established, amended and supplemented to gradually become more aligned with international practices which creates a legal basis and more favourable environment for attracting investment capital and in development of external financial and international integration.

Tax commitments according to the CEPT/AFTA road-map have been implemented. Policies and tariffs have been adjusted according to the process for WTO accession. The mobilisation and management of ODA and FDI resources have made important progress. The financial policies encourage at the highest level (refund of export duties, commercial promotion support, export bonus, increase of state credits for export support etc.) the export of goods and at the same time the national debt have been closely managed to ensure national financial security.

Seventhly, inspection, examination and auditing have achieved certain results in reducing  wastage and loss and in corruption prevention and detection thereby increasing the efficiency of the utilisiation of the state budget and public assets

- Some major elements in the public financial management field which are to be implemented by the end of 2005 and in the first months of 2006, are:

- To constantly maintain and develop the dialogue, consultation and coordination with relevant partners through activities of the Government/donor working groups.

- To continue to implement programmes and projects operating in the public financial management field according to plan.

- To finalise procedures for the preparation and approval of reform projects in the customs field (WB loans) and promote new cooperation relations with potential partners such as USAid, DFID, South Korea etc.

- To concentrate on the successful implementation of the budget revenue and expenditure estimates in 2005. To complete the preparation of the 2006 State budget estimates - quickly determine the size of the State budget; ensure a rational balance between expenditure for development investment, regular expenditure and expenditure for debt payment; increase expenditure on investment in educational, training and vocational development; give priority to an increase of expenditure for medical development, and at the same time, encourage socialisation of mobilisation of resources to cover health insurance for all people in 2010. Ensure national defence and security; speed up hunger elimination and poverty reduction; effectively deal with social issues; implement social development objectives in parallel with economic development; make contributions to the implementation of comprehensive and sustainable growth objectives; increase financial reserve funds, budget provisions and national reserves to take the initiative in confronting natural disasters; provide for important tasks which suddenly arise; reduce adverse impacts of large market fluctuations and world prices; make full payment of foreign and domestic debts as they fall due; successfully implement salary reform and give priority to development investment for mountainous areas and ethnic minorities having difficulties.

- To constantly and urgently implement the recommendations in the report on assessment of public expenditure in the near future. There are more than 100 recommendations in various areas in the 2004 report on the assessment of public expenditure which need to be implemented  through public financial management reform in the 2006-2008 period. This is a large and in depth reform of public finance. In the near future, it is therefore necessary to create closer coordination between relevant government agencies and donors in implementing these important tasks.

- To review and promulgate a system of financial mechanisms and policies to further improve the investment environment and diversify the form of capital mobilisation to meet the requirements for economic development. To encourage investment and development of business and production activities and take strong measures to promote the socialisation of medical, cultural, educational, scientific and technological fields.

- To concentrate on the strict implementation of basic reforms on the organisation and equitisation of state enterprises and solutions for the development of the securities market in order to improve the efficiency and quality of enterprise financial supervision.

- To perfect the land mechanism and implement efficient management in the use of public assets and efficiently operate the management of prices and national land reserves.

- To concentrate on the successful preparation and organisation of the APEC 2006 Conference of Finance Ministers. To improve the efficiency of external financial activities and complete financial and tax systems in order to accelerate the progress of negotiation of WTO accession and implement other commitments in the region.

- To accelerate the practice of economy and wastage prevention; improve the managment efficiency and use of public assets and strengthen financial and budget examination, inspection, supervision and publicity.

- To accelerate the progress of implementation of financial reforms and sector modernisation and organise information conferences on the financial reforms of the Ministry of Finance.

- Performance criteria to ensure the success of the cooperation relationship:

- Coordination is continuously improved through the leadership role of the Ministry of Finance.

- Donors express interest in and satisfaction of the needs for support according to the Governments’ priority order.

- The two way supply of information between the Government and donors is ensured.

projects of technical assistance for the FIELD of public finance management reform

November 2005

| Fields of reforms | Name of projects | Donors | Current status | Date of commencement | Partners |
| --- | --- | --- | --- | --- | --- |
| ### Public finance management | Multi-donor Trust Fund to support modernization of public finance management (MDTF) | 7 donors + WB | On-going | 2/2004 | Mr. Martin Rama/ Mr. Nguyen Van Minh /Mr. Hilmar Thor Hilmarson (WB); Tel: 9346600 Mr. Nguyen Huu Hieu (DFID) Nh-hieu@dfid.gov.uk Nguyen Ba Toan (BTC); Tel: 8240437 Hoang Tiet Kiem (BTC); Tel: 9341540 Nguyen Chi Tuan (BTC); Tel: 9719650 nguyenchituan@mof.gov.vn |
|  | Strengthening capacity of training on public finance management and economic statistics | Government of France | On-going | 2003-2006 1st extension 6/2007 | Mr. Ádrien Laroze (ADETEF) Ms. Nguyen Thi Thanh Ha (BTC);Tel:9719666 phamlienngoc@mof.gov.vn |
|  | Sharing | Government of Sweden | On-going | 11/2003 2008 | Mr. Jame Donovan (Sida); Tel 7260400/7260423 james.donovan@sida.se Mr. Nguyen Quang Ngoc (Sida) Mr. Nguyen Ba Toan (BTC); Tel: 8240437 Mr. Pham Minh Tu (BTC); Tel: 9719646 phamminhtu@mof.gov.vn |
|  | Vietnamese-French Financial Cooperation Program | French Ministry of Finance | On-going | 7/2004-2007 | Mr. Nguyen Thuy Vinh (BTC) ; Tel : 8241433 Ms. Nguyen Ngoc Tram (BTC); Tel 9341540 nguyenngoctram@mof.gov.vn |
| State budget management | Public finance management reform (PFMRP) | WB/DFID | On-going | 10/2003 2008 | Mr. Martin Rama (WB); Tel: 9346600 Mr. Nguyen Van Minh (WB); Tel: 9346600 Mr. Vu Van Truong (BTC); Tel: 9719640 Mr. Nguyen Huu Dung (BTC); Tel: 9719640 nguyenhuudung@mof.gov.vn pfmrp@mof.gov.vn |
|  | State budget reform support (Phase IV) | Government of Germany | On-going | 2004 12/2005 | Mr. Le Quyet Tam (BTC) Ms. Tran Kim Hien (BTC); Tel: 9331250 trankimhien@mof.gov.vn |
|  | Feasibility Study of information and technology development plan (State Treasury ) | USTDA | On-going | 10/2002 12/2005 | Ms. Dennis Zvinakis (USAid) Dzvinakis@usaid.com Mr. Le Quang Dau (BTC); Tel: 9332896 Quangdau60@hotmail.com |
| ### Management of State own enterprises | Improving the capacity of corporate governnance for directors of enterprises | WB/ASEM II | On-going | 1/2004-6/2005 1st extension 30/6/2006 | Mr Nam (BTC); Tel: 9341020 Nguyen_nam1971@yahoo.com |
|  | Support for operations and monitoring of social safety net for redundant workerss (Phase II) | WB/ASEM II | On-going | 6/2004-8/2005 1st extension 31/12/2006 | Mr Hiep/Ms Loan (BTC); Tel: 9716773 phanhoaihiep@mof.gov.vn |
|  | Auditing 100 state own enterprises | WB | Completed | Completed | Mr Tien (BTC); Tel: 9716773 |
| Debt management | Strengthening capacity of financial management of ODA projects through decentralization | ADB | Completed | Completed | Ms. Kanokpan Lao (ADB) Mr Khanh (BTC); Tel: 8262789 |
|  | Strengthening of the external debt management (VIE/01/010) | UNDP | On-going | 2002-12/2005 | Mr. Trinh Tien Dung (UNDP) Mrs. Truong Thai Phuong (BTC); Tel: 9719657 Vie01010@mof.gov.vn |
| Tax administration | Support for VAT and CIT self assessment pilot | IMF | On-going | 2003 Annual work plan | Mr. Nguyen Danh Hao (IMF) Mr Thinh (BTC); Tel: 9712724 Ms Binh (BTC); Tel: 9720847 httbinh@gdt.gov.vn |
| Customs | Technical Assistance to prepare for the customs modernization project | WB (PHRD) | On-going | 7/2004 5/2005 | Mr Tung (BTC); Tel: 8725258 / 0903459898 Ms Nga (BTC); Tel : 09121765/8720104 thtkhq@hn.vnn.vn |
| ### Securities market/ insurance | Development of capital market | WB/ASEM II | On-going | 8/2004-6/2005 1st extension 30/4/2006 | Mr Long (BTC); Tel: 9340750/Ext: 339 thanhlongssc@gmail.com |
| Policy making | Improving capacity of financial accountability for Vietnam | WB | Completed | Completed |  |
|  | Improving the analytical capacity of financial policies for human development (VIE/03/010) | UNDP | On-going | 12/2003 31/12/2006 | Mr. Trinh Tien Dung (UNDP) Ms. Nguyen Thi Bich (BTC); Tel: 9341430 Ms. Nguyen Thuy Vinh (BTC); Tel: 8241433 Mr. Pham Anh Duong (BTC); Tel: 9722208 Phamanhduong2006@yahoo.com |
|  | Improving capacity of legal framework and institutionalization of compensation for re-settlement in Vietnam | ADB | On-going | 2001-12/2005 | Ms. Kanokpan Lao (ADB) Mr Hạnh/Ms An (BTC); Tel: 9719279 trandieuan@mof.gov.vn |
|  | Support on the tax policy making | JICA | On-going | 2004 Report is not available | Mr. Oshikiri (JICA) Mr. Phung (BTC); Tel: 9332829 |
|  | Support on WTO accession | ADB | On-going | 2003 | Ms. Kanokpan Lao (ADB) Mr. Ha Huy Tuan (BTC); Tel: 8240437/ Ms. Le Thuy Linh (BTC); Tel: 9330558 lethuylinh@mof.gov.vn |
|  | Capacity building for financial policies and regime for private business | CEG | On-going | 8/2005-11/2005 | Ms. Duong Hong Loan (ĐSQ Úc) Mr. Tang (BTC); Tel: 9716631/ 0912827791 |
|  | Support to resolve the assets of enterprises | ASEM II | On-going | 8/2004-8/2005 1st extension 30/6/2006 | Tel: 9722196 |
|  | Development of Vietnam agriculture insurance | ADB | On-going | 4/2005-5/2007 | Ms. Kanokpan Lao (ADB) Mr Lai (BTC); Tel 9330038/ Ms Ha (BTC); Tel 8262239 |
|  | EU-Tapviet II | EC | On-going | 9/2005-2008 | Mr. Franciso Fontan /Ms. Vu Thi Tuan Anh (EU Commission) Mr Le Duc Trung (BTC); Tel: 9341540 |
|  | Capacity building for master trainers for financial modernization process 2004-2007 | JICE | On-going | 2004-2007 | Mr. Oshikiri (JICA) Ms Thu (BTC); Tel: 8724164 / 0912826674 |
|  | Insurance training center | AFD | On-going | 10/2004-10/2007 | Mr. Adrien Laroze (ADETEF) Ms Lan Anh (BTC); Tel: 9719658 duanbaohiem@yahoo.com |
|  | Introduction of public auditing standards to Vietnam | WB | On-going | 4/2005-9/2006 |  |
| Partners without specific projects/programmes |  |  |  |  | Ms. Lara Bremn (ĐSQ Canada); Tel: 7345052 larachristine.bremner@international.gc.ca Mr. Michael Kvetny (SIDA – VSRE) Ms Charlotte Laursen (ĐSQ Đan Mạch); Tel: 8231888 chalau@um.dk Mr. Bengt van Loosdrecht (ĐSQ Hà Lan); Tel: 8315650/237 bengt.Loosdrecht@minbuza.nl Ms. Phuong (ĐSQ Hà Lan); Tel: 8315650/237 Phuong.hoang@minbuza.nl Ms Ingrid Norstein (ĐSQ Nauy); Tel: 9742930 ingrid.norstein@mfa.no Ms. Nguyen Hong Giang (ĐSQ Nauy) Ms. Barbara Boni (SDC); Tel: 9346627 barbara.boeni@sdc.net Keith MacKiggan (DFID) k-mackiggan@dfid.gov.uk Mr. Hans Beck (EU Commission); Tel: 9341300/8267 HansAnand.BECK@cec.eu.int |

PUBLIC ADMINISTRATION REFORM PARTNERSHIP

Partnership Note, December 2005

Ministry of Home Affairs

I. GENERAL INFORMATION:

In 2005, public administration reform continued to be one of the central tasks and top priorities in the work agenda of the Government and the Prime Minister. Better progress and positive results were gained in the four areas of the PAR Master Programme for the 2001-2010 Period. This is especially true concerning the development and perfecting of the economic and administrative institutions to be consistent with and suitable for a market economy with a socialist orientation; contributing significantly to the successful implementation of national socio-economic development.

However, in general, public administration reform efforts are still beset with  shortcomings and setbacks, especially concerning its slow speed, poor effectiveness and mismatches in implementation.

II. SUPPORT TO THE P.A.R. MASTER PROGRAMME:

1. Institutional reform

Ongoing activities, outcomes, outputs:

Special attention has been given to the development and issuance of laws on key market institutions; institutions for international integration and for public administration. In 2005, the Government considered and submitted to the National Assembly and the Standing Committee of the National Assembly a series of proposed schemes for development of laws and ordinances, including important ones such as the Laws on Trade (revised); Audit; Customs (revised); Civil Code (revised); Education (revised); Electronic Transactions; Preventing and Combating Corruption;, Creating Savings and Preventing Wastage; Enterprise; Investment; Registration of Properties; etc. In general, all the proposed schemes for legislation development met requirements for feasibility and international economic integration, reflecting the spirit of decentralisation and ensured consistency and relevance with Vietnam’s international commitments.

The task of issuing legal documents of the Government was performed strictly in line with the focus of public administration reform which emphasises the need to provide timely guidance and instructions for the implementation of those laws and ordinances that have started to take effect so that they can quickly be translated into practice.

General stock-taking and review of administrative procedures was identified as one the central tasks for 2005. Under the close steering and guidance of the Government and the Prime Minister, ministries, central sectoral agencies and local authorities have been taking various measures to implement Directive No. 09/2005/CT-TTg of the Prime Minister. This  focuses efforts on such emerging priorities as the application and issuance of land use rights certificates; granting construction permits; business registration; granting licences for investments; imports and exports; registration of local inhabitants; examinations for selection and recruitment of public officials and civil servants, etc. At the same time, to deal with and to overcome obstacles in and deal with the requests of enterprises regarding administrative procedures, the Prime Minister created an Inter-sectoral Working Group charged with handling requests filed by enterprises in 5 provinces and cities of Da Nang, Hanoi, Hai Phong, Ho Chi Minh, Ba Ria – Vung Tau.

Continuing to accelerate the implementation of the one-stop-shop mechanism according to Decision No. 181/2003/QD-TTg dated 4 September 2003 of the Prime Minister, local authorities have been focusing their efforts on leading and guiding the implementation of the one-stop-shop mechanism at the commune level and the conduct of initial reviews, perfecting and scaling-up the one-stop-shop mechanism at the provincial and district levels. In general, positive results have resulted from the implementation of the one-stop-shop mechanism in localities, contributing to changing the mode of operation of the State administrative agencies. Work processes and procedures been improved, making them more scientifically rational. Unwieldy administrative procedures have been simplified. Unnecessary administrative procedures have been abolished and the relationship between the administrative agencies and organizations and citizens have been fundamentally improved.

Future activities, expected outcomes:

- 	Efforts will continue to improve and perfect the institutional framework, mechanisms and policies to make sure that they are suitable and relevant to modern societal development and to better reflect their intention of serving the people and supporting development.

- 	Efforts will continue to renovate the procedural process of development and issuance of legal documents, to overcome compartmentalisation, promoting democracy and mobilising the intellectual resources of the people to improve the quality of legal documents.

- 	In years to come, efforts will be made to completely abolish those administrative procedures that are unwieldy and characterised with red-tape that cause harassment to enterprises and citizens. To simplify new administrative procedures, creating openness, transparency and convenience for citizens and to continue to improve the quality of the one-stop-shop mechanism in administrative agencies at various levels, including the administrative agencies at the central level.

Constraints:

- Although worthwhile efforts were made, some ministries and central sectoral agencies still failed to meet established time schedules and progress in performing their task of developing the institutional framework, especially in the issuance of Decrees to provide concrete and specific guidance for the implementation of laws and ordinances.

- Certain shortcomings and setbacks were noted in the implementation of the one-stop-shop mechanism; such as poor and inadequate accommodation and head offices, especially in communes; mismatches in terms of knowledge, skills and abilities of the personnel working in one-stop-shop centres in receiving and handling requests and delivering results.

2. Reform of the organisational structure of the public administration:

Ongoing activities, outcomes, outputs:

In the reorganisation of the State administrative machinery; ministries, central sectoral agencies and local authorities have improved their guidance and supervision of the review of the organisational structures of their respective organisations in combination with the process of developing proposed schemes of governmental decentralisation in State management; rationalised structures and processes suitable and consistent with given functions and responsibilities and overcoming unnecessary overlaps and duplications. The organisational structure of the machinery has been rationalized in light of Decree No. 171/2004/ND-CP and Decree No. 172/2004/ND-CP. Efforts continue to be made in separating State administrative management from business; production management and the management of public service delivery agencies. This separation is in combination with the reform of administrative procedures based on the one-stop-shop mechanism and based on allocated staffing norms and quotas rationally developed with an optimal number of intermediary levels. Efforts were made to develop and to implement self-governance mechanisms in terms of organisation, finance and personnel for administrative agencies and public service delivery agencies. State administrative agencies paid due attention to the development and issuance of statutes on the organisation and operation, consolidation and strengthening of grassroots organisations; clearly defining the functions, responsibilities and mandates of individual organizations and units. Many ministries, central sectoral agencies and local government authorities continue to implement the revised Decree No. 09/2003/NQ-CP and Resolution No. 16/2000/NQ-CP of the Government regarding downsizing in administrative agencies and public service delivery agencies.

With regard to governmental decentralization in the light of Decree No. 08/2004/NQ-CP.  In 2005 the Ministry of Home Affairs (MOHA) focused their efforts in guiding 22 ministries and sectoral agencies to develop proposed schemes of decentralisation for their respective sectors and areas of jurisdiction, as request by Decree No. 08/2004/NQ-CP. To date, ministries and central sectoral agencies have developed their proposals and these have been approved by the inter-sectoral assessment council. As a result, MOHA has prepared a synthesis report on 166 governmental decentralisation items/issues to submit to the Government for consideration and approval. However, in some cases the process of delegating and handing over functions, responsibilities and powers from and among ministries and central sectoral agencies to local authorities is a difficult one. Therefore, is the process is still not as thorough as is desired and some ministries and central sectoral agencies have still failed to bring forward sufficient measures/solutions and the conditions necessary to fulfil those tasks that have been decentralised and delegated to local authorities.

Future activities, expected outcomes:

-	Efforts will continue to define functions, responsibilities, authority and accountability for all agencies within the administrative system and some tasks and services will be transferred and handed over to enterprises, civil society organizations and NGOs in the spirit of socialisation.

-	 Efforts will continue to complete the identification and implementation of new regulations on central/local governance decentralisation and decentralisation amongst local governments.

Constraints:

-  	Decentralisation in specific sectors and fields and socialisation have been implemented rather slowly and coupled with certain shortcomings and setbacks.

-	 Requirements on organisational restructuring of the machinery towards streamlining, rationalisation, effectiveness and efficiency have still not very strictly and seriously complied with or honored at both central and local levels while the number of intermediary levels tends to increase.

3. Training and upgrading public officials and civil servants:

Ongoing activities, outcomes, outputs:

-	 Ministries, central sectoral agencies and local authorities made focused efforts to improve the quality of public officials and civil servants through implementation of training, retraining, upgrading and personnel management programmes through numerous short and long term training courses suitable to the specific conditions and characters of individual agencies and units. Many local government authorities have introduced methods of training and upgrading public officials and civil servants based on skill profiles of public officials and civil servants and their posts, thereby strengthening their capacity in the execution of particular public tasks and duties.

-	Training and upgrading to improve professionalism and administrative competencies has been combined with equipping public officials and civil servants with ethical values; conducting examinations for selection and recruitment strictly in compliance with rules and regulations; taking initiatives in carrying out research and developing proposed schemes for management and the contingent of public officials and civil servants; applying policies of remuneration and incentives to attract public officials and civil servants to work at the grassroots levels; implementing new rules and regulations on management, recruitment and placement of public officials and civil servants in the spirit of strong decentralisation

.

-  	Ho Chi Minh City has drafted a proposed regulation on piloting competitive examinations for the positions of sub-departmental head and deputy head of some City departments and People’s Committees of urban and rural districts of the City.

-	 A considerable number of agencies, units and local government authorities conducted training and upgrading workshops on public administration reform for such target groups as leaders and managers of provincial/city departments, Chairpersons and Deputy Chairpersons of People’s Committees of the urban and rural districts and townships and leaders of mass organisations.

-  	MOHA, assigned by the Government, conducted 2 PAR training workshops for the Chairpersons and Deputy Chairpersons of People’s Councils and People’s Committees of the 64 provinces and cities throughout the country in June 2005 with a total of 306 participants.

Future activities, expected outcomes:

-	Efforts will be made to enhance professionalism and ethical values for public officials and civil servants, ensuring that the contingent of public officials and civil servants is right-sized and rationally structured, professional and modern.

-	 Efforts will be made to establish systems for public service inspection, systems for individual responsibility and new public service rules and regulations.

-	Efforts will be made to carry out public sector salary reform to the extent that it enables public officials and civil servants and their families to lead a decent life and salary becomes one of the driving forces of the civil service.

Constraints:

-	However, the training and upgrading of public officials and civil servants is still beset with shortcomings and setbacks and has failed to meet requirements. In fact, the knowledge, skills and abilities of public officials and civil servants are not consistent with the new tasks and functions of management in a market economy and international integration. This is especially true of grassroots public officials and civil servants.

4. Public finance reform

Ongoing activities, outcomes, outputs:

-	In general, 2005 saw public finance reform extended and deepened with positive changes in the management of public assets and the State budget.

-	Implementing Decree No. 10/2002/ND-CP dated 16 January 2002 regarding financial mechanisms for income-generating public service delivery agencies and Decision No.   192/2001/QD-TTg regarding expanding piloting efforts in block grants and block staffing. Ministries, central sectoral agencies and local authorities have been intensively guiding and steering the organisation of the implementation of these legal documents. At the same time, the Government also issued some financial mechanisms such as bidding for and contracting out certain types of work and services to the private sector which are currently carried out by State agencies.

-	The results achieved so far in the implementation of Decree No. 10/2002/ND-CP dated 16 January 2002, regarding financial mechanisms for income-generating public service delivery agencies, include (i) 520 out of 797 central level agencies and units, accounting for 62.5% of the total and (ii) 62% of the total of local level units have implemented the said mechanisms.

-	The Government issued Decree No. 132/2005/ND-CP dated 20 October 2005 on the exercise of the rights and obligations of State ownership vis-à-vis SOE’s.

-	Recently, the Government has issued Decree No. 130/2005/ND-CP, dated 17 October 2005 (replacing Decision No. 192) regarding block grants and block staffing for all the agencies and units concerned.

Future activities, expected outcomes:

-	 Efforts will continue to renovate financial mechanisms to be more suitable and relevant to the requirements for administrative agencies and public service delivery agencies and with a view to effectively utilising available resources.

Constraints:

-	Some ministries, central sectoral agencies and local authorities have not been as serious and committed as desired in their efforts to renovate financial mechanisms. A proportion of public officials and civil servants still have a wrong understanding and awareness that to implement block grants and block staffing mechanisms primarily serves to increase resources. They therefore fail to pay due attention to the requirements of renovation of management mechanisms.

5. Other initiatives:

5.1 Socialisation and public sector salary reform

The Government issued Resolution No. 05/2005/NQ-CP dated 18 April 2005 on the acceleration of socialisation in such sectors as education, health, culture, sports and games. Implementation of this Resolution will contribute to overcoming difficulties in State budget shortages; abolishing a sense of reliance on the State budget currently experienced by various public sector agencies and units; opening up new directions for proactive thinking towards the quest to bring domestic resources more fully into play. The non-State sector continues to develop with various new types and models of operation, while the State sector has been experiencing numerous positive changes towards self-governance and self-responsibility/ accountability. However, the rate of socialisation is still felt to be slow compared with its potential. Managerial leadership is still a mismatch between orientations for development, planning and steering/ guiding policy implementation. Mechanisms, policies and guidelines are not as detailed, specified and clear as desired, and are still unsynchronised.

The new public sector salary scheme has been implemented nationwide in spite of the fact that the progress is still slow due to obstacles still existing with the issuance of certain legal documents providing guidance for its implementation. Positive adjustments have been made to overcome mismatches in the former salary system, establishing correlations amongst various salary scales, grades and schedules for various categories of public officials and civil servants in public administration. The Prime Minister issued Decree No. 118/2005/ND-CP dated 15 September 2005 regarding “adjustiment of the common salary base level”, whereby from 1 October 2005 onwards, the common salary base level has been increased from 290,000 VND per month to 350,000 VND per month.

5.2 Strengthening order and discipline in public administration

Ministries, central sectoral agencies and local authorities have been paying due attention to the development and issuance of legal documents governing the strengthening of ethical values and working styles and attitudes of public officials, civil servants and employees. Many practical measures have been taken such as issuance of the Directive on Improving Working Rules and Regulations; paying more attention to local government and grassroots levels; piloting guidelines and policies on civil service inspection in some city agencies and units, etc. However, efforts made to strengthen order and discipline in public administration have not yet resulted in the visible desired changes, whilst weak supervision and limited corrective measures are still reported. The Government is urgently completing preparatory work to issue the Decree on civil service inspection with a view to improving the management of public officials and civil servants and thereby contributing to the development of clean State machinery that operates effectively and efficiently.

5.3 Modernising public administration

Ministries, central sectoral agencies and local authorities have been implementing many activities towards the realisation of the goals set forth for the modernisation of the public administration; making significant changes in the introduction of ICT for managerial leadership in public offices and developing the habits of using ICT to handle day-to-day work. The scheme of computerisation of State administrative management for the 2001-2005 period is being intensively implemented by agencies and units according to established time and progress schedules, contributing to the “step by step” introduction of ICT to managerial leadership and serving the citizens, and linked with PAR efforts towards modernisation. Some ministries, central sectoral agencies and local authorities have been proactive in conducting research and establishing procedural processes to handle work utilising the ISO 9001:2000 on aspects of management and public service delivery. The one-stop-shop mechanism has gained initial encouraging results, “first and foremost” making changes in the model of organising and assigning tasks within the State administrative agencies.

5.4 Renovation of steering and guiding PAR efforts

The Prime Minister issued Directive No. 09/2005/CT-Ttg regarding sustained efforts in accelerating the PAR process. On a monthly basis, the Government gives its steering and guidance instructions and ideas to ministries, central sectoral agencies and local authorities for them to implement PAR tasks that have been mentioned in the Programme in a well-aligned manner. The PAR Steering Committees of ministries, central sectoral agencies and local government authorities have been strengthened and consolidated; operating smoothly and providing recommended measures and solutions on a timely basis for accelerating PAR efforts. The new measure in the steering and guidance of the organisation and implementation of PAR tasks in 2005 is that an inter-sectoral working group has been created and inspection and supervision of civil service operations and thematic supervision activities have been carried out.

However, steering and guidance efforts made by PAR Steering Committees at all levels have not been fully focused and intensive, while insufficient resources and efforts have been allocated to steering and guiding the conduct of overall reviews of PAR implementation and drawing experiences and lessons learning from pilot models for replication purposes.

5.5 PAR advocacy:

Central and local mass media agencies have always been proactive in implementing PAR advocacy activities as per Decision No. 178/2003/QD-TTg of the Prime Minister.

5.6 General review of the implementation of the PAR Master Programme, Phase I (2001-2010):

As per the instructions and guidelines issued by the Prime Minister; to date, 50 provinces and 25 ministries and central sectoral agencies have conducted their general reviews of the implementation of Phase I of the PAR Master Programme. The Secretariat of the PAR Government Steering Committee is in the process of developing a report on the general review of the implementation of Phase I of the PAR Master Programme and the PAR plan for phase II (2006-2010). The PAR Government Steering Committee chaired by the Prime Minister will comment on this report some time between 21 and 25 November 2005. It is expected that an international seminar on the general review of the implementation of phase 1 of the PAR Master Programme and the PAR Plan for phase 2 will be organised by the Government of Vietnam with the participation of the PAR donor community during 29-30 November 2005 to provide an opportunity for all the stakeholders to discuss and provide inputs for the improvement of the reports so that they can be submitted to the Government in its regular meeting scheduled to take place in December 2005.

III. PUBLIC ADMINISTRATION REFORM PARTNERSHIP ACTIVITIES:

In 2005, the PAR Partnership continued to confirm and act as one of the active and dynamic partnerships between the Government of Vietnam and the PAR donor community. It should be acknowledged that through partnership activities, the donor community and Government agencies concerned, including MOHA, which has been playing a role as a lead agency, have together built mutual trust, sharing useful information and experiences for the benefits of both sides. This in turn has encouraged both sides to accelerate their partnership activities for mutual benefit. Partnership activities have become more diverse, combining both formal and informal, bilateral and multilateral activities. In such a spirit, the content, form and way to implement activities have been continually improved to produce greater relevance, effectiveness and efficiency, open and straightforward dialogue and respect for the ideas of both sides.

In general, in 2005 regular meetings and thematic workshops were conducted which help to enhance the value of the PAR partnership. The PAR partnership has provided good opportunities for the donor community to contribute their comments and ideas and to recommend how to improve management and coordination in the course of implementing the PAR Master Programme of the Government; linking PAR efforts with HEPR, socio-economic development and attaining the MDGs and at the same time promoting information and experience sharing amongst 26 PAR donor-funded projects of ministries, central sectoral agencies and local government. An update on these projects is as follows:

- PAR donor-funded projects in Vietnam:

- Support for the Implementation of the PAR 2001-2010 Master Programme –VIE/01/024 (MOHA) co-funded by UNDP, the Netherlands, Canada, Norway, Sweden, Switzerland  (2003-2006)

- Programme Loan to Support the Implementation of PAR Master Program funded by ADB, phase I 2003-2005 with a focus on (i) training program to improve the quality and competency of civil servants, and (ii) program of administrative modernization, including computerization and e-government. ADB also co-financed with France and New Zealand to support the implementation of the Program Loan through 3 technical assistance projects.

- Supporting Administration Reform in Dak Lak Province funded by DANIDA -Denmark phase II (10/2003-9/2007)

- Dong Hoi Urban Development Project (phase III) funded by SDC-Switzerland 1/7/2003-30/6/2006

- Nam Dinh Urban Development Project phase III funded by SDC- Switzerland, 1/7/2003- 30/6/2006

- PAR in Ninh Binh Province phase II (funded by NORAD-Norway), 2005-2008, (approved by the Government)

- Support to PAR in Ho Chi Minh City funded by UNDP phase II VIE/02/010 (2003-2005)

- PAR pilot project in Quang Tri Province, phase I funded by Sida-Sweden 1999-2002, (Plus budget and extending to 31/12/2003). At present, continuing 3 subprojects and preparing for the phase II

- Supporting Democracy Regulations Implementation at Grassroots of Quang Tri Province phase II funded by Finland 12/2004-12/2005

- Support to Can Tho City and Hau Giang Province PAR project funded by Belgium VIE/00/009 1/2002-1/2005. Extending to 28/2/2006

- Project of Enhance the Local Government Capacity at Commune level in Cao Bang Province. Funded by Helvetas-Switzerland. Pilot phase 2003-2004. Extending to the end of 2005

- Project Supporting Public Administration Reform in Cao Bang. Inception and Planning Phase (April 2005- September 2006). Funded by SDC- Switzerland

- Program of Rural Development in Thua Thien Hue, Phase II funded by Finland from April 2004 to April 2008

- Support to the Reform of the Forestry Administration System REFAS phase III  at MARD funded by GTZ- Germany 8/2003-7/2006

- Support to the PAR in MARD phase II  (funded by UNDP) (VIE/02/016)

- Support Project to the Fisheries Programme (SPS). Component 1 “Enhancing the institution of Fishery”  (STOFA) 1999-2010, phase I, 10/99-2004

- Strengthening the Capacity of People’s Elected Bodies in Vietnam phase II (VIE/02/007) at National Assembly funded by UNDP, SDC, CIDA, DFID. 1/1/2003 - 31/3/2008

- Support the Legal Reform at National Assembly funded by Denmark phase II 2001 – 2004. Extended until June 2005

- Support to the National Academy of Public Administration funded by DANIDA- Denmark, 2000-2004. Extended until end of 2005

- Capacity Building for Public Management Training in Vietnam NAPA- SDC (Switzerland) mid- term of phase II 12/2002-5/2004. Extending to 10/2005

- Development of State Audit in Vietnam phase III funded by GTZ - Germany. 1/2004-12/2007

- Capacity Strengthening of Office of the Government funded by Danida - Denmark 1/1/2002  30/6/2004. Extended until May 2005

- Technical support project “OOG in coordinating policies” (TA 4082) support to Loan for computerisation 2003-2005

- Project on “Corruption and Anti-Corruption Solutions in Vietnam”  of Central Commission on Internal Affairs (funded by Sida -Sweden)  2002-2005

- Project “Ministry of Finance on enhancing the capacity to analyse fiscal policies” VIE/03/010 (UNDP) 1/1/2004-31/12/2006

- Project of Vietnamese Academy of Social Sciences (VASS) “Upgrading the capacity of local authorities in planning and managing social-economic development in rural Vietnam  (phase I: 2005-2007) funded by the Netherlands.

Total number: 26 PAR or PAR component projects are under operation in which:

- Projects at the central level: 15 projects at MOHA (2), NAPA (2), MARD (2), ONA (2), Ministry of Fisheries (1), State Audit (1), Central Commission of Internal Affairs (1), OOG (2), MoF (1), VASS (1).

- Projects at provinces: 11 projects at Dak Lak (1), Dong Hoi (1), Nam Dinh (1), Ninh Binh (1), HCM City (1), Quang Tri (2), Can Tho (1), Cao Bang (2), and Thua Thien Hue (1).

- Projects completed in 2005: 12 projects including ADB-MOHA phase I, PAR project in HCM City, PAR in Quang Tri, Grassroots democracy in Quang Tri phase 2, pilot project in Cao Bang, STOFA in Fishery Ministry, Legal Reform in ONA, NAPA-Denmark, NAPA-SDC, OOG-Denmark, ADB-OOG, Central commission on Internal Affairs.

- Projects under formulation and appraisal for government’s approval: 2 projects including SIDA project, phase II (MOHA), PAR project in Quang Tri phase 2.

(2) Coordination and collaboration between the Secretariat under the PAR Government Steering Committee of Vietnam and PAR donors:

Within the framework of the Project VIE/01/024B co-funded by UNDP and multi  donors, “Support for the Implementation of the PAR 2001-2010 Master Programme”, the Secretariat under the PAR Government Steering Committee conducted a meeting with the donor community right from the beginning of 2005 to announce the content of Directive No. 09 by the Prime Minister regarding the priorities and directions for PAR efforts in 2005. This initiative opened up a new and systematic approach for donors to align with the PAR process. On such a basis, donors can integrate and adjust their workplans and activities. This useful initiative should be further promoted and sustained.

(3) Effective use of the PAR Website:

The PAR website – the only website run by the Government covering PAR activities – has been operational since the end of 2004 and continues to be updated and upgraded through exchanges of ideas and suggestions facilitated by the PAR partnership. The PAR website has proven very useful and is a very effective channel of information sharing and a model for advocacy and promotion of PAR models and initiatives. The development of information sharing on good practices and initiatives of PAR posted on the PAR website has been accelerated further following the PAR Partnership Meeting conducted in Nha Trang City in July 2005 so that it can be made operational as soon as possible. To contribute to realising this initiative, a thematic workshop specifically on sharing information and learning from good practices and models of PAR was conducted in Da Nang City in November 2005 by MOHA in conjunction with the PAR Project of MARD. This activity is considered an important thrust in creating favourable momentum for the process of preparing and putting this system into operation.

(4) Enhancing effectiveness and quality of training and upgrading public officials and civil servants:

The question of quality of training and upgrading public officials and civil servants has been paid due attention by PAR stakeholders. Almost all of the PAR donor-funded projects have their own training components. Furthermore, the Government is managing an ADB programme loan project with huge amounts of funds specifically for the training and upgrading of public officials and civil servants; the question of training quality has been recognised as a priority issue. In fact, the Government and the donors have always been paying great attention to training quality and to enhancing the quality of the personnel of public officials and civil servants and allocating significant amounts of funds to training and upgrading work. However, what has been achieved is still modest compared with the funding levels. Based on a common concern expressed by PAR partners, MOHA in collaboration with ADB and the ADB programme loan project conducted a workshop in Hanoi specifically on improving training quality as a follow-up activity of the PAR Partnership Meeting in Nha Trang City in July 2005. The coordination and cooperation between the Government of Vietnam and donors and amongst PAR projects as well as amongst donors has been considered a pressing issue for effective and efficient use of resources allocated to training and upgrading public officials and civil servants.

(5) Post-project evaluation:

SIDA of Sweden conducted a comparative study of the outputs and outcomes of the 2 PAR SIDA-funded projects that have been completed, i.e. the project on personnel management and development of MOHA (completed in 2003) and the PAR project of Quang Tri Province (completed in 2004). MOHA and SIDA agreed on the schedule for a workshop on the evaluation reports of the independent evaluation team regarding these 2 projects in December 2005. This is a good initiative and this has been the first time ever a post-project evaluation has been conducted. Objective and multi-dimensional findings and evaluations and in-depth analyses of the strengths and weaknesses of these projects will contribute significantly to the improvement and enhancement of effectiveness and efficiency of other SIDA-funded projects in particular and other PAR projects in general.

(6) Replication of what has been gained as a result of pilot activities conducted by PAR donor-funded projects

Most of the PAR donor-funded projects are of a pilot character. The results of such pilots need to be considered and assessed for possible replication. This is what all PAR partners are interested in. PAR donor-funded projects need to produce tangible outputs and outcomes and most importantly, they should ensure sustainability and replicability. From the actual replication of the one-stop-shop mechanism on a nationwide scale at provincial, district and commune levels to the self-sustaining mechanism through block grants and block staffing is being replicated throughout the country. Within the framework of Project VIE/01/024, support has been provided to introduce ISO to the administrative system and a result-based management system in Ho Chi Minh City and the outcomes of these pioneering practices now are being replicated in other provinces. Specifically, provinces of Ben Tre and Lao Cai are introducing the result-based management system to their public administration, while 4 provinces of Bac Ninh, Nam Dinh, Ninh Binh and Thai Binh are piloting job descriptions and job analysis which previously was supported by the PAR SIDA-funded project of MOHA (with the exception of Thai Binh province). After successful replication of the model of granting land use certificates pioneered by Quang Tri province to the 4 central provinces, SIDA continues to provide support Tra Vinh province in its efforts to install this model. SDC after having provided support to 9 provinces to implement the one-stop-shop mechanism at the provincial and district levels, now continues to support these provinces to replicate the mechanism to the commune, ward and township levels.

(7) Participation in the review of the implementation of phase I (2001-2005) of the PAR Master Programme, and the PAR plan for the upcoming years:

During the past few months, some PAR donor-funded projects were providing support to their own “client”agencies and local authorities to conduct reviews of their 5 years’ implementation of the PAR Master Programme. Project VIE/01/024 was assisting the PAR SC Secretariat in preparing a Report on the Five Years of Implementing the PAR Master Programme and the PAR Plan for the 2006-2010 Period to be submitted to the Government. An international workshop combined with a PAR Partnership meeting will be organised on 29-30 November 2005 in Hanoi to provide an opportunity for all PAR stakeholders to give their comments and ideas as inputs for the improvement of the PAR review and plan before its submission to the Government. This provides further evidence of the participatory approach, openness, transparency and straightforward dialogue in a constructive and responsible spirit of PAR partners and stakeholders.

(8) Support to the CPRGS:

All the PAR partners are aware of the need to link the implementation of the PAR Master Programme with the CPRGS roll-out. Apart from the UNDP-funded project of HCM City supporting the development of its strategy on PAR and sustainable development, the UNDP-funded project of MARD with additional funds is supporting the development of an Agricultural Extension Centre electronically networked with 13 communes of 10 provinces. SDC-funded projects in Dong Hoi and Nam Dinh are supporting the development of strategies for municipal development of these cities.

However, more debates and discourse need to be given to such topics as linking PAR efforts with socio-economic development, HEPR, grassroots democracy and anti-corruption. They are also the ultimate goals of PAR efforts, i.e. providing an enabling and conducive environment for socio-economic development. However, how to integrate them to produce synergy is still a question for all the stakeholders.

IV. FUTURE ACTIVITIES:

- To continue to improve the content and the way to implement the PAR Partnership activities, making the partnership between the Government of Vietnam and the donor community truly useful and relevant.

- To strengthen the sharing of information and good practices through exchange of knowledge combined with field visits.

- To strengthen coordination and supervision/monitoring of PAR donor-funded projects in order that available resources are more effectively and efficiently utilised.

- To try harder to link PAR projects’ activities with the implementation of the socio-economic development plans, HEPR, and the attainment of the MDGs.

ANNEX

Recently Issued Important Legal Documents

Relatting to PAR and the Administrative Apparatus

- Decree No. 115/2005/ND-CP dated September 5, 2005 by Government
Providing for the autonomy and self - management mechanism applicable to public scientific and technological organisations

- Resolution No. 05/2005/NQ-CP dated April 18, 2005 by Government
On stepping up socialisation of educational, healthcare, cultural, physical training and sport activities

- Directive No. 09/2005/CT-TTg dated April 5, 2005 by Prime Minister
On Further Stepping up the Administrative reform

- Decree No.203/2004/ND-CP dated December 14, 2004 by Government
Prescribing the minimum wage level

- Decision No 2343/QĐ-BNV dated December 8, 2004 by the Minister of Home Affairs
Regarding the Establishment of the Public Administration Reform Website of the Ministry of Home Affairs

- Decree No. 172/2004/ND-CP dated September 29, 2004 by Government
Prescribing the organisation of the professional agencies under the People's Committees of the rural and urban districts as well as provincial capitals and cities

- Decree No.171/2004/ND-CP dated September 29, 2004 by the Government
Prescribing the organisation of professional agencies under the People's Committees of the provinces and centrally-run cities

- Government Resolution No 08/2004/NQ-CP on 30/6/2004
On continuing to strengthen governance decentralisation from central to provincial government and centrally- managed cities.

- Programme on the renovation of the financial management mechanism for the state administrative agencies and public service delivery agencies Phase 2004-2005

- Law on the Organisation of the People Committee and People

- Prime Minister’s Decision No 181/2003/QD-TTg on 04/9/2003
On the issuance of the Regulation to implement the ‘One-Stop Shop’ mechanism in local administrative agencies

- Prime Minister’s Decision No 178/2003/QD-TTg on 03/9/2003
On the approval of the Advocacy Project for the Public Administration Reform Master Programme 2001-2010

- Project on the renovation of the management modality and modernisation of the State administrative system, Phase I (2003-2005)
Promulgated together with the Prime Minister's Decision No.169/2003/QD-TTg of August 12, 2003

- Government Decree No 79/2003/ND-CP on 07/7/2003
On the issuance of the Regulation on democracy implementation at the commune level

- Government Decree No 71/2003/ND-CP on 19/6/2003
On decentralisation of staff, administration and public service delivery management

- Ordinance on Cadres and Civil Servants

- Programme on redefining roles, functions and organisational structure of the agencies in the state administrative system, Phase I (2003-2005)

- Programme on developing and improving the quality of civil servants and public cadres, Phase I (2003-2005)

- Government Decree No 30/2003/ND-CP on 01/04/2003
    Regulating the functions, duties, authority and organisational structure of Government-affiliated agencies

- Government Decree No 86/2002/ND-CP on 05/11/2002
    on regulating the functions, duties, authority and organisational structure of ministries and ministerial agencies

- Government Decree No 10/2000/ND-CP on 16/01/2002
On the financial mechanism applying for income-generating public service delivery agencies

- Law on Government Organisation

- Prime Minister’s Decision No 192/2000/QD-TTg on 17/12/2001
On extending block staffing and block grants for the state administrative agencies

- The Public Administration Reform Master Programme 2001-2010

- Project on the computerisation of the state administrative management Phase 2001-2005

- Prime Minister’s Decision No 74/2001/QD-TTg on 07/5/2001
On the approval plan for training and retraining cadres and civil servants for the period 2001-2005

- Government Decree on 12/2001/ND-CP 27/3/2001
On the reorganisation of professional agencies belonging to the People’s Committee of provinces and centrally-managed cities, the People’s Committee of districts, rural districts and townships belonging to provinces

- Government Resolution No 38/CP on 4/5/1994
On taking a step in reforming administrative procedures for dealing with people and organisation affairs

- Government Resolution No 16/2000/NQ-CP on 18/10/2000
On staff down-sizing in administrative agencies and public service delivery agencies

- Government Resolution No 09/2003/NQ-CP on 19/06/2003 on the modification and amendment of Government Resolution No 16/2000/NQ-CP on 18/10/2000
On staff down-sizing in administrative agencies and public service delivery agencies on 30/6/2004

Prime Minister's Directive 33/2004/CT-TTg dated 23 September 2004 on the Preparation of the 5-Year Socio-Economic Development Plan

Upon instruction of MPI, Japan and the United Nations Industrial Development Organization (UNIDO) act as co-chairs of the “Partnership Group for SME Promotion and Private Sector Development” in Vietnam

The BTA covers much of what is in the WTO, with stronger investment requirements and limited requirements on agricultural support, tariff levels, subsidies and anti-dumping. STAR provides legal analysis and supports workshops and references to develop legal and policy reforms to conform with BTA and WTO requirements and to benefit from international best practice, as  requested by our Steering Committee, in the following areas: for trade in goods -- customs reform, commercial arbitration, contract and property law, trading rights, tariffs, VAT, special consumption taxes, non-tariff barriers, SPS, TBT, safeguards;  for IPR includes -- conforming with 5 international conventions on IPR and IPR enforcement in TRIPS, which includes: strengthening court procedures and skill levels, strengthening  remedies and enforcement of judgments, improving customs border measures,  and publication of court decisions; work on services includes -- complying with GATS and Annexes on Telecommunications, Financial Services and natural persons, the Telecoms Reference Paper, and liberalization of joint venture and other market access for more than 30 services, including banking, insurance, telecommunications, distribution, professional services, construction services, education services, health-related services, and travel-related services; work on investment includes -- TRIMS plus export requirements, strengthened investment protections, investment dispute settlement processes (ICSID), streamlining investment procedures, eliminating discriminatory pricing, certain corporate governance issues, and shifting most investment licensing to a registration rather than an evaluation process; and work on transparency includes -- rules for publishing laws of general application at the national and local levels, support for an Electronic Official Gazette, encouraging public comment of draft laws, and the right to appeal administrative actions, which includes the development of administrative tribunals and procedures and court capabilities and procedures.  STAR also supports the development of economic analysis and reports on the impact of the BTA, efforts to raise the public awareness and understanding of the BTA and WTO, and training for officials, judges, lawyers, and business leaders.

It is anticipated that the FSSP Program Framework, with its nine Result Areas, will be replaced by the forthcoming National Forest Strategy (NFS, 2006-2020), as the key document for collaborative support and implementation by both national and international partners.

RRMC: Regional road management company

PRMC: Provincial road management company

RRMU: Regional road management Unit

PDOT: Provincial Department of Transport, which is under a provincial people’s committee

Prepared by Pham Khanh Toan, Deputy Director of ICD-MOC,VUF Coordinator

jointly prepared by Nguyen Minh Phuong (VIE/02/015 TA to LSDS) and Luu Tien Dung (UNDP)

The matrix was consolidated by Nguyen Minh Phuong (VIE/02/015 TA to LSDS) and Luu Tien Dung (UNDP) with contributions from the group members

(?) Không bao gồm các khoản thu để bù lỗ kinh doanh xăng dầu nhập khẩu, lợi tức sau thuế từ hoạt động dầu khí để đầu tư các công trình trọng điểm ngành Dầu khí.